## General Road Works
Links to further information
| Traffic Scotland - realtime information on trunk roads including Edinburgh City Bypass |  |  |  | Details of Ward and Locality boundaries
SE Scotland trunk roads maintenance by BEAR Scotland
Key
| Transport for Edinburgh - Lothian Buses and Edinburgh Trams |  |  |  | New or updated information in this version
Underlined entries contain links to maps or further information
Edinburgh Travelling Safely measures and Low Traffic Neighbourhoods
| Our social media channels: |  | X (formerly Twitter) | Facebook | Threads
Excel - use the drop-down arrows to sort by any column. PDF - use CTRL + F to search for any keyword. |  |  |  | NB this is not intended to be a list of all the roadworks in Edinburgh. Please refer to the Scottish Roadworks Register website for basic information on all registered roadworks
Ward | Locality | Street | Location | Contractor / works description | Measures in place | Start | Finish
Almond | North West | CLIFTONHALL INDUSTRIAL ESTATE |  | City of Edinburgh Council - footway resurfacing | Temporary traffic lights (affecting the main road for the first 4 weeks then moving into the industrial estate) | 2025-01-20 | 2025-08-15
Almond | North West | MAYBURY ROAD | At Craigs Road | Construction of signalised junction | Phase 1 - Craigs Road closed on west side of Maybury Road from 06/05/25 12/05/25; Phase 2 - contraflow for removal of traffic island from 26/05/25; Phase 3 - Maybury Road closed southbound, estimated start 06/10/25; Phase 4 - temporary traffic lights, estimated start 10/12/25. | 2025-05-06 | 6 months estimated
Almond | North West | QUEENSFERRY AREA |  | Cruise liner visits. Click cell for full schedule | For each visit: prohibition of motor vehicles on Bankhead Road south of Station Road, parking restrictions as signed on Hawes car park, Newhalls Road and Hawes Brae | 2025-05-07 | 2025-10-09
Almond | North West | SHORE ROAD | At Hopetoun Road | Clancy Docwra - sewer repairs for Scottish Water | Temporary traffic lights | 2025-07-09 | TBC
Almond | North West | A89 / A8 | Between Broxburn and Gogar | City of Edinburgh Council - ground investigation surveys (starting between Broxburn viaduct and Newbridge) | Primarily nightshift works with lane closures and temporary bus stops as required. Some off-peak daytime works TBA. | 2025-07-14 | Late September 2025
Almond | North West | MUIRHOUSE GARDENS | Between Pennywell Gardens and 39 Muirhouse Gardens | City of Edinburgh Council - carriageway surfacing | Road closed (weekdays only) | 2025-07-14 | 18/07/25 22/07/25
Almond | North West | STATION ROAD, QUEENSFERRY |  | City of Edinburgh Council - carriageway surfacing | Week 1 (Monday - Friday) - temporary traffic lights between The Loan and Burdock Road; Week 2 (Monday - Wednesday) - road closed between Forth Terrace and Bankhead Road. | 2025-07-14 | 2025-07-23
Almond | North West | B800 QUEENSFERRY ROAD | Between M90 bridge and Milton Farm Road | BRM Utilities for Vodafone - cabling | Temporary traffic lights | 2025-07-21 | 2025-07-21
Almond | North West | BAIRD ROAD / HARVEST ROAD | Several locations between Norton House and Freelands Road | City of Edinburgh Council - remedial works and ironwork repairs | Temporary traffic lights | 2025-07-21 | 2025-07-25
Almond | North West | MUIRHOUSE PLACE WEST |  | City of Edinburgh Council - carriageway resurfacing | Road closed | 2025-07-21 | 2025-07-25
Almond | North West | A90 | Burnshot to Dalmeny | Transport Scotland - replacing VMS | Road closed to northbound traffic 9pm - 6am | 2025-07-22 | 2025-07-23
Almond | North West | FERRY ROAD | At Groathill Road North | Telecoms work | 3-way temporary traffic lights 8pm - 7am | 2025-07-22 | 2025-07-23
Almond | North West | QUEENSFERRY AREA |  | Ferry Fair Festival events | High Street closed between The Loan and McIver's Brae: 8am - midday on 03/08, 2pm - 10.30pm on 08/08, 9am - 6.30pm on 09/08, 8am - midday on 10/08. Burgess Road closed 10am - midday on 09/08. Rolling road closures thoughout the town 10.15am - 12.30pm on 09/08. | 2025-08-03 | 2025-08-10
Almond | North West | STATION ROAD, DALMENY | At the rail bridge | Network Rail - bridge inspection | Road closed 10pm - 6am | 2025-08-13 | 2025-08-14
City Centre | South East | CALTON ROAD | Between Waverley station access and New Street | Unsafe rock face, restrictions in place to provide safety zone | Temporary traffic lights. Shuttle system with full-time traffic signals in operation | 2018-12-01 | Ongoing
City Centre | South East | NORTH BRIDGE |  | City of Edinburgh Council / Balfour Beatty - bridge refurbishment | East footway closed, pedestrian access via west footway. One traffic lane open in each direction (as of 21/04/23). | 2020-02-15 | Summer 2026
City Centre | South East | TARVIT STREET |  | Redevelopment of King's Theatre | Tarvit Street closed between Home Street and Drumdryan Street. Drumdryan Street northbound only. NCR 75 closed, cycle diversion signed via Valleyfield Street | 2023-02-14 | Late 2026
City Centre | South East | DEVON PLACE | Between West Coates and no. 4 | For Ogilvie Construction | Road closed to southbound traffic. | 2023-06-06 | September 2025
City Centre | South East | LAWNMARKET AREA |  | City of Edinburgh Council - road, pavement and drainage improvements, including relaying setts. (click cell for more details.) | Phase 2 from 02/12/24. Roundabout junction at Upper Bow / Johnston Terrace closed. Existing Lawnmarket one-way order rescinded to allow access and egress at George IV Bridge. Small-vehicle access to Castlehill via Ramsay Lane. | 2024-09-23 | 2025-07-25
City Centre | South East | ROSEBERY CRESCENT |  | Scottish Water - sewer repairs | Road closed | 2025-01-25 | 15/05/25 August 2025 TBC
City Centre | South East | ROSE STREET SOUTH LANE | Section between Frederick Street and Hanover Street, east leg | Building development | Road closed | 2025-06-06 | 2025-08-29
City Centre | South East | ABBEYMOUNT | At Regent Road / Montrose Terrace | SGN - gas leak repairs | 4-way temporary traffic lights, Carlton Terrace Brae closed | 2025-06-11 | 05/08/25 estimated
City Centre | South East | CALTON ROAD | Between Waverley station access and New Street | Scottish Water - ironwork repair Postponed due to gas main repairs at Abbeymount | Road closed | 2025-06-22 | 2025-06-22
City Centre | South East | ALBANY LANE | Between Barony Street and Albany Street Lane | Scottish Water - sewer repairs | Road closed | 2025-06-23 | 18/07/25 25/07/25
City Centre | South East | WATERLOO PLACE | Between Leith Street and Calton Hill | GPR survey Postponed due to SGN work at Abbeymount | Road closed 8pm - 6am | 2025-06-23 | 2025-06-24
City Centre | South East | CALTON ROAD | At Leith Street | Crane lift Postponed due to gas main repairs at Abbeymount | Road closed | 2025-06-29 | 2025-06-29
City Centre | South East | WEST COATES |  | Energetics - utility connection | Temporary traffic lights, Devon Place closed | 2025-07-07 | 20/07/25 25/07/25
City Centre | South East | NORTH ST DAVID STREET |  | Comex2000 for Virgin Media Not carried out, new date TBA | Lane closures / contraflow, St Andrew Square north leg closed. 8pm - 6am | 2025-07-15 | 2025-07-16
City Centre | South East | ABBEYHILL / ABBEYMOUNT JUNCTION | At the rail bridge | Network Rail - bridge inspection Postponed due to extended SGN repairs | Roads closed 9pm - 6am | 2025-07-17 | 2025-07-18
City Centre | South East | GEORGE IV BRIDGE | Just north of Chambers Street | Scottish Power - new service connection | Northbound inside lane closed | 2025-07-17 | 2025-07-25
City Centre | South East | PRINCES STREET | Shandwick Place to Lothian Road | Siemens for Edinburgh Trams - track maintenance | Road closed to eastbound traffic (and Queensferry Street closed at Princes Street) 12.20am - 4.20am for 2 mornings | 2025-07-22 | 2025-07-23
City Centre | South East | QUEENSFERRY STREET |  | GPR survey | Road closed to citybound traffic 11.30pm - 6am | 2025-07-23 | 2025-07-24
City Centre | South East | GEORGE STREET | Between Frederick Street and Hanover Street | George Street Festival | Road closed (from 11pm on 24/07/25) except for cycles. Loading permitted 6am - 8am daily. | 2025-07-24 | 2025-08-26
City Centre | South East | MORRISON STREET | Semple Street to Gardner's Crescent | Scottish Water - ironwork repair | Road closed to westbound traffic 7pm - 7am | 2025-07-24 | 2025-07-25
City Centre | South East | BLAIR STREET | At South Bridge | Summertime Streets 2025 | Road closed. Normal one-way order rescinded. | 2025-07-28 | 2025-08-26
City Centre | South East | COWGATE | Between Candlemaker Row and Blackfriars Street | Summertime Streets 2025 | Road closed to motor vehicles 3pm - 5am each day | 2025-07-28 | 2025-08-26
City Centre | South East | EDINBURGH CASTLE AREA |  | Royal Edinburgh Military Tattoo | Road closures as follows: Castlehill: 6pm - 11pm on 30/07/25 then 4.30pm - midnight each day. Mound Place, Ramsay Lane, Ramsay Garden, Johnston Terrace, Lawnmarket at Castlehill, Upper Bow: 5pm - midnight on 30 and 31/07/25, 5.30pm - midnight each weekday from 01/08/25, 4pm - midnight each weekend day. St Giles' Street, Lawnmarket / High Street between Parliament Square and George IV Bridge: 7pm - midnight each weekday, 7pm - 9pm each weekend day. King's Stables Road: 7pm - midnight each week day, 4.15pm - midnight each weekend day. | 2025-07-30 | 2025-08-23
City Centre | South East | CENTRAL EDINBURGH |  | Parade | Multiple road closures 11am - 3pm. Click cell for full details | 2025-08-09 | 2025-08-09
City Centre | South East | REGENT ROAD | At the old Royal High | BT - ironwork repairs | 2-way temporary traffic lights | 2025-09-08 | Up to 5 days
City Centre | South East | DEVON PLACE | Between the south east corner and Devon Gardens | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-09-08 | 2025-09-17
City Centre | South East | ROSE STREET SOUTH LANE | Section between Castle Street and Frederick Street | SGN - gas main disconnection | Road closed | 2025-09-08 | 2025-09-26
City Centre | South East | WEST MAITLAND STREET |  | Scottish Water - ironwork repair | Citybound lane closure, bus stops closed. 12.15am - 4.30am. | 2025-09-13 | 2025-09-13
City Centre | South East | VALLEYFIELD STREET |  | Scottish Water - service connection | Road closed except for cycles | 2025-09-15 | 2025-09-24
City Centre | South East | ROSE STREET SOUTH LANE | Section between South Charlotte Street and Castle Street | Clancy Docwra for Scottish Water | Road closed | 2025-09-29 | 2025-10-08
Colinton / Fairmilehead | South West | WINTON DRIVE |  | Water main connection | Temporary traffic lights | 2025-07-14 | 2025-07-25
Colinton / Fairmilehead | South West | SWANSTON AVENUE | At Swanston Drive | Scottish Water - mains repairs | 4-way temporary traffic lights | 2025-07-22 | 2025-07-23
Colinton / Fairmilehead | South West | WINTON DRIVE | At Winton Terrace | Clancy Docwra - mains repairs for Scottish Water | 4-way temporary traffic lights | 2025-08-05 | 2025-08-05
Colinton / Fairmilehead | South West | WATERFIELD ROAD | Between Scottish Water office and Fairfield Gardens | Scottish Water - manhole repair | Road closed | 2025-08-07 | 2025-08-07
Colinton / Fairmilehead | South West | BONALY CRESCENT | Between Laverockdale Loan and Bonaly Terrace | Openreach - ducting installation Dates and details TBC | Road closed | 2025-08-14 | 2025-08-15
Colinton / Fairmilehead | South West | MOUNTHOOLY LOAN | Between Galachlawside and Galachlawshot | Clancy Docwra for Scottish Water - pipe repairs Details TBC for local access | Road closed | 2025-08-25 | 2025-09-05
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Murrayfield | Scottish Water - major works to install combined sewer overflow (CSO) | Temporary traffic lights. Ormidale Terrace closed. Westbound bus stop closed, please use the next stop. | 2025-06-08 | End of 2025
Corstorphine / Murrayfield | North West | CLERMISTON ROAD | At Old Kirk Road | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2025-07-16 | 24/07/25 estimated
Corstorphine / Murrayfield | North West | MURRAYFIELD and SURROUNDING AREA |  | Oasis concerts at Scottish Gas Murrayfield (8, 9 and 12/08/25) | Road closures before and after the event affecting Roseburn, Murrayfield, Haymarket areas plus West Approach Road afterwards. Details TBC | 2025-08-08 | 2025-08-12
Corstorphine / Murrayfield | North West | MURRAYFIELD and SURROUNDING AREA |  | AC / DC concert at Scottish Gas Murrayfield | Road closures before and after the event affecting Roseburn, Murrayfield, Haymarket areas plus West Approach Road afterwards. Details TBC | 2025-08-21 | 2025-08-21
Corstorphine / Murrayfield | North West | COLTBRIDGE TERRACE |  | Clancy Docwra for Scottish Water | Road closed to through traffic nos. 22 - 26 | 2025-09-01 | 2025-09-10
Craigentinny/ Duddingston | North East | ABBEY LANE | At Abbeyhill | Graham Construction - development works | Road closed | 2024-01-09 | End of October 2025
Craigentinny/ Duddingston | North East | DUDDINGSTON LOW ROAD |  | Historic Environment Scotland - risk of rock falls | Road closed to vehicles until Monday 17/03/25. Road closed to all path users from Tuesday 18/03/25, pedestrian and cyclist diversion via Innocent railway path. | 2025-03-15 | Until further notice
Craigentinny/ Duddingston | North East | RESTALRIG AVENUE | Between Loganlea Drive and Loganlea Avenue | Scottish Power - network upgrade | Temporary traffic lights | 2025-03-24 | 07/05/25 05/06/25 04/08/25
Craigentinny/ Duddingston | North East | LONDON ROAD | At Meadowbank Terrace | Clancy Docwra for Scottish Water - sewer repairs | 3-way temporary traffic lights | 2025-07-21 | 2025-07-25
Craigentinny/ Duddingston | North East | MEADOWFIELD DRIVE | At Lady Nairne Crescent | City of Edinburgh Council - junction realignment and resurfacing | Temporary traffic lights, Lady Nairne Crescent closed | 2025-07-28 | 2-3 weeks
Craigentinny/ Duddingston | North East | RESTALRIG ROAD SOUTH | Between the rail bridge and Restalrig Avenue | Virgin Media - clearing blocked ducts | Overnight temporary traffic lights | 2025-07-28 | 2025-07-29
Craigentinny/ Duddingston | North East | SEAFIELD ROAD | At Seafield Street | Clancy Docwra for Scottish Water - sewer repairs | 3-way temporary traffic lights | 2025-07-28 | 03/08/25 estimated
Craigentinny/ Duddingston | North East | DUDDINGSTON AREA |  | The Edinburgh International Cup at Cavalry Park | Roads closed 7am - 8pm each day (except for local access): The Causeway, Old Church Lane, Cavalry Park Drive. | 2025-08-01 | 2025-08-03
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Clark Contracts - building development | Section of north footway and eastbound cycle lane closed. | 2025-09-01 | December 2027
Craigentinny/ Duddingston | North East | WILLOWBRAE ROAD | Between Duddingston Mills and Northfield Broadway | Clancy Docwra for Scottish Water - lead renewal | Lane closures / contraflow. No right turn from the car dealership | 2025-09-08 | 2025-09-17
Craigentinny/ Duddingston | North East | WILLOWBRAE ROAD | At Willowbrae Gardens | Scottish Water - manhole repair Date TBC | 4-way temporary traffic lights | 2025-09-09 | 7am 10/09/25
Craigentinny/ Duddingston | North East | RESTALRIG ROAD SOUTH | Between the rail bridge and Restalrig Avenue | Network Rail - vegetation clearance | Road closed 10pm - 6am | 2025-09-15 | 2025-09-16
Drum Brae / Gyle | North West | GLASGOW ROAD | Citybound approach to Drum Brae roundabout | Clancy Docwra - repairs for Scottish Water | Inside lane closed | 2025-07-17 | 20/07/25 estimated 21/07/25
Drum Brae / Gyle | North West | DUART CRESCENT |  | City of Edinburgh Council - carriageway resurfacing | Road closed. Durar Drive and Dochart Drive closed as required | 2025-07-21 | 2025-08-03
Drum Brae / Gyle | North West | LOCHSIDE AVENUE | At Lochside Crescent | Siemens for Edinburgh Trams - track maintenance | Road closed to westbound traffic 12.30am - 5am each morning. Amendment to schedule - road will be closed to eastbound traffic on the finla morning (06/08/25). | 2025-07-27 | 2025-08-06
Drum Brae / Gyle | North West | SOUTH GYLE ROAD | At the rail bridge | Network Rail - renewing rail bridge | Road closed. Access to the station car park via South Gyle Broadway - Gogarloch Road. | 2025-07-28 | April 2026
Forth | North West | CRAIGHALL ROAD | Between Craighall Avenue and Grandville | Refurbishment of Trinity Academy | Road closed | 2025-06-30 | May 2028
Forth | North West | WARDIE CRESCENT | At Granton Road | Scottish Water - repairs to burst pipe | Road closed | 109/07 | TBC
Forth | North West | AFTON TERRACE | At Cargil Terrace | SGN - gas main renewal | 2-way temporary traffic lights, Wardie Road (south leg) closed | 2025-07-28 | 2025-08-31
Forth | North West | LOWER GRANTON ROAD | At Trinity Road | BT - manhole repair | 3-way temporary traffic lights | 2025-08-04 | 2025-08-06
Forth | North West | WATERFRONT AVENUE | On the bend just east of Waterfront Broadway | Scottish Water - ironwork repair | Temporary traffic lights | 2025-08-20 | 2025-08-20
Forth | North West | GRANTON ROAD | At Boswall Green | Openreach Rescheduled from 14/07/25 | Off-peak 4-way temporary traffic lights | 2025-08-27 | 2025-08-28
Forth | North West | ROYSTON TERRACE | At Inverleith Row | Clancy Docwra for Scottish Water | Road closed to through traffic. Existing one-way order rescinded for duration of works. | 2025-09-08 | 2025-09-17
Fountainbridge/ Craiglockhart | South West | HARRISON ROAD | At the dog-leg bend where it crosses the cycle path and at the canal bridge | City of Edinburgh Council - bridge repairs | Road closed. From 30/06/25 for 4-5 months - closure of both topside footways for demolition of the remaining existing (northern) bridge structure and installation of support system to facilitate construction of the new deck. The cycle path beneath the bridge will be closed from mid-July. | 2025-02-18 | Ongoing
Fountainbridge/ Craiglockhart | South West | DUNDEE STREET | At Viewforth | Cityfibre - clearing blocked cable ducts Work postponed due to ongoing footway works on Gilmore Place, provisional start date 28/07/25. | Temporary traffic lights, Viewforth closed | 2025-07-21 | 1 week estimated
Fountainbridge/ Craiglockhart | South West | OGILVIE TERRACE |  | Crane lift | Road closed to through traffic 8am - 6pm | 2025-07-24 | 2025-07-24
Fountainbridge/ Craiglockhart | South West | COLINTON ROAD | At Craiglockhart Road North | Clarke Telecom - trial holes | 2-way temporary traffic lights | 2025-07-25 | 2025-07-25
Fountainbridge/ Craiglockhart | South West | LANARK ROAD | At Water of Leith visitor centre | Scottish Power - mains disconnection | Westbound inside lane closed | 2025-09-15 | 2025-09-26
Fountainbridge/ Craiglockhart | South West | HUTCHISON PLACE | At Slateford Road | Scottish Water - ironwork repair | Road closed | 2025-09-29 | 2025-09-29
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Coxfield | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-09-29 | 2025-09-29
Inverleith | North West | QUEENSFERRY ROAD | At Blackhall Dip | City of Edinburgh Council - footway resurfacing | Westbound lane closure on the main carriageway, Gardiner Road and Columba Road closed in turn. | 2025-06-16 | 2025-07-25
Inverleith | North West | INVERLEITH ROW | Between Inverleith Terrace and Eildon Street | BT Circet - pole replacement Not carried out, new date TBA | Road closed 8am - 4pm. | 2025-06-22 | 2025-06-22
Inverleith | North West | ARBORETUM AVENUE |  | Scottish Water - mains upgrade | Currently 3-way temporary traffic lights at Inverleith Terrace. Arboretum Avenue will be closed for periods, dates TBC. | 2025-07-14 | 2025-09-14
Inverleith | North West | CANONMILLS |  | Scottish Power - cable fault | Warriston Road closed north of Canon Court. Temporary traffic lights at Brandon Terrace / Inverleith Row junction. | 2025-07-16 | TBC
Inverleith | North West | WARRISTON TERRACE |  | Clancy Docwra for Scottish Water | Road closed | 2025-08-05 | 2025-08-14
Inverleith | North West | COMELY BANK ROAD | At East Fettes Avenue | Scottish Water - mains survey | 4-way temporary traffic lights 8am - 1pm approximately | 2025-09-07 | 2025-09-07
Leith | North East | LINDSAY ROAD BRIDGE | Pedestrian / cycle bridge between Nicholfield and Lindsay Road main carriageway | City of Edinburgh Council - public safety measure | Bridge closed, pedestrian and cycle diversion as signed. Hawthornvale Path beneath remains open | 2021-12-15 | Until further notice
Leith | North East | GREAT JUNCTION STREET | Between Foot of the Walk and Henderson Street | City of Edinburgh Council - construction of segregated cycle lane | One lane open in each direction, temporary pedestrian crossing facility at Pirrie Street. Permanent traffic signals at Henderson Street back in operation from Tuesday 15/07/25. | 2024-11-18 | Summer 2025
Leith | North East | HENDERSON STREET | Between Great Junction Street and Yardheads | City of Edinburgh Council - construction of segregated cycle lane | Lane closures, parking restrictions, temporary traffic lights if required. One-way (southbound) system with northbound access via Cables Wynd from 19/03/25. | 2024-12-03 | Summer 2025
Leith | North East | NEWHAVEN AREA |  | Cruise liner visits. Click cell for full schedule | Parking restrictions as signed on Pier Place and Newhaven Place for each visit | 2025-04-02 | 2025-09-27
Leith | North East | QUEEN CHARLOTTE LANE | Beyond the nursery car park | Scottish Power - cable jointing | Road closed | 2025-07-21 | 2025-08-10
Leith | North East | NORTH JUNCTION STREET | At Ferry Road / Great Junction Street | Scottish Water | 4-way temporary traffic lights 8pm -7am | 2025-07-25 | 2025-07-26
Leith | North East | DUNCAN PLACE | Between Duke Place and Wellington Place | Event | Road closed 7am - 7pm | 2025-08-23 | 2025-08-23
Leith | North East | BERNARD STREET | At Commercial Street / Shore | Scottish Water - manhole repair | 4-way temporary traffic lights 7pm - 7am | 2025-08-29 | 2025-08-30
Leith | North East | GILES STREET | At Henderson Street | Clancy Docwra - sewer repairs for Scottish Water | Road closed | 2025-10-06 | 2025-10-13
Leith Walk | North East | DRYDEN STREET | Between Pilrig Street and Hawthornden Place | Scottish Power - network upgrade | Road closed to westbound traffic | 2025-06-06 | 2025-07-23
Leith Walk | North East | EASTER ROAD | Between Sunnyside and Drum Terrace | Clancy Docwra for Scottish Water Work cancelled | 4-way temporary traffic lights | 2025-07-20 | 2025-07-22
Leith Walk | North East | BROUGHTON ROAD | At McDonald Road | Scottish Power - cable connections for Powderhall development | Temporary traffic lights | 2025-07-29 | 2025-08-12
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Midtjlland, kick-off 8pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-07-31 | 2025-07-31
Leith Walk | North East | ANDERSON PLACE | At Bonnington Road | Scottish Water - ironwork repair | Road closed | 2025-08-02 | 2025-08-03
Leith Walk | North East | SPEY TERRACE | At Shaw's Place | Clancy Docwra for Scottish Water | Temporary traffic lights | 2025-08-05 | 2025-08-05
Liberton / Gilmerton | South East | LIBERTON BRAE | At Alnwickhill Road | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-07-22 | 2025-07-22
Liberton / Gilmerton | South East | SOUTHHOUSE BROADWAY | At Southhouse Avenue (south leg) | Scottish Water - ironwork repair | Road closed | 2025-07-23 | 2025-07-23
Liberton / Gilmerton | South East | GILMERTON ROAD | At Moredun Dykes Road | Openreach - access to carriageway manhole | Off-peak 3-way temporary traffic lights | 2025-07-24 | 2025-07-24
Liberton / Gilmerton | South East | GILMERTON ROAD | Between The Spinney and Morrisons | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2025-09-08 | 2025-09-19
Liberton / Gilmerton | South East | WOLRIGE ROAD | Between Kirk Brae and Orchardhead Road | Clancy Docwra for Scottish Water | Road closed to through traffic | 2025-09-22 | 2025-10-01
Midlothian |  | A7 at ESKBANK |  | Midlothian Council - carriageway resurfacing and footway construction | Lane closures. Lasswade Road closed between A7 and Captains Gardens. | 2025-07-07 | 6 weeks estimated
Morningside | South East | GILMORE PLACE | Between Upper Gilmore Place and Viewforth | City of Edinburgh Council - footway resurfacing | Temporary traffic lights. Scottish Water will be attending to a burst pipe here from 16/07/25, this may require adjustments to the existing traffic management. | 2025-04-21 | 11/07/25 25/07/25 estimated
Morningside | South East | BRUNTSFIELD PLACE | At Viewforth | Clancy Docwra for Scottish Water - valve repairs Postponed due to ongoing footway work on Gilmore Place | 2-way temporary traffic lights, Viewforth closed | 2025-06-02 | 2025-06-11
Morningside | South East | LEAMINGTON TERRACE | In its entirety | City of Edinburgh Council - carriageway resurfacing | Road closed (in sections) | 2025-07-14 | 6 - 8 weeks
Morningside | South East | MARCHMONT ROAD | At Warrender Park Road | SGN - mains disconnection works | 2-way temporary traffic lights, Warrender Park Road closed on both sides | 2025-07-14 | 2025-08-04
Morningside | South East | COMISTON VIEW | North side of junction with Pentland Crescent | Clancy Docwra for Scottish Water | Road closed | 2025-07-22 | 2025-07-31
Morningside | South East | BRUNTSFIELD PLACE | Between Holy Corner and Merchiston Place | Clancy Docwra for Scottish Water - lead renewal | Narrow lane citybound with contraflow | 2025-09-14 | 2025-09-21
Pentland Hills | South West | A71 | Between Bonnington Road and Dalmahoy Road | City of Edinburgh Council - carriageway resurfacing | Road closed and Haggs Farm Road closed at A71, 7.30pm - 6am for 5 nights. Parking restrictions as signed on Main Street and Wilkieston Road in Ratho. No A71 closure required Thursday or Friday night. w/c 21/07/25 - temporary traffic lights for 3 nights for line marking and anti-skid surfacing. Haggs Farm Road works ongoing each weekday night. | 2025-07-14 | 19/07/25 24/07/25
Pentland Hills | South West | CLOVENSTONE GARDENS | At Clovenstone Road | Works associated with Smart Builders development | Road closed 3-way temporary traffic lights | 2025-07-14 | 12 days
Pentland Hills | South West | LANARK ROAD WEST | Various locations between Dolphin Avenue and Muir Wood Road | BT Morrison - fibre installation | Temporary traffic lights (now instructed to be off-peak only) | 2025-07-16 | 2025-08-10
Pentland Hills | South West | HAUGHHEAD ROAD | Between Buteland Road and the Water of Leith bridge | Scottish Water - repairs to burst pipe | Road closed | 2025-07-18 | 25/07/25 TBC
Pentland Hills | South West | HARLAW ROAD | Between Harlaw Bank and Harlaw March | BT Morrison - clearing blocked cable ducts | Stop / Go boards | 2025-07-22 | 2025-07-26
Pentland Hills | South West | BRYCE ROAD | At Thomson Road | BT Morrison - fibre installation | 4-way temporary traffic lights | 2025-07-23 | 5 days estimated
Pentland Hills | South West | MANSFIELD ROAD | At Harlaw Road | Clancy Docwra - sewer repairs for Scottish Water | 3-way temporary traffic lights | 2025-07-28 | 2025-08-05
Portobello/ Craigmillar | North East | BRUNSTANE ROAD | Between Milton Road East and Argyle Crescent / Dalkeith Street | City of Edinburgh Council - Low Traffic Neighbourhood trial Click cell for more details | Road closed to through traffic, except cycles | 2022-02-15 | Ongoing
Portobello/ Craigmillar | North East | ABERCORN TERRACE / PORTOBELLO HIGH STREET |  | GTC Pipelines - utility connections for housing development | Temporary traffic lights at Fishwives' Causeway from 27/06/25, moving east to Adelphi Place on 13/07/25. | 2025-05-27 | October 2025 estimated
Portobello/ Craigmillar | North East | OVERSMAN ROAD | Between the Mercedes garage and the Porsche garage | Scottish Power - cable connections | Temporary traffic lights | 2025-07-11 | 2025-07-24
Portobello/ Craigmillar | North East | MILTON ROAD EAST | Between Eastfield Gardens and Brunstane Mill Road | Clancy Docwra for Scottish Water | Temporary traffic lights | 2025-07-27 | 2025-08-07
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | At Duddingston Park South crossroads | Energetics - ducting installation for new HV power cables | Starting with 4-way temporary traffic lights (work then progressing east to Fort Kinnaird) | 2025-07-28 | 2 weeks estimated
Portobello/ Craigmillar | North East | GREENDYKES ROAD | Between Pringle Street and Capella Way | Drainage installation | Road closed | 2025-08-04 | 2025-09-30
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | Between Newhailes Court Gardens and the rail bridge | Locktel for Cityfibre - trial holes | Temporary traffic lights | 2025-08-11 | 2025-08-11
Portobello/ Craigmillar | North East | DUDDINGSTON ROAD | Outside St John's RC School | BT Circet - pole replacement | Road closed | 2025-09-07 | 2025-09-08
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Flint Terrace | Scottish Water - manhole repair Dates and details TBC | 3-way temporary traffic lights | 2025-09-08 | 2025-09-08
Portobello/ Craigmillar | North East | MUSSELBURGH ROAD | At Coillesdene Terrace | Clancy Docwra for Scottish Water - lead renewal | 3-way temporary traffic lights | 2025-12-01 | 2025-12-10
Sighthill/Gorgie | South West | STENHOUSE ROAD / GORGIE ROAD |  | SGN - gas main renewal (click cell for more information) | Stenhouse Drive closed at Pure Gym throughout the works. Phase 1 - contraflow between Els House and Chesser Avenue from 7am 02/06/25 for approximately 1 week. Phase 2 from 09/06/25 - temporary traffic lights at Els House / Water of Leith bridge. | 2025-06-01 | By 08/08/25
Sighthill/Gorgie | South West | KINGSKNOWE ROAD NORTH | At Redhall Gardens | Scottish Water - manhole repairs | 3-way temporary traffic lights | 2025-07-22 | 6am 23/07/25
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Dumbarton, kick-off 7.45pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-07-23 | 2025-07-23
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Sunderland, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-07-26 | 2025-07-26
Sighthill/Gorgie | South West | BANKHEAD TERRACE | Between Bankead Drive and Bankhead Broadway | Telecoms company - mast replacement | Road closed 9.30am - 3.30pm each day | 2025-07-28 | 2025-07-30
Sighthill/Gorgie | South West | RUSSELL ROAD | At Sauchiebank | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2025-07-30 | 2025-08-01
Sighthill/Gorgie | South West | BROOMHOUSE CRESCENT | At Broomhouse Place North | Community event | Roads closed 10am - 6pm | 2025-08-07 | 2025-08-07
Sighthill/Gorgie | South West | KINGSKNOWE ROAD NORTH | At the level crossing | Network Rail | Temporary traffic lights 11.30pm - 7am | 2025-08-09 | 2025-08-10
Sighthill/Gorgie | South West | CALDER ROAD | Between Stenhouse and the City Bypass | City of Edinburgh Council - verge works | Lane closures in both directions | 2025-08-16 | 2025-08-17
Sighthill/Gorgie | South West | INGLIS GREEN ROAD | At Redhall Drive | Scottish Water - manhole repair | 4-way temporary traffic lights | 2025-08-21 | 2025-08-21
Sighthill/Gorgie | South West | PARKHEAD TERRACE | At Parkhead Loan | Scottish Power - works for substation | Temporary traffic lights, Parkhead Loan closed between Longstone Road and Parkhead Terrace | 2025-08-22 | 2025-09-19
Sighthill/Gorgie | South West | DALRY ROAD | At Murieston Crescent | Openreach - manhole reconstruction | 2-way temporary traffic lights, Murieston Crescent closed | 2025-09-15 | 2025-09-21
Sighthill/Gorgie | South West | CALDER ROAD SERVICE ROAD | At Parkhead Terrace | Telecoms company - mast and cabinet renewal | Service road and Parkhead Terrace closed (weekdays only) | 2025-09-22 | 2025-09-30
Southside / Newington | South East | SYLVAN PLACE | At Rillbank Crescent | Building development | Road closed | 2023-09-27 | 2025-07-28
Southside / Newington | South East | GEORGE SQUARE AREA |  | George Square Festival | East leg closed 23/06 - 03/09/25. North leg and Crichton Street closed 30/07 - 26/08/25. One-way restrictions in place on Crichton Street, George Square, George Square Lane and Buccleuch Place, 30/06 - 30/07 and 26/08 - 03/09/25 | 2025-06-23 | 2025-09-03
Southside / Newington | South East | DALKEITH ROAD | At East Preston Street | City of Edinburgh Council - footway buildouts | Lane closures, temporary traffic lights while existing poles are relocated. | 2025-07-07 | 3 weeks estimated
Southside / Newington | South East | HILL SQUARE |  | Hill Square festival fringe | Road closed and Hill Place eastbound only between Hill Square and Richmond Place | 2025-07-14 | 2025-08-29
Southside / Newington | South East | ROXBURGH PLACE | At Drummond Street | Assembly Festival | Road closed | 2025-07-16 | 2025-08-28
Southside / Newington | South East | BLACKFORD AVENUE | At West Savile Terrace | BRM Utilities for Vodafone - proving cable ducts | 4-way temporary traffic lights 7pm - 7am | 2025-07-21 | 2025-07-22
Southside / Newington | South East | DUNCAN STREET | At Minto Street | Scottish Water - valve repairs | Road closed | 2025-07-21 | 2025-07-25
Southside / Newington | South East | WHITEHOUSE TERRACE / NEWBATTLE TERRACE | Either side of Whitehouse Loan junction | City of Edinburgh Council - footway resurfacing | Lane closures and parking restrictions, details TBC | 2025-08-18 | 4-5 weeks estimated
Southside / Newington | South East | MINTO STREET | At Salisbury Place | Scottish Water - manhole repair | 4-way temporary traffic lights | 2025-09-09 | 2025-09-09
Trunk road network |  | M8 | Between J3A and 4 | BEAR Scotland - B792 bridge refurbishment | Road closed 8.30pm - 6am on Sunday night 18/05/25. Various lane closures on Monday 19/05/25. Contraflow and 40mph speed restriction from Tuesday 20/05/25. | 2025-05-18 | 4 months estimated
Trunk road network |  | FORTH ROAD BRIDGE |  | BEAR Scotland - bridge maintenance | Road closed 9.30pm - 4am for 2 nights, then single lane closures until October. | 2025-05-22 | October 2025
Trunk road network |  | A1 | Between Wallyford and Oaktree junctions | BEAR Scotland - drainage works (click cell for full details) | Southbound lane closure and off- and on-slips closed 7.30pm - 6am each weekday night. Wallyford w/c 30/06/25, Dolphingstone w/c 07/07/25, Bankton w/c 14/07/25, Gladsmuir w/c 21/07/25, Oaktree w/c 28/07/25. | 2025-06-30 | 2025-08-02
Trunk road network |  | A720 | Sheriffhall to Gilmerton | BEAR Scotland - carriageway resurfacing Extended by 1 night (and will now overlap with works further west at Dreghorn) | Road closed to westbound traffic 8.30pm - 6am for 7 nights NB 10.30pm start on 22/07/25. | 2025-07-14 | 22/07/25 23/07/25
Trunk road network |  | A720 | Dreghorn to Calder | BEAR Scotland - carriageway resurfacing | Road closed to westbound traffic 8.30pm - 6am for 7 weekday nights | 2025-07-22 | 2025-07-30
Trunk road network |  | A702 | Between Hillend and Easter Howgate | BEAR Scotland - carriageway resurfacing | Road closed 7.30pm - 6.30am for 3 weekday nights | 2025-07-24 | 2025-07-29
Trunk road network |  | A720 | Dreghorn to Calder | BEAR Scotland - bridge joint replacement | Road closed to westbound traffic 8.30pm - 6am for 5 nights | 2025-08-04 | 2025-08-09
Trunk road network |  | A90 | Burnshot to Dalmeny | BEAR Scotland - carriageway resurfacing (at Dalmeny) | Road closed to northbound traffic 8.30pm - 6am for 4 weekday nights | 2025-07-31 | 2025-08-06
Trunk road network |  | A1 | Between Old Craighall and Wallyford | BEAR Scotland - carriageway resurfacing and bridge joint repairs | 20/08/25 - road closed to northbound traffic 8.30pm - 6am for 5 weekday nights; 01/09/25 - as above plus partial closure of Old Craighall roundabout for 1 night; 02/09/25 - road closed to southbound traffic QMU to Wallyford for 1 night; 03/09/25 - road closed to southbound traffic Old Craighall to Wallyford for 8 weekday nights. | 2025-08-20 | 2025-09-13
Trunk road network |  | A702 / Old Pentland Road | Between Roseneath and Snowsports centre | Scottish Power - new supply | Overnight temporary traffic lights | 2025-09-22 | 2025-10-24
Roadworks & events report
Effective from 21 July 2025