## General Road Works
Links to further information
| Traffic Scotland - realtime information on trunk roads including Edinburgh City Bypass |  |  |  | Details of Ward and Locality boundaries
SE Scotland trunk roads maintenance by BEAR Scotland
Key
| Transport for Edinburgh - Lothian Buses and Edinburgh Trams |  |  |  | New or updated information in this version
Underlined entries contain links to maps or further information
Edinburgh Travelling Safely measures and Low Traffic Neighbourhoods
| Our social media channels: |  | X (formerly Twitter) | Facebook | Threads
Excel - use the drop-down arrows to sort by any column. PDF - use CTRL + F to search for any keyword. |  |  |  | NB this is not intended to be a list of all the roadworks in Edinburgh. Please refer to the Scottish Roadworks Register website for basic information on all registered roadworks
Ward | Locality | Street | Location | Contractor / works description | Measures in place | Start | Finish
Almond | North West | MAYBURY ROAD | At Craigs Road | Construction of signalised junction | Craigs Road closed on west side of Maybury Road from 06/05/25; Phase 2 - various lane closures and contraflow arrangements from 26/05/25; Phase 3 - 2-way traffic on northbound carriageway, Craigs Road closd on east side, estimated start 06/10/25; Phase 4 - temporary traffic lights, estimated start 10/12/25. | 2025-05-06 | 6 months estimated
Almond | North West | QUEENSFERRY AREA |  | Cruise liner visits. Click cell for full schedule | For each visit: prohibition of motor vehicles on Bankhead Road south of Station Road, parking restrictions as signed on Hawes car park, Newhalls Road and Hawes Brae | 2025-05-07 | 2025-10-09
Almond | North West | A89 / A8 | Between Broxburn and Gogar | City of Edinburgh Council - ground investigation surveys (starting between Broxburn viaduct and Newbridge) | Primarily nightshift works with lane closures and temporary bus stops as required. Some off-peak daytime works TBA. w/c 11/08/25 - nightworks on Glasgow Road between Gogar and Ingliston. | 2025-07-14 | Late September 2025
Almond | North West | RODDINGLAW ROAD | At Freelands Road | Scottish Power - cable fault | Temporary traffic lights | 2025-08-08 | TBC
Almond | North West | GLASGOW ROAD | Between Ratho Station and Ingliston | Commsworld - urgent telecoms maintenance | Off-peak citybound lane closure | 2025-08-11 | Up to 5 days
Almond / Drum Brae & Gyle / Inverleith | North West | QUEENSFERRY ROAD and GLASGOW ROAD |  | City of Edinburgh Council - carriageway line marking (40 to 30mph) Note new dates | Short-duration lane closures as required: Maybury Road at Glasgow Road and at Queensferry Road (off-peak daytime); Hillhouse Road at Telford Road and Glasgow Road at Drum Brae roundabout (nightshift). | 2025-08-15 | 2025-08-19
Almond | North West | CLIFTONHALL ROAD | Just north of M8 bridge | Commsworld - urgent telecoms maintenance | Temporary traffic lights | 2025-08-16 | 2025-08-16
Almond | North West | INGLISTON AREA |  | Summer Sessions at Royal Highland Centre (Sam Fender on 22/08/25 and Chappell Roan on 26 and 27/08/25) | Formal restrictions TBA but expect extra traffic on airport approach roads on all afternoons / evenings. | 2025-08-22 | 2025-08-27
City Centre | South East | CALTON ROAD | Between Waverley station access and New Street | Unsafe rock face, restrictions in place to provide safety zone | Temporary traffic lights. Shuttle system with full-time traffic signals in operation | 2018-12-01 | Ongoing
City Centre | South East | NORTH BRIDGE |  | City of Edinburgh Council / Balfour Beatty - bridge refurbishment | East footway closed, pedestrian access via west footway. One traffic lane open in each direction (as of 21/04/23). | 2020-02-15 | Summer 2026
City Centre | South East | TARVIT STREET |  | Redevelopment of King's Theatre | Tarvit Street closed between Home Street and Drumdryan Street. Drumdryan Street northbound only. NCR 75 closed, cycle diversion signed via Valleyfield Street | 2023-02-14 | Late 2026
City Centre | South East | DEVON PLACE | Between West Coates and no. 4 | For Ogilvie Construction | Road closed to southbound traffic. | 2023-06-06 | March 2026
City Centre | South East | ROSE STREET SOUTH LANE | Section between Frederick Street and Hanover Street, east leg | Building development | Road closed | 2025-06-06 | 2025-08-29
City Centre | South East | CALTON ROAD | At Leith Street | Crane lift Postponed due to gas main repairs at Abbeymount, new date TBA | Road closed | 2025-06-29 | 2025-06-29
City Centre | South East | WEST COATES |  | Energetics - utility connection Restrictions cleared 25/07/25, further work may be required | Temporary traffic lights, Devon Place closed | 2025-07-07 | 20/07/25 25/07/25
City Centre | South East | ABBEYHILL / ABBEYMOUNT JUNCTION | At the rail bridge | Network Rail - bridge inspection Postponed due to gas main repairs, new date TBA | Roads closed 9pm - 6am | 2025-07-17 | 2025-07-18
City Centre | South East | GEORGE STREET | Between Frederick Street and Hanover Street | George Street Festival | Road closed (from 11pm on 24/07/25) except for cycles. Loading permitted 6am - 8am daily. | 2025-07-24 | 2025-08-26
City Centre | South East | BLAIR STREET | At South Bridge | Summertime Streets 2025 | Road closed. Normal one-way order rescinded. | 2025-07-28 | 2025-08-26
City Centre | South East | COWGATE | Between Candlemaker Row and Blackfriars Street | Summertime Streets 2025 | Road closed to motor vehicles 3pm - 5am each day, local access via Guthrie Street. | 2025-07-28 | 2025-08-26
City Centre | South East | EDINBURGH CASTLE AREA |  | Royal Edinburgh Military Tattoo | Road closures as follows: Castlehill: 6pm - 11pm on 30/07/25 then 4.30pm - midnight each day. Mound Place, Ramsay Lane, Ramsay Garden, Johnston Terrace, Lawnmarket at Castlehill, Upper Bow: 5pm - midnight on 30 and 31/07/25, 5.30pm - midnight each weekday from 01/08/25, 4pm - midnight each weekend day. St Giles' Street, Lawnmarket / High Street between Parliament Square and George IV Bridge: 7pm - midnight each weekday, 7pm - 9pm each weekend day. King's Stables Road: 7pm - midnight each week day, 4.15pm - midnight each weekend day. | 2025-07-30 | 2025-08-23
City Centre | South East | HIGH STREET AREA | Lawnmarket / High Street between George IV Bridge and Cockburn Street, St Giles' Street at Lawnmarket, Parliament Square and Parliament Square West, Cockburn Street. | Fringe High Street | Roads closed 10.30am - 7pm Monday to Saturday and 10.30am - 9pm Sundays | 2025-08-01 | 2025-08-24
City Centre | South East | HILL STREET | Between its junctions with Hill Street North / South Lane | Clancy Docwra for Scottish Water | Road closed | 2025-08-06 | TBC
City Centre & Craigentinny / Duddingston | South East | HOLYROOD PARK AREA |  | Edinburgh Moonwalk | Holyrood Gait, Horse Wynd, Queen's Drive and Duke's Walk closed 10pm - 1.30am | 2025-09-06 | 2025-09-07
City Centre | South East | REGENT ROAD | At the old Royal High | BT - ironwork repairs | 2-way temporary traffic lights | 2025-09-08 | Up to 5 days
City Centre | South East | CANDLEMAKER ROW |  | City of Edinburgh Council - carriageway resurfacing | Daytime lane closure for gully works. Road closed 7pm - 6am each weekday night for resurfacing. | 2025-09-08 | 1 week estimated
City Centre | South East | DEVON PLACE | Between the south east corner and Devon Gardens | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-09-08 | 2025-09-17
City Centre | South East | ROSE STREET SOUTH LANE | Section between Castle Street and Frederick Street | SGN - gas main disconnection | Road closed | 2025-09-08 | 2025-09-26
City Centre | South East | WEST MAITLAND STREET |  | Scottish Water - ironwork repair | Citybound lane closure, bus stops closed. 12.15am - 4.30am. | 2025-09-13 | 2025-09-13
City Centre | South East | QUEENSFERRY STREET LANE | At Queensferry Street | BT Circet - ducting installation | Road closed | 2025-09-15 | 2025-09-19
City Centre | South East | WATERLOO PLACE | Between Leith Street and Calton Hill | GPR survey | Road closed 8pm - 6am for 2 nights | 2025-09-16 | 2025-09-18
City Centre | South East | GILMORE PLACE |  | City of Edinburgh Council - carriageway resurfacing Dates and details TBC | Road closed in sections | 2025-09-22 | March 2026
City Centre | South East | LEOPOLD PLACE |  | City of Edinburgh Council - resurfacing | Daytime lane closures for gully and footway works. Road and lane closures 7pm - 6am each weekday night for resurfacing: citybound traffic diverted via Regent Road, eastbound traffic as normal for week 1 and contraflow on citybound side for week 2. | 2025-09-22 | 2 weeks estimated
City Centre | South East | LONDON ROAD | At Hillside Crescent | City of Edinburgh Council - pedestrian crossing upgrade | Lane closures, temporary traffic lights as required | 2025-09-22 | 2 weeks estimated
City Centre | South East | CALTON ROAD | Between Waverley station access and New Street | Scottish Water - ironwork repair | Road closed | 2025-09-28 | 2025-09-28
City Centre | South East | GAYFIELD SQUARE | At Gayfield Street | SGN - gas main renewal | 2-way temporary traffic lights, Gayfield Street closed | 2025-09-29 | 2025-10-17
City Centre | South East | ROSE STREET SOUTH LANE | Section between South Charlotte Street and Castle Street | Clancy Docwra for Scottish Water | Road closed | 2025-09-29 | 2025-10-08
City Centre | South East | VALLEYFIELD STREET |  | Scottish Water - service connection | Road closed except for cycles | 2025-12-01 | 2025-12-10
Colinton / Fairmilehead | South West | BONALY CRESCENT | Between Laverockdale Loan and Bonaly Terrace | Openreach - ducting installation Not started | Road closed | 2025-08-14 | 2025-08-15
Colinton / Fairmilehead | South West | MOUNTHOOLY LOAN | Between Galachlawside and Galachlawshot | Clancy Docwra for Scottish Water - pipe repairs Details TBC for local access | Road closed | 2025-08-25 | 2025-09-05
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Murrayfield | Scottish Water - major works to install combined sewer overflow (CSO) | Temporary traffic lights. Ormidale Terrace closed. Westbound bus stop closed, please use the next stop. | 2025-06-08 | End of 2025
Corstorphine / Murrayfield | North West | SAUGHTON ROAD NORTH | Between Stenhouse Drive and Carrick Knowe Road | Network Rail - removal of bird netting for bridge survey. | Road closed 9pm - 7am for 3 nights (no works on night of 12/08/25) | 2025-08-11 | 2025-08-15
Corstorphine / Murrayfield | North West | ROSEBURN STREET | At the tram bridge | Bilfinger for Edinburgh Trams - concrete and drainage repairs | Temporary traffic lights 8.30am - 4.30pm each day | 2025-08-18 | 2025-08-19
Corstorphine / Murrayfield | North West | MURRAYFIELD and SURROUNDING AREA |  | AC / DC concert at Scottish Gas Murrayfield | Road closures before and after the event affecting Roseburn, Murrayfield, Haymarket areas plus West Approach Road afterwards. Click cell to view details. | 2025-08-21 | 2025-08-21
Corstorphine / Murrayfield | North West | COLTBRIDGE TERRACE |  | Clancy Docwra for Scottish Water | Road closed to through traffic nos. 22 - 26 | 2025-09-01 | 2025-09-10
Corstorphine / Murrayfield | North West | RAVELSTON DYKES ROAD |  | Edinburgh Moonwalk | Road closed 11.30pm - 3.45am | 2025-09-06 | 2025-09-07
Corstorphine / Murrayfield | North West | CORSTORPHINE AREA |  | Corstorphine Connections scheme - replacing some temporary measures with permanent materials. Dates and details TBC | Phased closures of Kirk Loan and Manse Road | 2025-09-18 | Late October
Corstorphine / Murrayfield | North West | ST JOHN'S ROAD | Opposite Station Road | Clancy Docwra - sewer repairs for Scottish Water Dates and details TBC as at 06/08/25 | 2-way temporary traffic lights, Clermiston Road and Station Road closed | 2025-11-18 | 2025-11-27
Corstorphine / Murrayfield | North West | ELLERSLY ROAD |  | City of Edinburgh Council - carriageway resurfacing | Road closed (excluding any affected 6 Nations dates) | 2026-01-12 | Up to 6 weeeks
Craigentinny/ Duddingston | North East | ABBEY LANE | At Abbeyhill | Graham Construction - development works | Road closed | 2024-01-09 | End of October 2025
Craigentinny/ Duddingston | North East | DUDDINGSTON LOW ROAD |  | Historic Environment Scotland - risk of rock falls | Road closed to motor vehicles. Road closed to all path users from Tuesday 18/03/25, pedestrian and cyclist diversion via Innocent railway path. Reopened to pedestrians and cyclists 07/08/25, cyclists please dismount through the barrier system at Samson's Ribs. | 2025-03-15 | Until further notice
Craigentinny/ Duddingston | North East | WILLOWBRAE AVENUE | Between Abercorn Road and Paisley Crescent | City of Edinburgh Council - carriageway resurfacing | Road closed | 2025-08-11 | 5 days estimated
Craigentinny/ Duddingston | North East | NANTWICH DRIVE | At Stapeley Avenue | Scottish Water - manhole repair | Temporary traffic lights | 2025-08-15 | 2025-08-15
Craigentinny/ Duddingston | North East | GLENLEE GARDENS |  | City of Edinburgh Council - carriageway resurfacing | Road closed | 2025-08-18 | 5 days estimated
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Clark Contracts - building development | Section of north footway and eastbound cycle lane closed. | 2025-09-01 | December 2027
Craigentinny/ Duddingston | North East | WILLOWBRAE ROAD | Between Duddingston Mills and Northfield Broadway | Clancy Docwra for Scottish Water - lead renewal | Lane closures / contraflow. No right turn from the car dealership | 2025-09-08 | 2025-09-17
Craigentinny/ Duddingston | North East | WILLOWBRAE ROAD | At Willowbrae Gardens | Scottish Water - manhole repair | Temporary traffic lights and Willowbrae Gardens closed. 7pm - 7am | 2025-09-04 | 2025-09-05
Craigentinny/ Duddingston | North East | RESTALRIG ROAD SOUTH | Between the rail bridge and Restalrig Avenue | Network Rail - vegetation clearance | Road closed 10pm - 6am | 2025-09-15 | 2025-09-16
Craigentinny/ Duddingston | North East | SPRING GARDENS | Between Abbey Lane and Milton Street | Network Rail - vegetation clearance | Road closed for 1 night (times TBC) | 2025-11-03 | 2025-11-04
Drum Brae / Gyle | North West | SOUTH GYLE ROAD | At the rail bridge | Network Rail - renewing rail bridge Start TBC, no confirmation / documentation received. | Road closed. Access to the station car park via South Gyle Broadway - Gogarloch Road. | 2025-07-28 | April 2026
Drum Brae / Gyle | North West | LADYWELL AVENUE | Between Kirklands and Broomhall Crescent | Network Rail - renewing rail bridge | Road closed | 2025-09-24 | August 2026
East Lothian |  | TRANENT / MUSSELBURGH AREA |  | Scottish Half Marathon | Multiple road closures and parking restrictions - click cell for details | 2025-08-17 | 2025-08-17
Forth | North West | CRAIGHALL ROAD | Between Craighall Avenue and Grandville | Refurbishment of Trinity Academy | Road closed | 2025-06-30 | May 2028
Forth | North West | AFTON TERRACE | At Cargil Terrace | SGN - gas main renewal | 2-way temporary traffic lights, Wardie Road (south leg) closed | 2025-08-04 | 2025-08-31
Forth | North West | LOMOND ROAD / TRINITY ROAD | Between Primrose Bank Road and East Trinity Road | City of Edinburgh Council - micro-asphalt surfacing | Roads closed | 2025-08-20 | 2025-08-21
Forth | North West | WATERFRONT AVENUE | On the bend just east of Waterfront Broadway | Scottish Water - ironwork repair | Temporary traffic lights | 2025-08-20 | 2025-08-20
Forth | North West | GRANTON ROAD | At Boswall Green | Openreach Rescheduled from 14/07/25 | Off-peak 4-way temporary traffic lights | 2025-08-27 | 2025-08-28
Forth | North West | WEST GRANTON AREA |  | Procession | Rolling road closure West Granton Road - Waterfront Broadway - Caroline Park Avenue- Speir’s Bruce Way - West Shore Road. Between 4.45pm and 5.45pm. | 2025-08-31 | 2025-08-31
Forth | North West | ROYSTON TERRACE | At Inverleith Row | Clancy Docwra for Scottish Water | Road closed to through traffic. Existing one-way order rescinded for duration of works. | 2025-09-08 | 2025-09-17
Forth | North West | BANGHOLM ROAD |  | Clancy Docwra for Scottish Water | Road closed to through traffic. | 2025-10-20 | 2025-10-20
Fountainbridge/ Craiglockhart | South West | HARRISON ROAD | At the dog-leg bend where it crosses the cycle path and at the canal bridge | City of Edinburgh Council - bridge repairs | Road closed. Topside footway closures as signed. Dates for demolition of the remaining existing (northern) bridge structure TBC. | 2025-02-18 | Ongoing
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Moat Terrace | Scottish Power / Excalon - cable jointing Not started | Temporary traffic lights | 2025-08-13 | 4 - 5 weeks
Fountainbridge/ Craiglockhart | South West | CRAIGLOCKHART CROSSROADS |  | Clancy Docwra for Scottish Water | 4-way temporary traffic lights | 2025-09-12 | 2025-09-12
Fountainbridge/ Craiglockhart | South West | LANARK ROAD | At Water of Leith visitor centre | Scottish Power - mains disconnection | Westbound inside lane closed | 2025-09-15 | 2025-09-26
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At the rail bridge | Network Rail - bridge maintenance | Temporary traffic lights 7pm - 7am | 2025-09-20 | 2025-09-21
Fountainbridge/ Craiglockhart | South West | ROBB'S LOAN | At Eltringham Gardens | Clancy Docwra - sewer works for Scottish Water | 3-way temporary traffic lights | 2025-09-22 | 2025-09-24
Fountainbridge/ Craiglockhart | South West | HUTCHISON PLACE | At Slateford Road | Scottish Water - ironwork repair | Road closed | 2025-09-29 | 2025-09-29
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Coxfield | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-09-29 | 2025-09-29
Inverleith | North West | ARBORETUM AVENUE |  | Scottish Water - mains upgrade | Road closed | 2025-07-14 | 2025-09-14
Inverleith | North West | HAMILTON PLACE | At Clarence Street | Scottish Power - cable fault | Temporary traffic lights. Road closed from Thursday 07/08/25, works provisionally registered until 22/08/25. | 2025-08-01 | TBC
Inverleith | North West | WARRISTON TERRACE |  | Clancy Docwra for Scottish Water | Road closed | 2025-08-06 | 2025-08-15
Inverleith | North West | FERRY ROAD | At Boswall Drive | Clarke Telecom - trial holes | 3-way temporary traffic lights | 2025-08-18 | 2025-08-19
Inverleith | North West | TELFORD PLACE | At Telford Road | SGN - gas main renewal | Road closed | 2025-08-18 | 2025-09-30
Inverleith | North West | COMELY BANK ROAD | At East Fettes Avenue | Scottish Water - mains survey | 4-way temporary traffic lights 8am - 1pm approximately | 2025-09-07 | 2025-09-07
Inverleith | North West | CANONMILLS | At Inverleith Row / Brandon Terrace | Vodafone - proving cable ducts | 3-way temporary traffic lights, 8pm - 6am | 2025-09-10 | 2025-09-11
Inverleith | North West | LEARMONTH TERRACE | At Dean Park Crescent | Community event | Road closed 10am - 4pm | 2025-09-14 | 2025-09-14
Leith | North East | LINDSAY ROAD BRIDGE | Pedestrian / cycle bridge between Nicholfield and Lindsay Road main carriageway | City of Edinburgh Council - public safety measure | Bridge closed, pedestrian and cycle diversion as signed. Hawthornvale Path beneath remains open | 2021-12-15 | Until further notice
Leith | North East | GREAT JUNCTION STREET | Between Foot of the Walk and Henderson Street | City of Edinburgh Council - construction of segregated cycle lane | One lane open in each direction, temporary pedestrian crossing facility at Pirrie Street. Permanent traffic signals at Henderson Street back in operation from Tuesday 15/07/25. | 2024-11-18 | Summer 2025
Leith | North East | HENDERSON STREET | Between Great Junction Street and Yardheads | City of Edinburgh Council - construction of segregated cycle lane | Lane closures, parking restrictions, temporary traffic lights if required. One-way (southbound) system with northbound access via Cables Wynd from 19/03/25. | 2024-12-03 | Summer 2025
Leith | North East | NEWHAVEN AREA |  | Cruise liner visits. Click cell for full schedule | Parking restrictions as signed on Pier Place and Newhaven Place for each visit | 2025-04-02 | 2025-09-27
Leith | North East | DUNCAN PLACE | Between Duke Place and Wellington Place | Event | Road closed 7am - 7pm | 2025-08-23 | 2025-08-23
Leith | North East | BERNARD STREET | At Commercial Street / Shore | Scottish Water - manhole repair | 4-way temporary traffic lights 7pm - 7am | 2025-08-29 | 2025-08-30
Leith | North East | RESTALRIG TERRACE | At Lochend Road | Community event | Road closed midday - 9.30pm | 2025-08-31 | 2025-08-31
Leith | North East | LINDSAY ROAD | Between North Leith Sands and Hawthornvale path | Virgin Media | Temporary traffic lights 7pm - 7am | 2025-09-04 | 2025-09-05
Leith | North East | GILES STREET | At Henderson Street | Clancy Docwra - sewer repairs for Scottish Water | Road closed | 2025-10-06 | 2025-10-13
Leith Walk | North East | ALBION ROAD | Between Easter Road and Albion Place | Scottish Water - collapsed sewer | Road closed | 2025-08-07 | TBC
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Partizan Belgrade, kick-off 8pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-08-14 | 2025-08-14
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v St Mirren, kick-off 3pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-08-30 | 2025-08-30
Leith Walk | North East | LEITH WALK | Pilrig Street to Foot of the Walk | Bilfinger for Edinburgh Trams - concrete repairs | Road closed to northbound traffic 12.15am - 4.30am for 3 mornings. | 2025-09-08 | 2025-09-10
Leith Walk | North East | EASTER ROAD | Between Sunnyside and Drum Terrace | Clancy Docwra for Scottish Water | 4-way temporary traffic lights | 2025-10-05 | 2025-10-07
Liberton / Gilmerton | South East | GILMERTON ROAD | At Liberton High School | Buildng works | Temporary traffic lights on and ad-hoc basis to accommodate materials and spoil | 2025-07-31 | 2025-08-15
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | BT Morrison - fibre installation To be rescheduled | Off-peak 3-way temporary traffic lights | 2025-08-18 | 2025-08-18
Liberton / Gilmerton | South East | GILMERTON ROAD | Between The Spinney and Morrisons | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2025-09-08 | 2025-09-19
Liberton / Gilmerton | South East | LIBERTON ROAD | At Gilmerton Road | Locktel for Cityfibre - proving / clearing cable ducts | 3-way temporary traffic lights 9.30am - 5pm each day | 2025-09-10 | 2025-09-11
Liberton / Gilmerton | South East | LASSWADE ROAD | At Gracemount high school | BT Morrison - fibre installation | 2-way temporary traffic lights and separate lane closures between the school and Captain's Road | 2025-09-12 | 2025-09-13
Liberton / Gilmerton | South East | KAIMES CROSSROADS |  | Openreach - access to carriageway manholes | Off-peak 4-way temporary traffic lights | 2025-09-14 | 2025-09-14
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | Telecoms company - pole replacement (preparatory works) | 3-way temporary traffic lights | 2025-09-20 | 2025-09-24
Liberton / Gilmerton | South East | WOLRIGE ROAD | Between Kirk Brae and Orchardhead Road | Clancy Docwra for Scottish Water | Road closed to through traffic | 2025-09-22 | 2025-10-01
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | Telecoms company - pole replacement | 3-way temporary traffic lights | 2025-10-04 | 2025-10-05
Midlothian |  | A7 at ESKBANK |  | Midlothian Council - carriageway resurfacing and footway construction | Lane closures. Lasswade Road closed between A7 and Captains Gardens. NEW - Lasswade Road expected to reopen Monday 18/08/25, lane restrictions thereafter for phase 2. | 2025-07-07 | Late September 2025
Midlothian |  | THE WISP | Between Speedwell Avenue and Edmonstone Road | Midlothian Council - street lighting renewal | Temporary traffic lights | 2025-08-08 | 2025-08-22
Midlothian |  | STRAITON ROAD | Between Loanhead Road and roundabout at Burger King | Midlothian Council - street lighting renewal | Lane closures | 2025-08-14 | 2025-08-28
Midlothian |  | NIVENSKNOWE ROAD | Between Main Street and Dryden Road | Scottish Water - ironwork repair | Road closed | 2025-08-17 | 2025-08-17
Morningside | South East | MARCHMONT ROAD |  | Scottish Power - cable installations | Phase 1 - 3-way temporary traffic lights at Beaufort Road, Marchmont Road closed to southbound traffic; Phase 2 - 3-way temporary traffic lights at Marchmont Crescent, no exit from Spottiswoode Road. | 2025-08-04 | 26/09/25 estimated
Morningside | South East | BRAID ROAD | At Hermitage of Braid | Openreach - urgent works to restore service | Temporary traffic lights | 2025-08-14 | TBC
Morningside | South East | BRUNTSFIELD PLACE | Between Holy Corner and Merchiston Place | Clancy Docwra for Scottish Water - lead renewal | Narrow lane citybound with contraflow | 2025-09-14 | 2025-09-21
Morningside | South East | BRUNTSFIELD PLACE | At Viewforth | Clancy Docwra for Scottish Water - valve repairs | 2-way temporary traffic lights, Viewforth closed | 2025-12-07 | 2025-12-16
Multiple Wards |  | CITYWIDE |  | City of Edinburgh Council - micro-asphalt surfacing | Road closures - click cell for full details | 2025-08-13 | 2025-08-31
Pentland Hills | South West | DEAN PARK AVENUE | At Dean Park Grove | Scottish Power - mains upgrade | Temporary traffic lights | 2025-08-08 | 2025-08-21
Pentland Hills | South West | LANARK ROAD WEST | At Muir Wood Road / Blinkbonny Road | BT Morrison - fibre installation | Off-peak temporary traffic lights | 2025-08-13 | 2025-08-14
Pentland Hills | South West | RICCARTON MAINS ROAD | Between Corslet Road and north of the s-bends | City of Edinburgh Council - gully investigations | Overnight temporary traffic lights | 2025-08-14 | 2025-08-15
Pentland Hills | South West | LANARK ROAD WEST | At Gibson Craig Hall | BT Morrison - clearing blocked cable ducts | Off peak temporary traffic lights | 2025-08-15 | 2025-08-18
Pentland Hills | South West | LANARK ROAD WEST | At Currie community centre | BT Morrison - pole installation | Off peak temporary traffic lights | 2025-08-19 | 5 days estimated
Pentland Hills | South West | CLOVENSTONE GARDENS | At Clovenstone Road | Works associated with Smart Builders development | Road closed | 2025-08-25 | 2025-08-29
Pentland Hills | South West | LANARK ROAD WEST | At Gibson Craig Hall | Scottish Water - lead renewal | Temporary traffic lights | 2025-08-27 | 2025-08-29
Pentland Hills | South West | RICCARTON MAINS ROAD | Near the garden centre | City of Edinburgh Council - carriageway line marking | Temporary traffic lights for around 1 hour during off-peak period | 2025-09-11 | 2025-09-11
Pentland Hills | South West | WESTER HAILES ROAD |  | City of Edinburgh Council - litter picking and grass cutting | Outside lane closed in both directions | 2025-09-17 | 2025-09-17
Portobello/ Craigmillar | North East | BRUNSTANE ROAD | Between Milton Road East and Argyle Crescent / Dalkeith Street | City of Edinburgh Council - Low Traffic Neighbourhood trial Click cell for more details | Road closed to through traffic, except cycles | 2022-02-15 | Ongoing
Portobello/ Craigmillar | North East | ABERCORN TERRACE / PORTOBELLO HIGH STREET |  | GTC Pipelines - utility connections for housing development | From 14/08/25, 2-way lights with Windsor Place and Regent Street closed. | 2025-05-27 | October 2025 estimated
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | Starting at Duddingston Park South crossroads, working eastwards to Fort Kinnaird | Energetics - ducting installation for new HV power cables | 4-way temporary traffic lights at the crossroads for 2 weeks until 06/08/25 then lane closures and no right turns into or out of Peacocktail Close, Cleikiminfield, Cleikiminrig and Blackchapel Close. | 2025-07-28 | 8 - 10 weeks estimated
Portobello/ Craigmillar | North East | RAMSAY PLACE | At Portobello High Street | Building demolition | Road closed | 2025-07-28 | TBC
Portobello/ Craigmillar | North East | GREENDYKES ROAD | At Greendykes Drive | Drainage installation | Road closed, diversion via Tudsbury Avenue | 2025-08-04 | 2025-09-30
Portobello/ Craigmillar | North East | DUDDINGSTON ROAD | Outside St John's RC School | BT Circet - pole replacement | Road closed | 2025-09-07 | 2025-09-08
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Flint Terrace | Scottish Water - manhole repair Dates and details TBC | 3-way temporary traffic lights | 2025-09-08 | 2025-09-08
Portobello/ Craigmillar | North East | MUSSELBURGH ROAD | At Coillesdene Terrace | Clancy Docwra for Scottish Water - lead renewal | 3-way temporary traffic lights | 2025-12-01 | 2025-12-10
Sighthill/Gorgie | South West | STENHOUSE DRIVE | Between Stenhouse Cross and Saughton Mains Street | BRM Utilities for Vodafone | Lane closures / contraflow. | 2025-08-13 | 2025-08-16
Sighthill/Gorgie | South West | WHEATFIELD ROAD | At Gorgie Road | Cityfibre - remedial works | Road closed | 2025-08-16 | 2025-08-17
Sighthill/Gorgie | South West | KINGSKNOWE ROAD NORTH | At the level crossing | Network Rail | Temporary traffic lights 11.30pm - 7am | 2025-08-16 | 2025-08-17
Sighthill/Gorgie | South West | INGLIS GREEN ROAD | At Redhall Drive | Scottish Water - manhole repair | 4-way temporary traffic lights | 2025-08-21 | 2025-08-21
Sighthill/Gorgie | South West | PARKHEAD TERRACE | At Parkhead Loan | Scottish Power - works for substation | Temporary traffic lights, Parkhead Loan closed between Longstone Road and Parkhead Terrace | 2025-08-22 | 2025-09-19
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Motherwell, kick-off 8pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-08-23 | 2025-08-23
Sighthill/Gorgie | South West | INGLIS GREEN ROAD | At Redhall Drive / Sainsburys | Scottish Water - access to sewer overflow | 3-way temporary traffic lights, Redhall Drive closed | 2025-09-10 | 2025-09-10
Sighthill/Gorgie | South West | DALRY ROAD | At Orwell Terrace | Cityfibre - manhole repair | Temporary traffic lights, Orwell Terrace closed | 2025-09-10 | 2025-09-13
Sighthill/Gorgie | South West | DALRY ROAD | At Murieston Crescent | Openreach - manhole reconstruction | 2-way temporary traffic lights, Murieston Crescent closed | 2025-09-15 | 2025-09-21
Sighthill/Gorgie | South West | CALDER ROAD SERVICE ROAD | At Parkhead Terrace | Telecoms company - mast and cabinet renewal | Service road and Parkhead Terrace closed (weekdays only) | 2025-09-22 | 2025-09-30
Southside / Newington | South East | GEORGE SQUARE AREA |  | George Square Festival | East leg closed 23/06 - 03/09/25. North leg and Crichton Street closed 30/07 - 26/08/25. One-way restrictions in place on Crichton Street, George Square, George Square Lane and Buccleuch Place, 30/06 - 30/07 and 26/08 - 03/09/25 | 2025-06-23 | 2025-09-03
Southside / Newington | South East | DALKEITH ROAD | At East Preston Street | City of Edinburgh Council - footway buildouts | 3-way temporary traffic lights | 2025-07-07 | 08/08/25 12/08/25 15/08/25
Southside / Newington | South East | HILL SQUARE |  | Hill Square festival fringe | Road closed and Hill Place eastbound only between Hill Square and Richmond Place | 2025-07-14 | 2025-08-29
Southside / Newington | South East | ROXBURGH PLACE | At Drummond Street | Assembly Festival | Road closed | 2025-07-16 | 2025-08-28
Southside / Newington | South East | SOUTH CLERK STREET | Bernard Terrace to Lutton Place | Clancy Docwra - mains repairs for Scottish Water | Southbound lane closure | 2025-08-13 | TBC
Southside / Newington | South East | WHITEHOUSE TERRACE / NEWBATTLE TERRACE | Either side of Whitehouse Loan junction | City of Edinburgh Council - footway resurfacing | Lane closures and parking restrictions, details TBC | 2025-08-18 | 4-5 weeks estimated
Southside / Newington | South East | MINTO STREET | At Salisbury Place | Scottish Water - manhole repair | 4-way temporary traffic lights | 2025-09-09 | 2025-09-09
Trunk road network |  | M8 | Between J3A and 4 | BEAR Scotland - B792 bridge refurbishment | Contraflow and 40mph speed restriction from Tuesday 20/05/25. Westbound carriageway reduced to single lane 8.30pm - 6am on night of 24/08/25. | 2025-05-18 | 4 months estimated
Trunk road network |  | FORTH ROAD BRIDGE |  | BEAR Scotland - bridge maintenance | Road closed 9.30pm - 4am for 2 nights, then single lane closures until October. | 2025-05-22 | October 2025
Trunk road network |  | M8 | Between J2 and J3 | BEAR Scotland - drainage investigations | Lane closures 8.30pm - 6am each night | 2025-08-11 | 2025-09-16
Trunk road network |  | A1 | Between Old Craighall and Wallyford | BEAR Scotland - carriageway resurfacing and bridge joint repairs | 20/08/25 - road closed to northbound traffic 8.30pm - 6am for 5 weekday nights; 01/09/25 - as above plus partial closure of Old Craighall roundabout for 1 night; 02/09/25 - road closed to southbound traffic QMU to Wallyford for 1 night; 03/09/25 - road closed to southbound traffic Old Craighall to Wallyford for 8 weekday nights. | 2025-08-20 | 2025-09-13
Trunk road network |  | M9 | At J1 Newbridge underpass | BEAR Scotland - carriageway repairs | Road closed to southbound traffic 8.30pm - 6am, diversion via Newbridge roundabout. | 2025-08-22 | 2025-08-23
Trunk road network |  | M8 | J3A - J4A | BEAR Scotland - carriageway resurfacing (J4A off-slip) | Road closed to westbound traffic 8.30pm - 6am for 4 nights | 2025-08-26 | 2025-08-30
Trunk road network |  | M8 | J2 - J3 | BEAR Scotland - carriageway resurfacing | Road closed to westbound traffic 8.30pm - 6am each weekday night | 2025-09-01 | 2025-09-18
Trunk road network |  | A702 / Old Pentland Road | Between Roseneath and Snowsports centre | Scottish Power - new supply | Overnight temporary traffic lights | 2025-09-22 | 2025-10-24
Roadworks & events report
Effective from 14 August 2025