## General Road Works
Links to further information
| Traffic Scotland - realtime information on trunk roads including Edinburgh City Bypass |  |  |  | Details of Ward and Locality boundaries
SE Scotland trunk roads maintenance by BEAR Scotland
Key
| Transport for Edinburgh - Lothian Buses and Edinburgh Trams |  |  |  | New or updated information in this version
Underlined entries contain links to maps or further information
Edinburgh Travelling Safely measures and Low Traffic Neighbourhoods
| Our social media channels: |  | X (formerly Twitter) | Facebook | Threads
Excel - use the drop-down arrows to sort by any column. PDF - use CTRL + F to search for any keyword. |  |  |  | NB this is not intended to be a list of all the roadworks in Edinburgh. Please refer to the Scottish Roadworks Register website for basic information on all registered roadworks
Ward | Locality | Street | Location | Contractor / works description | Measures in place | Start | Finish
Almond | North West | MAYBURY ROAD | At Craigs Road | Construction of signalised junction | Craigs Road closed on west side of Maybury Road from 06/05/25; Phase 2 - various lane closures and contraflow arrangements from 26/05/25; Phase 3 - 2-way traffic on northbound carriageway, Craigs Road closed on east side, estimated start 06/10/25; Phase 4 - temporary traffic lights, estimated start 10/12/25. | 2025-05-06 | 6 months estimated
Almond | North West | QUEENSFERRY AREA |  | Cruise liner visits. Click cell for full schedule | For each visit: prohibition of motor vehicles on Bankhead Road south of Station Road, parking restrictions as signed on Hawes car park, Newhalls Road and Hawes Brae | 2025-05-07 | 2025-10-09
Almond | North West | A89 / A8 | Between Broxburn and Gogar | City of Edinburgh Council - ground investigation surveys | Primarily nightshift works with lane closures and temporary bus stops as required. Some off-peak daytime works TBA. | 2025-07-14 | Late September 2025
Almond | North West | A90 | Between Cramond Brig and Dolphington | City of Edinburgh Council - verge works | Lane closures 7pm - midnight: Monday - inside lane northbound, Tuesday - outside lanes, Wednesday - inside lane citybound | 2025-09-01 | 2025-09-03
City Centre | South East | NORTH BRIDGE |  | City of Edinburgh Council / Balfour Beatty - bridge refurbishment | East footway closed, pedestrian access via west footway. One traffic lane open in each direction (as of 21/04/23). | 2020-02-15 | Summer 2026
City Centre | South East | TARVIT STREET |  | Redevelopment of King's Theatre | Tarvit Street closed between Home Street and Drumdryan Street. Drumdryan Street northbound only. NCR 75 closed, cycle diversion signed via Valleyfield Street | 2023-02-14 | Late 2026
City Centre | South East | DEVON PLACE | Between West Coates and no. 4 | For Ogilvie Construction | Road closed to southbound traffic. | 2023-06-06 | March 2026
City Centre | South East | CALTON ROAD | At Leith Street | Crane lift Postponed due to gas main repairs at Abbeymount, new date TBA | Road closed | 2025-06-29 | 2025-06-29
City Centre | South East | HILL STREET | Between its junctions with Hill Street North / South Lane | Clancy Docwra for Scottish Water | Road closed | 2025-08-06 | 20/08/25 26/08/25 01/09/25 03/09/25
City Centre | South East | SOUTH CHARLOTTE STREET |  | SGN - gas leak repairs | Southbound lanes closed, contraflow on northbound side. Northbound lane closure on Lothian Road to get traffic into one lane prior to the Princes Street junction. | 2025-08-19 | TBC
City Centre | South East | MORRISON STREET | Between Morrison Link and Dewar Place | SGN - gas leak repairs | Road closed to eastbound traffic and Grove Street closed at Morrison Street. Southbound lane closure on Torphichen Place, Grove Street one-way order suspended to allow access via Fountainbridge. | 2025-08-22 | TBC
City Centre | South East | COCKBURN STREET | In its entirety | Film shoot | Road closed 7pm Friday - 1am Saturday | 2025-09-05 | 2025-09-06
City Centre | South East | ROYAL MILE AREA |  | March (Johnston Terrace to Scottish Parliament) | Johnston Terrace, Castlehill, Lawnmarket (west) closed 11am - 3pm. Lawnmarket (east), High Street, George IV Bridge, Bank Street, St Giles Street, Canongate, Horse Wynd, Queen's Drive to Broad Pavement car park closed 11.45am - 3pm. | 2025-09-06 | 2025-09-06
City Centre | South East | THISTLE STREET NORTH EAST LANE |  | Hyperoptic - cabling and clearing ducts | Road closed | 2025-09-07 | 2025-09-07
City Centre | South East | HOLYROOD ROAD | At Holyrood Gait | Locktel for Cityfibre - proving / clearing cable ducts | 3-way temporary traffic lights | 2025-09-08 | 2025-09-10
City Centre | South East | REGENT ROAD | At the old Royal High | BT - ironwork repairs | 2-way temporary traffic lights | 2025-09-08 | Up to 5 days
City Centre | South East | DEVON PLACE | Between the south east corner and Devon Gardens | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-09-08 | 2025-09-17
City Centre | South East | HOME STREET |  | Cityfibre - installations | Northbound lane closure, Lochrin Terrace closed | 2025-09-08 | 2025-09-12
City Centre | South East | LOTHIAN ROAD | At Festival Square | Cityfibre - manhole repair | Northbound lane closure, temporary taxi rank at Capital House | 2025-09-08 | 2025-09-12
City Centre | South East | ROSE STREET SOUTH LANE | Section between Castle Street and Frederick Street | SGN - gas main disconnection | Road closed | 2025-09-08 | 2025-09-26
City Centre | South East | ATHOLL CRESCENT LANE |  | Scottish Water - ironwork repair | Road closed | 2025-09-09 | 2025-09-09
City Centre | South East | WEST MAITLAND STREET |  | Scottish Water - ironwork repair | Citybound lane closure, bus stops closed. 12.15am - 4.30am. | 2025-09-13 | 2025-09-13
City Centre | South East | SHANDWICK PLACE |  | Siemens for Edinburgh Trams - track maintenance | 14/09/25 for 5 nights and 21/09/25 for 5 nights - road closed to westbound traffic 11pm - 6am each night. 11pm 26/09/25 - 5am 30/09/25 - road closed in both directions. 30/08/25 for 3 nights - road closed to westbound traffic 11pm - 5am each night. | 2025-09-14 | 2025-10-02
City Centre | South East | CANDLEMAKER ROW |  | City of Edinburgh Council - carriageway resurfacing | Daytime lane closure for gully works. Road closed 7pm - 6am each weekday night for resurfacing. | 2025-09-15 | 1 week estimated
City Centre | South East | QUEENSFERRY STREET LANE | At Queensferry Street | BT Circet - ducting installation | Road closed | 2025-09-15 | 2025-09-19
City Centre | South East | WATERLOO PLACE | Between Leith Street and Calton Hill | GPR survey | Road closed 8pm - 6am for 2 nights | 2025-09-16 | 2025-09-18
City Centre | South East | ABBEYHILL / ABBEYMOUNT JUNCTION | At the rail bridge | Network Rail - bridge inspection | Roads closed 9pm - 6am | 2025-09-18 | 2025-09-19
City Centre | South East | CENTRAL EDINBURGH | Royal Mile, Cowgate, Grassmarket, Lothian Road, West Approach Raod | Men's and Women's 10k (Lawnmarket - Holyrood Park - Murrayfield) | Multiple road closures 5am - 1.30pm approximately. Click cell for full details | 2025-09-21 | 2025-09-21
City Centre | South East | GILMORE PLACE |  | City of Edinburgh Council - carriageway resurfacing Dates and details TBC | Road closed in sections | 2025-09-22 | March 2026
City Centre | South East | LEOPOLD PLACE |  | City of Edinburgh Council - resurfacing | Daytime lane closures for gully and footway works. Road and lane closures 7pm - 6am each weekday night for resurfacing: citybound traffic diverted via Regent Road, eastbound traffic as normal for week 1 and contraflow on citybound side for week 2. | 2025-09-22 | 2 weeks estimated
City Centre | South East | HAYMARKET TERRACE | At Haymarket Yards | BRM Utilities - manhole repair for Vodafone | 3-way temporary traffic lights 12.30am - 4.30am on Wednesday, westbound lane restriction thereafter. | 2025-09-24 | 2025-09-26
City Centre | South East | CALTON ROAD | Between Waverley station access and New Street | Scottish Water - ironwork repair | Road closed | 2025-09-28 | 2025-09-28
City Centre | South East | GAYFIELD SQUARE | At Gayfield Street | SGN - gas main renewal | 2-way temporary traffic lights, Gayfield Street closed | 2025-09-29 | 2025-10-17
City Centre | South East | ROSE STREET SOUTH LANE | Section between South Charlotte Street and Castle Street | Clancy Docwra for Scottish Water | Road closed | 2025-09-29 | 2025-10-08
City Centre | South East | ALBYN PLACE |  | Clancy Docwra for Scottish Water | Eastbound inside lane closed | 2025-10-01 | 2025-10-08
City Centre | South East | LONDON ROAD | At Hillside Crescent | City of Edinburgh Council - pedestrian crossing upgrade | Lane closures, temporary traffic lights as required | 2025-10-06 | 2 weeks estimated
City Centre | South East | CORNWALL STREET | At Castle Terrace | Crane lift | Road closed | 2025-10-09 | 2025-10-09
City Centre | South East | THISTLE STREET | At Hanover Street (west side) | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-10-20 | 2025-10-24
City Centre | South East | WEST PORT | At Lady Lawson Street | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-10-26 | 2025-10-26
City Centre | South East | VALLEYFIELD STREET |  | Scottish Water - service connection | Road closed except for cycles | 2025-12-01 | 2025-12-10
City Centre | South East | ROSEBERY CRESCENT | At Haymarket Terrace | Clancy Docwra for Scottish Water To be rescheduled for January 2026 | Road closed | 2025-12-15 | 2025-12-19
City Centre & Craigentinny / Duddingston | South East | HOLYROOD PARK AREA |  | Edinburgh Moonwalk | Holyrood Gait, Horse Wynd, Queen's Drive and Duke's Walk closed 10pm - 1.30am | 2025-09-06 | 2025-09-07
Colinton / Fairmilehead | South West | MOUNTHOOLY LOAN | Between Galachlawside and Galachlawshot | Clancy Docwra for Scottish Water - pipe repairs | Road closed. Temporary traffic lights during w/c 01/09/25. | 2025-08-25 | 2025-09-05
Colinton / Fairmilehead | South West | CAMUS AVENUE | At East Camus Place | Scottish Power - new supply | Temporary traffic lights | 2025-09-01 | 2025-09-12
Colinton / Fairmilehead | South West | REDFORD ROAD | At Redford Drive | Cityfibre - remedial works | 3-way temporary traffic lights | 2025-09-02 | 2025-09-04
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Murrayfield | Scottish Water - major works to install combined sewer overflow (CSO) | Temporary traffic lights. Ormidale Terrace closed. Westbound bus stop closed, please use the next stop. | 2025-06-08 | November 2025
Corstorphine / Murrayfield | North West | COLTBRIDGE TERRACE |  | Clancy Docwra for Scottish Water | Road closed to through traffic nos. 22 - 26 | 2025-09-01 | 2025-09-10
Corstorphine / Murrayfield | North West | RAVELSTON DYKES ROAD |  | Edinburgh Moonwalk | Road closed 11.30pm - 3.45am | 2025-09-06 | 2025-09-07
Corstorphine / Murrayfield | North West | CRAIGLEITH CRESCENT | Between Ravelston Dykes and Craigleith View | Clancy Docwra for Scottish Water | Temporary traffic lights | 2025-09-08 | 2025-09-17
Corstorphine / Murrayfield | North West | CORSTORPHINE AREA |  | Corstorphine Connections scheme - replacing some temporary measures with permanent materials. Dates and details TBC | Phased closures of Kirk Loan and Manse Road | 2025-09-18 | Late October
Corstorphine / Murrayfield | North West | ROSEBURN STREET | At West Approach Road | Men's and Women's 10k (Lawnmarket - Holyrood Park - Murrayfield) | Road closed 8.30am - 1.30pm. Click cell for more details. | 2025-09-21 | 2025-09-21
Corstorphine / Murrayfield | North West | BALGREEN ROAD and SAUGHTON CRESCENT |  | City of Edinburgh Council - carriageway resurfacing and active travel improvements, final details TBC. | Daytime lane closures and temporary traffic lights for preparatory and footway works, nightshift road closures for main resurfacing work. | 2025-10-20 | 9-12 weeks
Corstorphine / Murrayfield | North West | MURRAYFIELD AREA |  | Autumn Internationals - click cell for fixture list | Road closures before and after each match, details TBC. | 2025-11-01 | 2025-11-23
Corstorphine / Murrayfield | North West | ST JOHN'S ROAD | Opposite Station Road | Clancy Docwra - sewer repairs for Scottish Water Dates and details TBC | 2-way temporary traffic lights, Clermiston Road and Station Road closed | 2025-11-18 | 2025-11-27
Corstorphine / Murrayfield | North West | ELLERSLY ROAD |  | City of Edinburgh Council - carriageway resurfacing | Road closed (excluding any affected 6 Nations dates) | 2026-01-12 | Up to 6 weeeks
Craigentinny/ Duddingston | North East | ABBEY LANE | At Abbeyhill | Graham Construction - development works | Road closed | 2024-01-09 | End of October 2025
Craigentinny/ Duddingston | North East | DUDDINGSTON LOW ROAD |  | Historic Environment Scotland - risk of rock falls | Road closed to motor vehicles. Road closed to all path users from Tuesday 18/03/25, pedestrian and cyclist diversion via Innocent railway path. Reopened to pedestrians and cyclists 07/08/25, cyclists please dismount through the barrier system at Samson's Ribs. | 2025-03-15 | Until further notice
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Clark Contracts - building development (demolition phase) Not started, new dates TBA. | Section of north footway closed. | 2025-09-01 | December 2027
Craigentinny/ Duddingston | North East | WILLOWBRAE ROAD | At Willowbrae Gardens | Scottish Water - manhole repair | Temporary traffic lights and Willowbrae Gardens closed. 7pm - 7am | 2025-09-04 | 2025-09-05
Craigentinny/ Duddingston | North East | NANTWICH DRIVE | At Stapeley Avenue | Scottish Water - access to sewer overflow | Temporary traffic lights | 2025-09-08 | 2025-09-10
Craigentinny/ Duddingston | North East | WILLOWBRAE ROAD | Between Duddingston Mills and Northfield Broadway | Clancy Docwra for Scottish Water - lead renewal | Lane closures / contraflow. No right turn from the car dealership | 2025-09-08 | 2025-09-17
Craigentinny/ Duddingston | North East | RESTALRIG ROAD SOUTH | Between the rail bridge and Restalrig Avenue | Network Rail - vegetation clearance | Road closed 10pm - 6am | 2025-09-15 | 2025-09-16
Craigentinny/ Duddingston | North East | SPRING GARDENS | Between Abbey Lane and Milton Street | Network Rail - vegetation clearance | Road closed for 1 night (times TBC) | 2025-11-03 | 2025-11-04
Drum Brae / Gyle | North West | SOUTH GYLE ROAD | At the rail bridge | Network Rail - renewing rail bridge | Road closed. Access to the station car park via South Gyle Broadway - Gogarloch Road. | 2025-07-28 | April 2026
Drum Brae / Gyle | North West | LADYWELL AVENUE | Between Kirklands and Broomhall Crescent | Network Rail - renewing rail bridge | Road closed | 2025-08-21 | August 2026
Drum Brae / Gyle | North West | BROOMHOUSE ROAD | At St Augustine's HS | Scottish Power - new supply Actual start date 25/08/25 | Temporary traffic lights No significant carriageway occupation at this time | 2025-08-22 | 2025-09-05
Drum Brae / Gyle | North West | CLERMISTON ROAD NORTH |  | Scottish Power - cable fault Work finished 02/09/25 | Temporary traffic lights | 2025-08-25 | TBC
Drum Brae / Gyle | North West | GLASGOW ROAD | At Craigs Gardens | Clancy Docwra - urgent sewer repair for Scottish Water | 3-way temporary traffic lights initially then contraflow with 2-way traffic on the citybound side from mid-afternoon. | 2025-09-02 | 04/09/25 estimated
Drum Brae / Gyle | North West | CLERMISTON HILL | Between Clermiston Drive and Clermiston Park | Community event | Road closed 12pm - 4pm | 2025-09-14 | 2025-09-14
East Lothian |  | BRIDGE STREET, MUSSELBURGH | Outside Wetherspoons | Clancy Docwra - sewer repair for Scottish Water | Temporary traffic lights | 2025-09-01 | TBC
Forth | North West | CRAIGHALL ROAD | Between Craighall Avenue and Grandville | Refurbishment of Trinity Academy | Road closed | 2025-06-30 | May 2028
Forth | North West | EAST TRINITY ROAD | Between Russell Place and York Road | SGN - gas main renewal | Temporary traffic lights | 2025-08-22 | 2025-09-15
Forth | North West | BOSWALL ROAD | Near Netherby Road | Clancy Docwra - sewer repairs for Scottish Water | Temporary traffic lights | 2025-08-25 | 03/09/25 estimated
Forth | North West | BOSWALL PARKWAY | Between Pilton Avenue and Boswall Terrace | Clancy Docwra for Scottish Water - lead renewal | Temporary traffic lights | 2025-09-02 | 2025-09-11
Forth | North West | LOMOND ROAD / TRINITY ROAD | Between Primrose Bank Road and East Trinity Road | City of Edinburgh Council - micro-asphalt surfacing | Roads closed | 2025-09-08 | 2025-09-09
Forth | North West | ROYSTON TERRACE | At Inverleith Row | Clancy Docwra for Scottish Water - lead renewal | Road closed to through traffic. Existing one-way order rescinded for duration of works. | 2025-09-08 | 2025-09-17
Forth | North West | BANGHOLM ROAD |  | Clancy Docwra for Scottish Water - sewer cleaning | Road closed to through traffic. | 2025-10-20 | 2025-10-20
Fountainbridge/ Craiglockhart | South West | HARRISON ROAD | At the dog-leg bend where it crosses the cycle path and at the canal bridge | City of Edinburgh Council - bridge repairs | Road closed. Topside footway closures as signed. Road bridge expected to be renewed by end of 2025. Trial holes ongoing at canal bridge. | 2025-02-18 | Ongoing
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Moat Terrace | Scottish Power / Excalon - cable jointing Not started, new dates TBA | Temporary traffic lights | 2025-08-13 | 4-5 weeks
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Allan Park | Water main connection at development site (adjacent to Domino's) | Lane closures, loading bay suspended | 2025-08-22 | 26/08/25 Ongoing
Fountainbridge/ Craiglockhart | South West | GLENLOCKHART ROAD | Around 200m east of Napier University entrance | Collapsed manhole, reported to Scottish Water 02/09/25 | Awaiting details for urgent repair | 2025-09-02 | TBC
Fountainbridge/ Craiglockhart | South West | CRAIGLOCKHART CROSSROADS |  | Clancy Docwra for Scottish Water - mains survey | 4-way temporary traffic lights | 2025-09-14 | 2025-09-14
Fountainbridge/ Craiglockhart | South West | LANARK ROAD | At Water of Leith visitor centre | Scottish Power - mains disconnection | Westbound inside lane closed | 2025-09-15 | 2025-09-26
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At the rail bridge | Network Rail - bridge maintenance | Temporary traffic lights 7pm - 7am | 2025-09-20 | 2025-09-21
Fountainbridge/ Craiglockhart | South West | CRAIGLOCKHART CROSSROADS |  | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-09-21 | 2025-09-21
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | Between Ford's Road and Balgreen Road | Mackenzie Construction for Scottish Water - installation of new water meter | Outside lane closed in both directions. Bus stops closed on both sides. | 2025-09-22 | 2025-09-24
Fountainbridge/ Craiglockhart | South West | ROBB'S LOAN | At Eltringham Gardens | Clancy Docwra - sewer works for Scottish Water | 3-way temporary traffic lights | 2025-09-22 | 2025-09-24
Fountainbridge/ Craiglockhart | South West | HUTCHISON PLACE | At Slateford Road | Scottish Water - ironwork repair | Road closed | 2025-09-29 | 2025-09-29
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Coxfield | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-09-29 | 2025-09-29
Fountainbridge/ Craiglockhart | South West | ALLAN PARK ROAD |  | Clancy Docwra for Scottish Water | Temporary traffic lights | 2025-10-13 | 7-10 days
Fountainbridge/ Craiglockhart | South West | RITCHIE PLACE | At Watson Crescent | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-11-05 | 2025-11-14
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | Between Ford's Road and Balgreen Road | Scottish Water - major works to install combined sewer overflow (CSO) | Road closed and section of north footway closed. | 2026-01-04 | 16 weeks
Inverleith | North West | TELFORD PLACE | At Telford Road | SGN - gas main renewal | Road closed | 2025-08-18 | 2025-09-30
Inverleith | North West | RAEBURN PLACE | At Portgower Place | Scottish Water - repairs to burst main | 3-way temporary traffic lights (from 8pm Monday) | 2025-09-01 | TBC
Inverleith | North West | COMELY BANK ROAD | At East Fettes Avenue | Scottish Water - mains survey | 4-way temporary traffic lights 8am - 1pm approximately | 2025-09-07 | 2025-09-07
Inverleith | North West | QUEENSFERRY ROAD | At Blackhall dip | City of Edinburgh Council - carriageway repairs Second of two consecutive Sundays | 3-way temporary traffic lights at Maidencraig Crescent. Craigcrook Road closed | 2025-09-07 | 2025-09-07
Inverleith | North West | RAEBURN PLACE | At Raeburn Street | SGN - gas main alteration | 2-way temporary traffic lights | 2025-09-08 | 10 days estimated
Inverleith | North West | CANONMILLS | At Inverleith Row / Brandon Terrace | Vodafone - proving cable ducts | 3-way temporary traffic lights, 8pm - 6am | 2025-09-10 | 2025-09-11
Inverleith | North West | LEARMONTH TERRACE | At Dean Park Crescent | Community event | Road closed 10am - 4pm | 2025-09-14 | 2025-09-14
Inverleith | North West | HAMILTON PLACE | At Stockbridge library | Clancy Docwra - sewer cleaning | Temporary traffic lights | 2025-10-09 | 2025-10-09
Leith | North East | LINDSAY ROAD BRIDGE | Pedestrian / cycle bridge between Nicholfield and Lindsay Road main carriageway | City of Edinburgh Council - public safety measure | Bridge closed, pedestrian and cycle diversion as signed. Hawthornvale Path beneath remains open | 2021-12-15 | Until further notice
Leith | North East | HENDERSON STREET | Between Shore and Parliament Street | City of Edinburgh Council - construction of segregated cycle lane | Lane closures, parking restrictions, temporary traffic lights if required. One-way (southbound) system with northbound access via Cables Wynd from 19/03/25. w/c 25/08/25 - 2-way traffic restored. Temporary traffic lights at northern end and Parliament Street closed at Henderson Street. | 2024-12-03 | Summer 2025
Leith | North East | NEWHAVEN AREA |  | Cruise liner visits. Click cell for full schedule | Parking restrictions as signed on Pier Place and Newhaven Place for each visit | 2025-04-02 | 2025-09-27
Leith | North East | NORTH FORT STREET | At Madeira Place | Clancy Docwra - emergency repairs for Scottish Water | Temporary traffic lights | 2025-08-20 | 29/08/25 05/09/25
Leith | North East | LINDSAY ROAD | Between North Leith Sands and Hawthornvale path | Virgin Media | Temporary traffic lights 7pm - 7am | 2025-09-04 | 2025-09-05
Leith | North East | BONNINGTON ROAD | At Great Junction Street | Scottish Water - ironwork repair | 4-way temporary traffic lights 7pm - 7am | 2025-10-24 | 2025-10-25
Leith Walk | North East | ALBION ROAD | Between Easter Road and Albion Place | Scottish Water - collapsed manhole | Road closed | 2025-08-07 | TBC
Leith Walk | North East | MCDONALD ROAD | Outside Kwik Fit | Scottish Power - cable fault | Lane closures / contraflow (right turn lane into Leith Walk closed) | 2025-08-27 | TBC
Leith Walk | North East | MCDONALD ROAD | At Bellevue Road | Scottish Water - drainage survey | 3-way temporary traffic lights | 2025-09-06 | 2025-09-07
Leith Walk | North East | STEAD'S PLACE |  | Community event | Road closed 10am - 6.30pm | 2025-09-07 | 2025-09-07
Leith Walk | North East | LEITH WALK | Pilrig Street to Foot of the Walk | Bilfinger for Edinburgh Trams - concrete repairs | Road closed to northbound traffic 12.15am - 4.30am for 3 mornings. | 2025-09-08 | 2025-09-10
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Dundee Utd, kick-off 5.45pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-09-13 | 2025-09-13
Leith Walk | North East | BRUNSWICK STREET | Between Elm Row and Montgomery Street | Community event | Road closed 12pm - 8pm | 2025-09-13 | 2025-09-13
Leith Walk | North East | EASTER ROAD | Between Sunnyside and Drum Terrace | Clancy Docwra for Scottish Water | 4-way temporary traffic lights | 2025-10-05 | 2025-10-07
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | BT Morrison - fibre installation To be rescheduled | Off-peak 3-way temporary traffic lights | 2025-08-18 | 2025-08-18
Liberton / Gilmerton | South East | HOWDEN HALL ROAD | Between Mortonhall and Alnwickhill Road | Scottish Power - trial holes | Temporary traffic lights | 2025-09-08 | 2025-09-12
Liberton / Gilmerton | South East | LIBERTON GARDENS | Between Longformacus Road and Liberton Place | Scottish Water - ironwork repair | Lane closures and contraflow, citybound cycle lane closed | 2025-09-08 | 2025-09-08
Liberton / Gilmerton | South East | GILMERTON ROAD | Between The Spinney and Morrisons | Clancy Docwra for Scottish Water - lead renewal | 3-way temporary traffic lights | 2025-09-09 | 2025-09-19
Liberton / Gilmerton | South East | LIBERTON BRAE | Between Cadogan Road and Wolrige Road | Scottish Water - ironwork repair | Lane closures and contraflow, bus stops closed on both sides | 2025-09-09 | 2025-09-09
Liberton / Gilmerton | South East | LIBERTON ROAD | At Gilmerton Road | Locktel for Cityfibre - proving / clearing cable ducts | 3-way temporary traffic lights 9.30am - 5pm each day | 2025-09-10 | 2025-09-11
Liberton / Gilmerton | South East | LASSWADE ROAD | At Gracemount high school | BT Morrison - fibre installation | 2-way temporary traffic lights and separate lane closures between the school and Captain's Road | 2025-09-12 | 2025-09-13
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | Telecoms company - pole replacement (preparatory works) | 3-way temporary traffic lights | 2025-09-20 | 2025-09-24
Liberton / Gilmerton | South East | KAIMES CROSSROADS |  | Openreach - access to carriageway manholes | Off-peak 4-way temporary traffic lights | 2025-09-21 | 2025-09-21
Liberton / Gilmerton | South East | GILMERTON ROAD | At Guardwell Glen | BT Morrison - fibre installation | 3-way temporary traffic lights 7pm - 6am | 2025-09-22 | 2025-09-23
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | Telecoms company - pole replacement | 3-way temporary traffic lights | 2025-10-04 | 2025-10-05
Midlothian |  | A7 at ESKBANK |  | Midlothian Council - carriageway resurfacing and footway construction | Lane closures. Lasswade Road closed between A7 and Captains Gardens. Lasswade Road reopened Monday 18/08/25, lane restrictions thereafter for phase 2. | 2025-07-07 | Late September 2025
Midlothian |  | MILLERHILL ROAD | Between Shawfair Spine Road and Newton Village | Carriageway upgrade / footway widening / traffic signal installation / utility diversion works / district heating system installation | Temporary traffic lights | 2025-08-11 | April 2026
Morningside | South East | MARCHMONT ROAD |  | Scottish Power - cable installations | Phase 1 - 3-way temporary traffic lights at Beaufort Road, Marchmont Road closed to southbound traffic; Phase 2 - 3-way temporary traffic lights at Marchmont Crescent, no exit from Spottiswoode Road. | 2025-08-04 | 26/09/25 estimated
Morningside | South East | CRAIGLEA DRIVE | Between St Ninian's Terrace and St Claire Terrace | Community event | Road closed 1pm - 4pm | 2025-09-07 | 2025-09-07
Morningside | South East | GREENHILL GARDENS | At Church Hill | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-09-08 | 2025-09-08
Morningside | South East | BRUNTSFIELD PLACE | Between Holy Corner and Merchiston Place | Clancy Docwra for Scottish Water - lead renewal | Narrow lane citybound with contraflow | 2025-09-14 | 2025-09-21
Morningside | South East | GILMORE PLACE | At Viewforth | Scottish Water - ironwork repair New date, previously listed for 08/09/25 | 4-way temporary traffic lights | 2025-10-05 | 2025-10-05
Morningside | South East | BRUNTSFIELD PLACE | At Viewforth | Clancy Docwra for Scottish Water - valve repairs | 2-way temporary traffic lights, Viewforth closed | 2025-12-07 | 2025-12-16
Pentland Hills | South West | DEANPARK AVENUE | At Deanpark Grove | Scottish Power - mains upgrade | Temporary traffic lights | 2025-08-08 | 21/08/25 28/08/25 04/09/25
Pentland Hills | South West | LANARK ROAD WEST | At Gibson Craig Hall | Scottish Water - lead renewal Work postponed, new dates TBA | Temporary traffic lights | 2025-08-27 | 2025-08-29
Pentland Hills | South West | KIRKGATE | At Lanark Road West | BT Morrison - fibre installation / clearing blocked ducts Road reopened 03/09/25 | Road closed | 2025-08-28 | TBC
Pentland Hills | South West | WOODHALL TERRACE | At Woodhall Drive | BT Morrison - ducting installation | Temporary traffic lights | 2025-08-29 | 2025-09-04
Pentland Hills | South West | CLIFTONHALL ROAD | At Clifton Road (south junction) | Scottish Water - repairs to burst main | Temporary traffic lights, Clifton Road closed | 2025-09-01 | TBC
Pentland Hills | South West | JOHNSBURN ROAD | Between Main Street and Lovedale Road | City of Edinburgh Council - manhole repairs | Temporary traffic lights | 2025-09-01 | Up to 5 days
Pentland Hills | South West | WESTER HAILES ROAD |  | City of Edinburgh Council - litter picking and grass cutting | Outside lane closed in both directions | 2025-09-17 | 2025-09-17
Pentland Hills | South West | CURRIEHILL ROAD | Between Pentland View and Forthview Crescent | Scottish Water - ironwork repair | Road closed 9.30am - 9pm | 2025-10-14 | 2025-10-14
Portobello/ Craigmillar | North East | BRUNSTANE ROAD | Between Milton Road East and Argyle Crescent / Dalkeith Street | City of Edinburgh Council - Low Traffic Neighbourhood trial Click cell for more details | Road closed to through traffic, except cycles | 2022-02-15 | Ongoing
Portobello/ Craigmillar | North East | ABERCORN TERRACE / PORTOBELLO HIGH STREET |  | GTC Pipelines - utility connections for housing development | Rolling programme with lane closures, temporary traffic lights and side-road closures as required (at Marlborough Street as of 01/09/25, expected at Brighton Place / Bath Street from 08/09/25). | 2025-05-27 | October 2025 estimated
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | Starting at Duddingston Park South crossroads, working eastwards to Fort Kinnaird | Energetics - ducting installation for new HV power cables | 4-way temporary traffic lights at the crossroads for 2 weeks until 06/08/25 then lane closures and no right turns into or out of Peacocktail Close, Cleikiminfield, Cleikiminrig and Blackchapel Close. | 2025-07-28 | 8-10 weeks estimated
Portobello/ Craigmillar | North East | GREENDYKES ROAD | At Greendykes Drive | Drainage installation | Road closed, diversion via Tudsbury Avenue | 2025-08-04 | 2025-09-30
Portobello/ Craigmillar | North East | DUDDINGSTON ROAD | Outside St John's RC School | BT Circet - pole replacement | Road closed | 2025-09-07 | 2025-09-07
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Flint Terrace | Scottish Water - manhole repair Dates and details TBC | 3-way temporary traffic lights | 2025-09-08 | 2025-09-08
Portobello/ Craigmillar | North East | WHITEHILL ROAD | Outside the Honda garage | Installation of new sewer services | Temporary traffic lights | 2025-09-08 | 2025-09-15
Portobello/ Craigmillar | North East | GREENDYKES ROAD | Between Scott Street and Friary Road | Scottish Water - ironwork repair | Temporary traffic lights | 2025-09-09 | 7am 10/09/25
Portobello/ Craigmillar | North East | SIR HARRY LAUDER ROAD | Adjacent to the railway line | Network Rail - devegetation | Off-peak temporary traffic lights | 2025-09-10 | 2025-09-10
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | Between Benhar Road and the rail bridge | Scottish Water - lead renewal | 2-way temporary traffic lights, bus stops closed on both sides. | 2025-09-20 | 8am 22/09/25 estimated
Portobello/ Craigmillar | North East | MUSSELBURGH ROAD | At Coillesdene Terrace | Clancy Docwra for Scottish Water - lead renewal | 3-way temporary traffic lights | 2025-12-01 | 2025-12-10
Sighthill/Gorgie | South West | PARKHEAD TERRACE | At Parkhead Loan | Scottish Power - works for substation | Temporary traffic lights, Parkhead Loan closed between Longstone Road and Parkhead Terrace | 2025-08-22 | 2025-09-19
Sighthill/Gorgie | South West | MCLEOD STREET |  | Hearts Women v Hibs Women at Tynecastle, kick-off 1.10pm | Parking suspended on both sides. Road closed 12:10pm to 1:10pm and 2:40pm to 3:40pm | 2025-09-07 | 2025-09-07
Sighthill/Gorgie | South West | INGLIS GREEN ROAD | At Redhall Drive / Sainsburys | Scottish Water - access to sewer overflow | 3-way temporary traffic lights, Redhall Drive closed | 2025-09-10 | 2025-09-10
Sighthill/Gorgie | South West | GORGIE ROAD | At Springwell House | Scottish Water - ironwork repair | Temporary traffic lights 7pm - 7am | 2025-09-12 | 2025-09-13
Sighthill/Gorgie | South West | DALRY ROAD | At Murieston Crescent | Openreach - manhole reconstruction | 2-way temporary traffic lights, Murieston Crescent closed | 2025-09-15 | 2025-09-21
Sighthill/Gorgie | South West | WEST APPROACH ROAD | Lothian Road to Roseburn Street | Men's and Women's 10k (Lawnmarket - Holyrood Park - Murrayfield) | Westbound carriageway closed 8.30am - 1.30pm. Click cell for more details. | 2025-09-21 | 2025-09-21
Sighthill/Gorgie | South West | CALDER ROAD SERVICE ROAD | At Parkhead Terrace | Telecoms company - mast and cabinet renewal | Service road and Parkhead Terrace closed (weekdays only). Some nighttime occupation of westbound Calder Road for crane lift, details TBC. | 2025-09-22 | 2025-09-30
Sighthill/Gorgie | South West | DALRY ROAD | At Caledonian Place | Scottish Water - ironwork repair | 3-way temporary traffic lights, West Park Place closed | 2025-09-24 | 2025-09-24
Sighthill/Gorgie | South West | DALRY ROAD | At Orwell Terrace | Cityfibre - manhole repair | Temporary traffic lights, Orwell Terrace closed | 2025-09-25 | 2025-09-26
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Falkirk, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-09-27 | 2025-09-27
Southside / Newington | South East | GEORGE SQUARE AREA |  | George Square Festival | East leg closed 23/06 - 03/09/25. North leg and Crichton Street closed 30/07 - 26/08/25. One-way restrictions in place on Crichton Street, George Square, George Square Lane and Buccleuch Place, 30/06 - 30/07 and 26/08 - 03/09/25 | 2025-06-23 | 2025-09-03
Southside / Newington | South East | SOUTH CLERK STREET | Bernard Terrace to Lutton Place | Clancy Docwra - sewer repairs for Scottish Water | Southbound lane closure | 2025-08-13 | 26/08/25 estimated Ongoing
Southside / Newington | South East | WHITEHOUSE TERRACE / NEWBATTLE TERRACE | Either side of Whitehouse Loan junction | City of Edinburgh Council - footway resurfacing | Lane closures and parking restrictions, details TBC | 2025-08-18 | 4-5 weeks estimated
Southside / Newington | South East | MENTONE TERRACE |  | City of Edinburgh Council - carriageway resurfacing | Road closed (and Moston Terrace closed at Mentone Terrace) | 2025-09-01 | 2025-09-05
Southside / Newington | South East | BLACKFORD AVENUE | At Charterhall Road | Scottish Water - access to sewer overflow | 4-way temporary traffic lights | 2025-09-06 | 2025-09-07
Southside / Newington | South East | MANSIONHOUSE ROAD | Section between Grange Road and Dick Place (at no. 26) | Scottish Water - new service connection | Road closed to through traffic | 2025-09-08 | 2025-09-12
Southside / Newington | South East | ST THOMAS ROAD |  | City of Edinburgh Council - carriageway resurfacing | Road closed to through traffic in sections | 2025-09-08 | 2025-09-12
Southside / Newington | South East | MINTO STREET | At Salisbury Place | Scottish Water - manhole repair | 4-way temporary traffic lights | 2025-09-09 | 2025-09-09
Southside / Newington | South East | MINTO STREET | At Salisbury Place | Scottish Water - manhole repair | 4-way temporary traffic lights | 2025-09-14 | 2025-09-14
Southside / Newington | South East | FOUNTAINHALL ROAD | Between Findhorn Place and Newington library | Clancy Docwra for Scottish Water | Road closed | 2025-09-25 | 2025-09-25
Southside / Newington | South East | MINTO STREET | At Blacket Place | Clancy Docwra for Scottish Water | 3-way temporary traffic lights, Duncan Street closed | 2025-11-10 | 2025-11-19
Trunk road network |  | M8 | Between J3A and 4 | BEAR Scotland - B792 bridge refurbishment | Contraflow and 40mph speed restriction from Tuesday 20/05/25. Westbound carriageway reduced to single lane 8.30pm - 6am on night of 24/08/25. | 2025-05-18 | 4 months estimated
Trunk road network |  | FORTH ROAD BRIDGE |  | BEAR Scotland - bridge maintenance | Road closed 9.30pm - 4am for 2 nights, then single lane closures until October. | 2025-05-22 | October 2025
Trunk road network |  | M8 | Between J2 and J3 | BEAR Scotland - drainage investigations | Lane closures 8.30pm - 6am each night | 2025-08-11 | 2025-09-16
Trunk road network |  | A1 | Between Old Craighall and Wallyford | BEAR Scotland - carriageway resurfacing and bridge joint repairs | Series of overnight carriageway closures - click cell for full details | 2025-08-21 | 2025-09-19
Trunk road network |  | M9 | Between J1 and J10 | BEAR Scotland - maintenance | Series of overnight lane and carriageway closures - click cell for full details | 2025-09-01 | 2025-10-15
Trunk road network |  | M8 | J2 - J3 | BEAR Scotland - carriageway resurfacing | Road closed to westbound traffic 8.30pm - 6am each weekday night | 2025-09-02 | 2025-09-18
Trunk road network |  | M9 | Between J3 and J4 | BEAR Scotland - bridge refurbishment | Road closed in both directions 7.30pm - 6am | 2025-09-03 | 2025-09-04
Trunk road network |  | M8 | At J2 | BEAR Scotland - street lighting renewal | Eastbound on-slip closed 8pm - 6am for 6 nights | 2025-09-15 | 2025-09-21
Trunk road network |  | A720 | Lothianburn to Dreghorn | BEAR Scotland - carriageway resurfacing | Road closed to westbound traffic 8.30pm - 6am for 5 weekday nights | 2025-09-16 | 2025-09-23
Trunk road network |  | A702 / OLD PENTLAND ROAD | Between Roseneath and Snowsports centre | Scottish Power - new supply | Overnight temporary traffic lights | 2025-09-22 | 2025-10-24
Trunk road network |  | M8 | Between J2 and J3A | BEAR Scotland - carriageway resurfacing | Eastbound on-slip at J3 closed 8.30pm - 6am for 4 nights. Eastbound carriageway closed J3A - J2, 8.30pm - 6am from 29/09/25 for 15 weekday nights. | 2025-09-23 | 2025-10-18
Roadworks & events report
Effective from 3 September 2025