## General Road Works
Links to further information
| Traffic Scotland - realtime information on trunk roads including Edinburgh City Bypass |  |  |  | Details of Ward and Locality boundaries
SE Scotland trunk roads maintenance by BEAR Scotland
Key
| Transport for Edinburgh - Lothian Buses and Edinburgh Trams |  |  |  | New or updated information in this version
Underlined entries contain links to maps or further information
Edinburgh Travelling Safely measures and Low Traffic Neighbourhoods
| Our social media channels: |  | X (formerly Twitter) | Facebook | Threads
Excel - use the drop-down arrows to sort by any column. PDF - use CTRL + F to search for any keyword. |  |  |  | NB this is not intended to be a list of all the roadworks in Edinburgh. Please refer to the Scottish Roadworks Register website for basic information on all registered roadworks
Ward | Locality | Street | Location | Contractor / works description | Measures in place | Start | Finish
Almond | North West | MAYBURY ROAD | At Craigs Road | Construction of signalised junction | Craigs Road closed on west side of Maybury Road from 06/05/25; Phase 2 - various lane closures and contraflow arrangements from 26/05/25. NEW - Craigs Road closed on east side from 22/09/25. Phase 3 - 2-way traffic on northbound carriageway , estimated start 06/10/25; Phase 4 - temporary traffic lights, estimated start 10/12/25. | 2025-05-06 | 6 months estimated
Almond | North West | QUEENSFERRY AREA |  | Cruise liner visits. Click cell for full schedule | For each visit: prohibition of motor vehicles on Bankhead Road south of Station Road, parking restrictions as signed on Hawes car park, Newhalls Road and Hawes Brae | 2025-05-07 | 2025-10-09
Almond | North West | A89 / A8 | Between Broxburn and Gogar | City of Edinburgh Council - ground investigation surveys | Primarily nightshift works with lane closures and temporary bus stops as required. | 2025-07-14 | Late September 2025
Almond | North West | MAIN STREET, DALMENY | At Easter Dalmeny Cottages | Scottish Power - new service installation | Temporary traffic lights | 2025-09-12 | 2025-09-25
Almond | North West | STIRLING ROAD | At the M9 bridge | City of Edinburgh Council - carriageway resurfacing | Temporary traffic lights | 2025-09-15 | 8-10 weeks estimated
Almond | North West | GOGARMUIR ROAD | At the M8 bridge (west of Roddinglaw Road) | Telecoms company - decommissioning and replacement of tower and cabinet | Road closed 8am - 4.30pm on Tuesday 16/09/25 and Friday 19/09/25 | 2025-09-16 | 2025-09-19
Almond | North West | GATESIDE ROAD, KIRKLISTON | Just off Newliston Road | Clancy Docwra - mains repairs for Scottish Water | 3-way temporary traffic lights | 2025-09-17 | TBC
Almond | North West | OLD LISTON ROAD | Between Parkside and Bridge Street | Scottish Power - street lighting repair | Temporary traffic lights | 2025-09-19 | 2025-10-02
Almond | North West | TURNHOUSE ROAD | At Macginlay Way | Scottish Water - manhole repair | 3-way temporary traffic lights | 2025-09-20 | 7am 21/09/25
Almond | North West | GLASGOW ROAD | Between Ratho Station and Ingliston | Clarke Telecom - cabinet works | Off-peak citybound lane closure to accommodate temporary walkway. Bus stop closed for duration of works. | 2025-09-22 | 2025-09-26
Almond | North West | HOPETOUN ROAD | At Shore Road | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2025-09-22 | 2025-10-01
Almond | North West | A90 | West of Dolphington | Transport Scotland - replacing digital message board | Overnight westbound lane closure | 2025-09-24 | 2025-09-25
Almond | North West | GOGAR STATION ROAD | At M8 bridge | Transport Scotland - CCTV camera works | Overnight temporary traffic lights | 2025-11-13 | 2025-11-14
City Centre | South East | NORTH BRIDGE |  | City of Edinburgh Council / Balfour Beatty - bridge refurbishment | East footway closed, pedestrian access via west footway. One traffic lane open in each direction (as of 21/04/23). | 2020-02-15 | Summer 2026
City Centre | South East | TARVIT STREET |  | Redevelopment of King's Theatre | Tarvit Street closed between Home Street and Drumdryan Street. Drumdryan Street northbound only. NCR 75 closed, cycle diversion signed via Valleyfield Street | 2023-02-14 | Late 2026
City Centre | South East | ROSE STREET | At South St David Street | Redevelopment of former Scottish Widows / Sainsbury's building | Road closed, delivery access via Hanover Street | 2025-06-01 | TBC
City Centre | South East | DEVON PLACE | Between West Coates and no. 4 | For Ogilvie Construction | Road closed to southbound traffic. | 2023-06-06 | March 2026
City Centre | South East | CALTON ROAD | At Leith Street | Crane lift Postponed due to gas main repairs at Abbeymount, new date TBA | Road closed | 2025-06-29 | 2025-06-29
City Centre | South East | MORRISON STREET | Between Morrison Link and Dewar Place | SGN - gas leak repairs Work finished and road reopened 19/09/25 | Road closed to eastbound traffic and Grove Street closed at Morrison Street. Southbound lane closure on Torphichen Place, Grove Street one-way order suspended to allow access via Fountainbridge. | 2025-08-22 | TBC
City Centre | South East | ROSE STREET SOUTH LANE | Section between Castle Street and Frederick Street | SGN - gas main disconnection | Road closed | 2025-09-08 | 2025-09-26
City Centre | South East | SHANDWICK PLACE |  | Siemens for Edinburgh Trams - track maintenance | 14/09/25 for 5 nights and 21/09/25 for 5 nights - road closed to westbound traffic 11pm - 6am each night. 11pm 26/09/25 - 5am 30/09/25 - road closed in both directions plus traffic management at Haymarket Yards to ensure safe access / egress during tram turnarounds. 30/08/25 for 3 nights - road closed to westbound traffic 11pm - 5am each night. | 2025-09-14 | 2025-10-02
City Centre | South East | CANDLEMAKER ROW |  | City of Edinburgh Council - carriageway resurfacing | Road closed 7pm - 6am for 5 weekday nights. | 2025-09-15 | 2025-09-20
City Centre | South East | QUEENSFERRY STREET LANE | At Queensferry Street | BT Circet - ducting installation | Road closed | 2025-09-15 | 2025-09-19
City Centre | South East | YORK PLACE | South footway between Broughton Street and Elder Street | Cityfibre - ducting installation | Section of CCWEL cycle path closed | 2025-09-15 | 19/09/25 22/09/25
City Centre | South East | ROYAL MILE AREA |  | Special event | Rolling road closure Johnston Terrace - Lawnmarket - High Street - Canongate - Horse Wynd - Queen's Drive to Broad Pavement car park, as required between 11am and 12.30pm. | 2025-09-20 | 2025-09-20
City Centre | South East | GILMORE PLACE |  | City of Edinburgh Council - carriageway resurfacing Dates and details TBC | Road closed in sections | 2025-09-22 | March 2026
City Centre | South East | LEOPOLD PLACE |  | City of Edinburgh Council - resurfacing | Daytime lane closures for gully and footway works. London Road citybound, Windsor Street and Blenheim Place all closed 7pm - 6am each night for 7 weekday nights. | 2025-09-22 | 2 weeks estimated
City Centre | South East | HAYMARKET TERRACE | At Haymarket Yards | BRM Utilities - manhole repair for Vodafone | 3-way temporary traffic lights 12.30am - 4.30am on Wednesday, westbound lane restriction thereafter. | 2025-09-24 | 2025-09-26
City Centre | South East | CALTON ROAD | Between Waverley station access and New Street | Scottish Water - ironwork repair | Road closed | 2025-09-28 | 2025-09-28
City Centre | South East | COWGATE | Between Blackfriars Street and St Mary's Street | Scottish Water - ironwork repair | Lane closures and contraflow. South Gray's Close closed | 2025-09-28 | 2025-09-28
City Centre | South East | GAYFIELD SQUARE | At Gayfield Street | SGN - gas main renewal | 2-way temporary traffic lights, Gayfield Street closed | 2025-09-29 | 2025-10-17
City Centre | South East | GEORGE IV BRIDGE | At Lawnmarket | For Sir Robert McAlpine | 3-way temporary traffic lights, Lawnmarket closed on east side | 2025-09-29 | 03/10/25 estimated
City Centre | South East | ROSE STREET SOUTH LANE | Section between South Charlotte Street and Castle Street | Clancy Docwra for Scottish Water | Road closed | 2025-09-29 | 2025-10-08
City Centre | South East | ALBYN PLACE |  | Clancy Docwra for Scottish Water | Eastbound inside lane closed | 2025-10-01 | 2025-10-08
City Centre | South East | MORRISON STREET | Between Semple Street and Gardner's Crescent | Tower crane installation | Road closed 12.30am Friday - 6pm Sunday | 2025-10-03 | 2025-10-05
City Centre | South East | LONDON ROAD | At Hillside Crescent | City of Edinburgh Council - pedestrian crossing upgrade | Lane closures, temporary traffic lights as required | 2025-10-06 | 2 weeks estimated
City Centre | South East | CORNWALL STREET | At Castle Terrace | Crane lift | Road closed | 2025-10-09 | 2025-10-09
City Centre | South East | ATHOLL CRESCENT LANE |  | Scottish Water - ironwork repair | Road closed | 2025-10-14 | 2025-10-14
City Centre | South East | THISTLE STREET | At Hanover Street (west side) | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-10-20 | 2025-10-24
City Centre | South East | WEST PORT | At Lady Lawson Street | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-10-26 | 2025-10-26
City Centre | South East | GRASSMARKET | At Victoria Street / West Bow | Scottish Water - ironwork repair | 2-way temporary traffic lights | 2025-10-27 | 7am 28/10/25
City Centre | South East | GEORGE IV BRIDGE |  | BRM Utilities - manhole repair for Vodafone | Southbound lane closure and temporary bus stop as signed | 2025-11-03 | 2025-11-07
City Centre | South East | VALLEYFIELD STREET |  | Scottish Water - service connection | Road closed except for cycles | 2025-12-01 | 2025-12-10
City Centre | South East | ROSEBERY CRESCENT | At Haymarket Terrace | Clancy Docwra for Scottish Water To be rescheduled for January 2026 | Road closed | 2025-12-15 | 2025-12-19
Colinton / Fairmilehead | South West | CAMUS AVENUE | At East Camus Place | Scottish Power - new supply | Temporary traffic lights (works ongoing, traffic lights removed 12/09/25) | 2025-09-08 | 2025-09-19
Colinton / Fairmilehead | South West | BONALY ROAD | Between West Carnethy Avenue and Munro Drive | Scottish Power - cable fault | No traffic management information provided but Lothian Buses service 10 diverted | 2025-09-18 | TBC
Colinton / Fairmilehead | South West | REDFORD ROAD | At The Gallolee | Telecoms company - trial holes | Off-peak 2-way temporary traffic lights | 2025-09-18 | 2025-09-19
Colinton / Fairmilehead | South West | SPYLAW BANK ROAD | At Pentland Road | Scottish Power - cable jointing | Temporary traffic lights | 2025-09-18 | 2025-09-24
Colinton / Fairmilehead | South West | OXGANGS ROAD | Between Swanston Avenue and Fairmile Avenue | BT - pole replacement | Off-peak temporary traffic lights | 2025-09-19 | 2025-09-19
Colinton / Fairmilehead | South West | COLINTON ROAD | Between Westgarth Avenue and Thorburn Road | Scottish Water - sewer repair | Lane closures and contraflow, no right turn into or out of St Cuthberts Court. 9.30am - midday approximately | 2025-09-21 | 2025-09-21
Colinton / Fairmilehead | South West | FROGSTON ROAD WEST | At Winton Drive | Energetics - cable installation | 3-way temporary traffic lights | 2025-09-22 | 2025-11-06
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Murrayfield | Scottish Water - major works to install combined sewer overflow (CSO) | Temporary traffic lights. Ormidale Terrace closed. Westbound bus stop closed, please use the next stop. | 2025-06-08 | November 2025
Corstorphine / Murrayfield | North West | CRAIGLEITH CRESCENT | Between Ravelston Dykes and Craigleith View | Clancy Docwra for Scottish Water | Temporary traffic lights | 2025-09-08 | 17/09/25 Ongoing
Corstorphine / Murrayfield | North West | BROOMHALL ROAD | At Broomhall Park | Film shoot | Broomhall Park closed 10am - 11pm; Broomhall Road closed 1pm - 11pm. | 2025-09-24 | 2025-09-24
Corstorphine / Murrayfield | North West | BALGREEN ROAD and SAUGHTON CRESCENT |  | City of Edinburgh Council - carriageway resurfacing and active travel improvements. Extents, traffic management and dates TBC. | Daytime lane closures and temporary traffic lights for preparatory and footway works, nightshift road closures for main resurfacing work. | 2025-10-20 | 9-12 weeks
Corstorphine / Murrayfield | North West | MURRAYFIELD AREA |  | Autumn Internationals - click cell for fixture list | Road closures before and after each match, details TBC. | 2025-11-01 | 2025-11-23
Corstorphine / Murrayfield | North West | ST JOHN'S ROAD | Opposite Station Road | Clancy Docwra - sewer repairs for Scottish Water Dates and details TBC | 2-way temporary traffic lights, Clermiston Road and Station Road closed | 2025-11-18 | 2025-11-27
Corstorphine / Murrayfield | North West | CORSTORPHINE AREA |  | Corstorphine Connections scheme - replacing some temporary measures with permanent materials. Dates and details TBC | Phased closures of Kirk Loan and Manse Road | 2026-01-05 | 2 weeks estimated
Corstorphine / Murrayfield | North West | ELLERSLY ROAD |  | City of Edinburgh Council - carriageway resurfacing | Road closed (excluding any affected 6 Nations dates) | 2026-01-12 | Up to 6 weeeks
Craigentinny/ Duddingston | North East | ABBEY LANE | At Abbeyhill | Graham Construction - development works | Road closed | 2024-01-09 | End of October 2025
Craigentinny/ Duddingston | North East | DUDDINGSTON LOW ROAD |  | Historic Environment Scotland - risk of rock falls | Road closed to motor vehicles. Road closed to all path users from Tuesday 18/03/25, pedestrian and cyclist diversion via Innocent railway path. Reopened to pedestrians and cyclists 07/08/25, cyclists please dismount through the barrier system at Samson's Ribs. | 2025-03-15 | Until further notice
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Clark Contracts - building development (demolition phase) Not started, new dates TBA. | Section of north footway closed. | 2025-09-01 | December 2027
Craigentinny/ Duddingston | North East | WILLOWBRAE ROAD | At Northfield Broadway / Lady Nairne | Telecoms company - trial holes | Temporary traffic lights | 2025-09-23 | 2025-09-23
Craigentinny/ Duddingston | North East | NANTWICH DRIVE | At Stapeley Avenue | Scottish Water - access to sewer overflow | Temporary traffic lights | 2025-09-29 | 2025-10-01
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Scottish Power - disconnection at development site | Section of north footway closed. Eastbound lane closure to accommodate temporary walkway, cycle lane closed. | 2025-10-13 | 2025-10-17
Craigentinny/ Duddingston | North East | SPRING GARDENS | Between Abbey Lane and Milton Street | Network Rail - vegetation clearance | Road closed for 1 night (times TBC) | 2025-11-03 | 2025-11-04
Drum Brae / Gyle | North West | SOUTH GYLE ROAD | At the rail bridge | Network Rail - renewing rail bridge | Road closed. Access to the station car park via South Gyle Broadway - Gogarloch Road. | 2025-07-28 | April 2026
Drum Brae / Gyle | North West | LADYWELL AVENUE | Between Kirklands and Broomhall Crescent | Network Rail - renewing rail bridge | Road closed | 2025-08-21 | August 2026
Drum Brae / Gyle | North West | GLASGOW ROAD | At the rail bridge between Gogar and Maybury junctions | Network Rail - adjusting parapets as part of electrification project | Lane closures 8pm - 7am each night | 2025-09-13 | 2025-10-24
Drum Brae / Gyle | North West | NORTH GYLE ROAD | At Glasgow Road | Clancy Docwra - emergency sewer repairs for Scottish Water | Road closed and section of citybound bus lane closed on Glasgow Road | 2025-09-16 | TBC
Drum Brae / Gyle | North West | GLASGOW ROAD | At Drum Brae roundabout | BT - manhole repairs at north west corner of roundabout | 4-way temporary traffic lights 7pm - 7am | 2025-09-22 | 2025-09-23
Drum Brae / Gyle | North West | GLASGOW ROAD | At North Gyle Grove | Scottish Water - manhole repair | Lane closures and contraflow on Glasgow Road, North Gyle Grove closed | 2025-09-30 | 7am 01/10/25
Drum Brae / Gyle | North West | DRUM BRAE SOUTH | At Drum Brae Avenue | Telecoms company - pole and cabinet renewal | Off-peak 3-way temporary traffic lights | 2025-11-03 | 2025-11-07
Drum Brae / Gyle | North West | MEADOW PLACE ROAD | At the rail bridge | Network Rail | Temporary traffic lights, cycle lane closed | 2026-01-16 | 1 week estimated
Forth | North West | CRAIGHALL ROAD | Between Craighall Avenue and Grandville | Refurbishment of Trinity Academy | Road closed | 2025-06-30 | May 2028
Forth | North West | ROYSTON TERRACE | At Inverleith Row | Clancy Docwra for Scottish Water - lead renewal | Road closed to through traffic. Existing one-way order rescinded for duration of works. | 2025-09-16 | 2025-09-20
Forth | North West | FERRY ROAD | At Granton Road | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-09-21 | 7am 22/09/25
Forth | North West | CREWE ROAD NORTH | At Boswall Parkway | Telecoms company - pole and cabinet renewal | Off-peak 3-way temporary traffic lights. Crane lift and bus diversion (service 19) on first day to swap poles, working space reduced thereafter. | 2025-09-22 | 2025-09-26
Forth | North West | BOSWALL DRIVE | Between Boswall Crescent and Boswall Parkway | Scottish Water - lead renewal | Road closed | 2025-09-24 | 2025-09-29
Forth | North West | GRANTON AREA |  | March | Rolling road closure Waterfront Broadway - West Granton Road - Crewe Road North to Crewe Toll, as required between 1pm and 3pm | 2025-09-27 | 2025-09-27
Forth | North West | BOSWALL PARKWAY | Between Pilton Avenue and Boswall Terrace | Clancy Docwra for Scottish Water - lead renewal | Temporary traffic lights | 2025-09-29 | 2025-10-08
Forth | North West | BANGHOLM ROAD |  | Clancy Docwra for Scottish Water - sewer cleaning | Road closed to through traffic. | 2025-10-20 | 2025-10-20
Fountainbridge/ Craiglockhart | South West | HARRISON ROAD | At the dog-leg bend where it crosses the cycle path and at the canal bridge | City of Edinburgh Council - bridge repairs | Road closed. Topside footway closures as signed. Road bridge expected to be renewed by end of 2025. Trial holes ongoing at canal bridge. | 2025-02-18 | Ongoing
Fountainbridge/ Craiglockhart | South West | LANARK ROAD | At Water of Leith visitor centre | Scottish Power - mains disconnection | Westbound inside lane closed, bus stop closed | 2025-09-16 | 2025-09-26
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Moat Terrace | Scottish Power / Excalon - cable jointing | Temporary traffic lights | 2025-09-17 | 4-5 weeks
Fountainbridge/ Craiglockhart | South West | DUNDEE STREET | At Viewforth | Scottish Power - cable fault | Temporary traffic lights | 2025-09-19 | TBC
Fountainbridge/ Craiglockhart | South West | LANARK ROAD | At Inglis Green Road | City of Edinburgh Council - line marking | 3-way temporary traffic lights 5am - 11am | 2025-09-20 | 2025-09-20
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At the rail bridge | Network Rail - bridge maintenance | Temporary traffic lights 7pm - 7am | 2025-09-20 | 2025-09-21
Fountainbridge/ Craiglockhart | South West | CRAIGLOCKHART CROSSROADS |  | Scottish Water - ironwork repair | 4-way temporary traffic lights 8am - 7pm | 2025-09-21 | 2025-09-21
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | Between Ford's Road and Balgreen Road | Mackenzie Construction for Scottish Water - installation of new water meter | Outside lane closed in both directions. Bus stops closed on both sides. | 2025-09-22 | 2025-09-24
Fountainbridge/ Craiglockhart | South West | LANARK ROAD | Between Redhall Bank Road and Inglis Green Rpad | Amey - removing diseased trees | Citybound lane closure and north footway closed, 9.30am - 3.30pm eachd ay | 2025-09-22 | 2025-09-24
Fountainbridge/ Craiglockhart | South West | ROBB'S LOAN | At Eltringham Gardens | Clancy Docwra - sewer works for Scottish Water | 3-way temporary traffic lights | 2025-09-22 | 2025-09-24
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Balgreen Road | Scottish Power - trial holes | 4-way temporary traffic lights 7pm - 7am | 2025-09-25 | 2025-09-26
Fountainbridge/ Craiglockhart | South West | CRAIGLOCKHART TERRACE | At the dog-leg at no.11 | Clancy Docwra for Scottish Water | 4-way temporary traffic lights | 2025-09-29 | 2025-10-06
Fountainbridge/ Craiglockhart | South West | HUTCHISON PLACE | At Slateford Road | Scottish Water - ironwork repair | Road closed | 2025-09-29 | 2025-09-29
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Coxfield | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-09-29 | 2025-09-29
Fountainbridge/ Craiglockhart | South West | ALLAN PARK ROAD |  | Clancy Docwra for Scottish Water - sewer repairs | Temporary traffic lights | 2025-10-13 | 7-10 days
Fountainbridge/ Craiglockhart | South West | RITCHIE PLACE | At Watson Crescent | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-11-05 | 2025-11-14
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Chesser Avenue | Scottish Power - trial holes Dates TBC | 3-way temporary traffic lights 7pm - 7am | 2025-12-09 | 2025-12-10
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | Between Ford's Road and Balgreen Road | Scottish Water - major works to install combined sewer overflow (CSO) | Road closed and section of north footway closed. | 2026-01-04 | 16 weeks
Inverleith | North West | TELFORD PLACE | At Telford Road | SGN - gas main renewal | Road closed | 2025-08-18 | 2025-09-30
Inverleith | North West | RAEBURN PLACE | At Raeburn Street | SGN - gas main alteration | 2-way temporary traffic lights | 2025-09-08 | 19/09/25 estimated
Inverleith | North West | CANONMILLS | At Inverleith Row / Brandon Terrace | Vodafone - proving cable ducts Work postponed | 3-way temporary traffic lights, 8pm - 6am | 2025-09-10 | 2025-09-11
Inverleith | North West | INVERLEITH ROW | At Goldenacre Terrace | Openreach - manhole reconstruction | Temporary traffic lights | 2025-09-22 | 2025-09-28
Inverleith | North West | HAMILTON PLACE | At Stockbridge library | Clancy Docwra - sewer cleaning | Temporary traffic lights | 2025-10-09 | 2025-10-09
Leith | North East | LINDSAY ROAD BRIDGE | Pedestrian / cycle bridge between Nicholfield and Lindsay Road main carriageway | City of Edinburgh Council - public safety measure | Bridge closed, pedestrian and cycle diversion as signed. Hawthornvale Path beneath remains open | 2021-12-15 | Until further notice
Leith | North East | HENDERSON STREET | Between Shore and Parliament Street | City of Edinburgh Council - construction of segregated cycle lane | Lane closures, parking restrictions, temporary traffic lights if required. Currently temporary traffic lights at northern end and Parliament Street closed at Henderson Street. | 2024-12-03 | Summer 2025
Leith | North East | NEWHAVEN AREA |  | Cruise liner visits. Click cell for full schedule | Parking restrictions as signed on Pier Place and Newhaven Place for each visit | 2025-04-02 | 2025-09-27
Leith | North East | SALAMANDER STREET | At Salamander Yards | BT Circet - ducting installation | 4-way temporary traffic lights | 2025-10-01 | 2025-10-06
Leith | North East | SALAMANDER STREET | Between Assembly Street and Elbe Street | Scottish Water - ironwork repairs (x2) | 2-way temporary traffic lights | 2025-10-14 | 2025-10-15
Leith | North East | BONNINGTON ROAD | At Great Junction Street | Scottish Water - ironwork repair | 4-way temporary traffic lights 7pm - 7am | 2025-10-24 | 2025-10-25
Leith Walk | North East | ALBION ROAD | Between Easter Road and Albion Place | Scottish Water - collapsed manhole | Road closed | 2025-08-07 | TBC
Leith Walk | North East | ARTHUR STREET | Between Pilrig Street and the corner at no.18 | Scottish Water - mains disconnection | Road closed to westbound traffic, parking suspended on both sides. | 2025-09-22 | 2025-09-26
Leith Walk | North East | EASTER ROAD | Between Sunnyside and Drum Terrace | Clancy Docwra for Scottish Water - lead renewal | 4-way temporary traffic lights | 2025-10-05 | 2025-10-07
Leith Walk | North East | DRYDEN STREET | At Pilrig Street | Scottish Water - mains disconnection | Road closed | 2025-10-06 | 2025-10-08
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Livingston, kick-off 3pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-10-18 | 2025-10-18
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | BT Morrison - fibre installation To be rescheduled | Off-peak 3-way temporary traffic lights | 2025-08-18 | 2025-08-18
Liberton / Gilmerton | South East | LIBERTON ROAD | At Gilmerton Road | Locktel for Cityfibre - proving / clearing cable ducts Work postponed | 3-way temporary traffic lights 9.30am - 5pm each day | 2025-09-10 | 2025-09-11
Liberton / Gilmerton | South East | SOUTHHOUSE BROADWAY | At Captain's Road | Scottish Power - cable fault | Road closed | 2025-09-11 | TBC
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | Telecoms company - pole replacement (preparatory works) | 3-way temporary traffic lights | 2025-09-20 | 2025-09-24
Liberton / Gilmerton | South East | KAIMES CROSSROADS |  | Openreach - access to carriageway manholes | 4-way temporary traffic lights 9.30am - 3.30pm | 2025-09-21 | 2025-09-21
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | BT Morrison - fibre installation Work postponed | 3-way temporary traffic lights 7pm - 6am | 2025-09-22 | 2025-09-23
Liberton / Gilmerton | South East | LASSWADE ROAD | At Gracemount high school | BT Morrison - fibre installation | 2-way temporary traffic lights at the school and separate lane closures between the school and Captain's Road | 2025-09-27 | 2025-09-28
Liberton / Gilmerton | South East | GILMERTON CROSSROADS |  | Scottish Water - manhole repair | 4-way temporary traffic lights | 2025-09-28 | 2025-09-28
Liberton / Gilmerton | South East | LIBERTON BRAE | Between Kirk Brae and Orchardhead Road | SGN - gas main repairs | Lane closures and contraflow, temporary stop for southbound buses | 2025-09-30 | 2 weeks estimated
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | Telecoms company - pole replacement (crane lift) | 3-way temporary traffic lights | 2025-10-04 | 2025-10-05
Liberton / Gilmerton | South East | LIBERTON BRAE |  | Scottish Water - manhole repair | 2-way temporary traffic lights, Wolrige Road and Hawkhead Crescent closed | 2025-10-22 | 7am 23/10/25
Midlothian |  | A7 at ESKBANK |  | Midlothian Council - carriageway resurfacing and footway construction | Lane closures. Lasswade Road closed between A7 and Captains Gardens. Lasswade Road reopened Monday 18/08/25, lane restrictions thereafter for phase 2. | 2025-07-07 | 2025-10-10
Midlothian |  | MILLERHILL ROAD | Between Shawfair Spine Road and Newton Village | Carriageway upgrade / footway widening / traffic signal installation / utility diversion works / district heating system installation | Temporary traffic lights | 2025-08-11 | April 2026
Midlothian |  | A701 STRAITON ROAD | B702 Loanhead Road to Sainsbury’s roundabout | Midlothian Council - carriageway resurfacing | Road closed to southbound traffic 10pm - 6am for 10 nights | 2025-09-15 | 2025-09-24
Morningside | South East | MARCHMONT ROAD |  | Scottish Power - cable installations Expected to finish over weekend of 20-21/09/25 | Phase 1 - 3-way temporary traffic lights at Beaufort Road, Marchmont Road closed to southbound traffic; Phase 2 - 3-way temporary traffic lights at Marchmont Crescent, no exit from Spottiswoode Road. | 2025-08-04 | 26/09/25 estimated
Morningside | South East | BELHAVEN TERRACE |  | Virgin Media - cable and ducting installation | Left turn lane into Morningside Road closed | 2025-09-15 | 2025-09-19
Morningside | South East | GRANVILLE PLACE | At Merchiston Park | Clancy Docwra - emergency sewer repairs for Scottish Water | 4-way temporary traffic lights | 2025-09-16 | TBC
Morningside | South East | NILE GROVE |  | Community event | Road closed 2pm - 5pm | 2025-09-21 | 2025-09-21
Morningside | South East | NILE GROVE |  | BT - pole replacement | Road closed to through traffic at nos. 9-23 | 2025-09-23 | 2025-09-24
Morningside | South East | GILMORE PLACE | At Viewforth | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-10-05 | 2025-10-05
Morningside | South East | BRUNTSFIELD PLACE | Between Holy Corner and Merchiston Place | Clancy Docwra for Scottish Water - lead renewal | Narrow lane citybound with contraflow | 2025-10-12 | 2025-10-14
Morningside | South East | ROSENEATH STREET |  | Clancy Docwra for Scottish Water - sewer survey | Road closed | 2025-11-04 | 2025-11-04
Morningside | South East | BRUNTSFIELD PLACE | At Viewforth | Clancy Docwra for Scottish Water - valve repairs | 2-way temporary traffic lights, Viewforth closed | 2025-12-07 | 2025-12-16
Morningside | South East | MONTPELIER PARK | Between Montpelier and Bruntsfield Place | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-12-08 | 2025-12-17
Pentland Hills | South West | KIRKGATE | At Currie Community Church | Scottish Water - repairs to burst pipe | Road closed | 2025-09-17 | TBC
Pentland Hills | South West | RICCARTON MAINS ROAD | Between Corslet Road and the garden centre | City of Edinburgh Council - kerb works | Temporary traffic lights | 2025-09-21 | 2025-09-21
Pentland Hills | South West | LANARK ROAD WEST | Between Riccarton Mains Road and Bryce Road | Scottish Water - lead renewal | Temporary traffic lights | 2025-09-22 | 2025-09-24
Pentland Hills | South West | MAIN STREET, RATHO | At Dalmahoy Road | Scottish Water - manhole repair | 4-way temporary traffic lights | 2025-09-22 | 2025-09-22
Pentland Hills | South West | RICCARTON MAINS ROAD | Between Corslet Road and 280m north of the rail bridge | City of Edinburgh Council - carriageway resurfacing | Road closed | 2025-10-06 | Up to 8 weeks
Pentland Hills | South West | LANARK ROAD | At City Bypass bridge | Transport Scotland - CCTV camera works | Overnight temporary traffic lights | 2025-11-13 | 2025-11-14
Pentland Hills | South West | CURRIEHILL ROAD | Between Pentland View and Forthview Crescent | Scottish Water - ironwork repair | Road closed 9.30am - 9pm | 2025-11-16 | 2025-11-16
Portobello/ Craigmillar | North East | BRUNSTANE ROAD | Between Milton Road East and Argyle Crescent / Dalkeith Street | City of Edinburgh Council - Low Traffic Neighbourhood trial Click cell for more details | Road closed to through traffic, except cycles | 2022-02-15 | Ongoing
Portobello/ Craigmillar | North East | ABERCORN TERRACE / PORTOBELLO HIGH STREET |  | GTC Pipelines - utility connections for housing development | Rolling programme with lane closures, temporary traffic lights and side-road closures as required. As at 19/09/25, citybound lane closure at King's Road junction pulling cables. Temporary traffic lights at Adelphi Grove on 22/09.25. Line marking 23 and 24/09/25, traffic will be held for 1-2minutes as required. Estimated finish date is 24/09/25. | 2025-05-27 | October 2025 estimated
Portobello/ Craigmillar | North East | GREENDYKES ROAD | At Greendykes Drive | Drainage installation | Road closed, diversion via Tudsbury Avenue | 2025-08-04 | 2025-09-30
Portobello/ Craigmillar | North East | WHITEHILL ROAD | Outside the Honda garage | Installation of new sewer services | Temporary traffic lights | 2025-09-15 | 2025-09-23
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | Between Benhar Road and the rail bridge | Scottish Water - lead renewal Work postponed, new dates TBA | 2-way temporary traffic lights, bus stops closed on both sides. | 2025-09-20 | 8am 22/09/25 estimated
Portobello/ Craigmillar | North East | MUSSELBURGH ROAD | At Coillesdene Terrace | Clancy Docwra for Scottish Water - lead renewal | 3-way temporary traffic lights | 2025-12-01 | 2025-12-10
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Flint Terrace | Scottish Water - manhole repair | 3-way temporary traffic lights | 2025-12-04 | 2025-12-04
Portobello/ Craigmillar | North East | BRIGHTON PLACE | At the rail bridge | Network Rail - bridge repairs | Road closed 10pm - 6am | 2025-12-04 | 2025-12-05
Portobello/ Craigmillar | North East | DUDDINGSTON ROAD | At Mountcastle Drive South | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-12-07 | 7am 08/12/25
Sighthill/Gorgie | South West | GORGIE ROAD | At Springwell House | Scottish Water - ironwork repair Work postponed | Temporary traffic lights 7pm - 7am | 2025-09-12 | 2025-09-13
Sighthill/Gorgie | South West | CALDER ROAD SERVICE ROAD | At Parkhead Terrace | Telecoms company - mast and cabinet renewal | 3-way temporary traffic lights for preparatory works (15 - 19/09/25). Westbound Calder Road bus stops and layby closed from 7pm on night of 28/09/25 for crane lift to install new pole. | 2025-09-15 | 2025-09-29
Sighthill/Gorgie | South West | GORGIE ROAD | At Wardlaw Place | Cityfibre - clearing blocked cable ducts | 2-way temporary traffic lights, Wheatfield Street and Wardlaw Place closed | 2025-09-22 | 2025-09-24
Sighthill/Gorgie | South West | PANSY WALK | Between Baird Drive and Balgreen community garden (just south of the rail / tram bridge) | Scottish Water / CWA - sewer upgrade | Path closed, diversion signed via footbridge and Westfield Avenue | 2025-09-22 | March 2026
Sighthill/Gorgie | South West | DALRY ROAD | At Orwell Terrace | Cityfibre - manhole repair | Temporary traffic lights, Orwell Terrace closed | 2025-09-25 | 2025-09-26
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Falkirk, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-09-27 | 2025-09-27
Sighthill/Gorgie | South West | GORGIE ROAD | At Wardlaw Place | Clancy Docwra for Scottish Water - sewer cleaning | 2-way temporary traffic lights, Wheatfield Street and Wardlaw Place closed | 2025-09-29 | 2025-10-03
Sighthill/Gorgie | South West | DALRY ROAD | At Caledonian Place | Scottish Water - ironwork repair | 3-way temporary traffic lights, West Park Place closed | 2025-10-02 | 2025-10-02
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Hibs, kick-off 5.45pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-10-04 | 2025-10-04
Sighthill/Gorgie | South West | BALGREEN ROAD | At Stevenson Drive | Scottish Water - meter exchange | 3-way temporary traffic lights | 2025-10-15 | 2025-10-23
Sighthill/Gorgie | South West | GORGIE ROAD | At Robertson Avenue | Scottish Water - ironwork repair | 4-way temporary traffic lights 9.30am - 11.30am | 2025-11-30 | 2025-11-30
Sighthill/Gorgie | South West | GORGIE ROAD | At Stenhouse Drive / Stenhouse Mill Lane | Scottish Power - trial holes Dates TBC | 4-way temporary traffic lights 7pm - 7am | 2025-12-08 | 2025-12-09
Sighthill/Gorgie | South West | BROOMHOUSE CRESCENT | Immediately west of Broomhouse Row | Clancy Docwra for Scottish Water - sewer repairs | Road closed | 2025-12-15 | 2025-12-22
Southside / Newington | South East | SOUTH CLERK STREET | Bernard Terrace to Lutton Place | Clancy Docwra for Scottish Water - sewer repairs | Southbound lane closure | 2025-08-13 | 26/08/25 estimated Ongoing
Southside / Newington | South East | WHITEHOUSE TERRACE / NEWBATTLE TERRACE | Either side of Whitehouse Loan junction | City of Edinburgh Council - footway resurfacing | Lane closures and parking restrictions | 2025-09-15 | 4-5 weeks estimated
Southside / Newington | South East | GRANGE LOAN | Between Kilgraston Road and Blackford Avenue | SGN - gas leak repairs | No traffic management information provided but Lothian Buses service 9 diverted | 2025-09-17 | TBC
Southside / Newington | South East | HOLYROOD PARK ROAD | At East Parkside | Scottish Water - hydrant repairs | 3-way temporary traffic lights | 2025-09-19 | TBC
Southside / Newington | South East | NICOLSON STREET | Between West Nicolson Street and Nicolson Square | SGN - new gas service | Citybound lane closure, temporary bus stop for northbound services | 2025-09-22 | 2025-10-03
Southside / Newington | South East | FOUNTAINHALL ROAD | Between Findhorn Place and Newington library | Clancy Docwra for Scottish Water - sewer cleaning | Road closed | 2025-09-25 | 2025-09-25
Southside / Newington | South East | GEORGE SQUARE |  | University of Edinburgh open day | North and east legs and Crichton Street closed 8am - 4.30pm | 2025-10-04 | 2025-10-04
Southside / Newington | South East | MINTO STREET | At Blacket Place | Clancy Docwra for Scottish Water - valve repairs | 3-way temporary traffic lights, Duncan Street closed | 2025-11-10 | 2025-11-19
Southside / Newington | South East | MINTO STREET | At Salisbury Place | Scottish Water - manhole repair | 4-way temporary traffic lights | 2026-01-11 | 7am 12/01/26
Trunk road network |  | M8 | Between J3A and 4 | BEAR Scotland - B792 bridge refurbishment | Contraflow and 40mph speed restriction | 2025-05-18 | 4 months estimated
Trunk road network |  | FORTH ROAD BRIDGE |  | BEAR Scotland - bridge maintenance | Road closed 9.30pm - 4am for 2 nights, then single lane closures until October. | 2025-05-22 | October 2025
Trunk road network |  | A1 | Between Old Craighall and Wallyford | BEAR Scotland - carriageway resurfacing and bridge joint repairs | Series of overnight carriageway closures - click cell for full details 1 additional closure of the A1 southbound from Old Craighall to Wallyford on the night of Sunday 21/09/25, 8.30pm - 6am | 2025-08-21 | 19/09/25 22/09/25
Trunk road network |  | M9 | Between J1 and J10 | BEAR Scotland - maintenance | Series of overnight lane and carriageway closures - click cell for full details | 2025-09-01 | 2025-10-15
Trunk road network |  | M8 | At J2 | BEAR Scotland - street lighting renewal | Eastbound on-slip closed 8pm - 6am for 6 nights | 2025-09-15 | 2025-09-21
Trunk road network |  | A720 | Lothianburn to Dreghorn | BEAR Scotland - carriageway resurfacing Work finished, no further closures required | Westbound on-slip closed for 6 weekday nights. Main carriageway closed to westbound traffic 8.30pm - 6am for 5 weekday nights from 16/09/25. | 2025-09-15 | 2025-09-23
Trunk road network |  | A702 / OLD PENTLAND ROAD | Between Roseneath and Snowsports centre | Scottish Power - new supply | Overnight temporary traffic lights | 2025-09-22 | 2025-10-24
Trunk road network |  | M8 | Between J2 and J3A | BEAR Scotland - carriageway resurfacing | Eastbound on-slip at J3 closed 8.30pm - 6am for 4 nights. Eastbound carriageway closed J4 - J2, 8.30pm - 6am from 29/09/25 for 15 weekday nights. | 2025-09-23 | 2025-10-18
Trunk road network |  | FORTH ROAD BRIDGE |  | BEAR Scotland - removal of high-level access gantries | Road closed 9.30pm - 6am for 2 nights (southbound on 01/10/25 and northbound on 02/10/25). Pedestrian and cycle access maintained. | 2025-10-01 | 2025-10-03
Various Wards | South East South West North West | CENTRAL and WESTERN EDINBURGH | Royal Mile, Cowgate, Grassmarket, Lothian Road, West Approach Road | Men's and Women's 10k races | Multiple road closures 5am - 1.30pm approximately. Click cell for full details | 2025-09-21 | 2025-09-21
Roadworks & events report
Effective from 19 September 2025