## General Road Works
Links to further information
| Traffic Scotland - realtime information on trunk roads including Edinburgh City Bypass |  |  |  | Details of Ward and Locality boundaries
SE Scotland trunk roads maintenance by BEAR Scotland
Key
| Transport for Edinburgh - Lothian Buses and Edinburgh Trams |  |  |  | New or updated information in this version
Underlined entries contain links to maps or further information
Edinburgh Travelling Safely measures and Low Traffic Neighbourhoods
| Our social media channels: |  | X (formerly Twitter) | Facebook | Threads
Excel - use the drop-down arrows to sort by any column. PDF - use CTRL + F to search for any keyword. |  |  |  | NB this is not intended to be a list of all the roadworks in Edinburgh. Please refer to the Scottish Roadworks Register website for basic information on all registered roadworks
Ward | Locality | Street | Location | Contractor / works description | Measures in place | Start | Finish
Almond | North West | MAYBURY ROAD | At Craigs Road | Construction of signalised junction | Craigs Road closed on west side of Maybury Road from 06/05/25; Phase 2 - various lane closures and contraflow arrangements from 26/05/25. Craigs Road closed on east side from 22/09/25. Phase 3 - 2-way traffic on northbound carriageway , start date TBC; Phase 4 - temporary traffic lights, estimated start 10/12/25. | 2025-05-06 | 6 months estimated
Almond | North West | QUEENSFERRY AREA |  | Cruise liner visits. Click cell for full schedule | For each visit: prohibition of motor vehicles on Bankhead Road south of Station Road, parking restrictions as signed on Hawes car park, Newhalls Road and Hawes Brae | 2025-05-07 | 2025-10-09
Almond | North West | STIRLING ROAD | At the M9 bridge | City of Edinburgh Council - carriageway resurfacing | Temporary traffic lights | 2025-09-15 | 8-10 weeks estimated
Almond | North West | A89 | Between Broxburn and Newbridge | City of Edinburgh Council - ground investigation surveys | Off-peak lane closures, temporary traffic lights if required | 2025-10-01 | 2025-10-14
Almond | North West | SILVERKNOWES ROAD | Between Silverknowes Parkway and Marine Drive | City of Edinburgh Council - carriageway surfacing and road marking Work extended due to additional work identified | Road closed. Click cell for details of service 29 diversion. | 2025-10-01 | 05/10/25 26/10/25
Almond | North West | LENNYMUIR | At the rail bridge | Network Rail - adjusting parapets as part of electrification project | Overnight temporary traffic lights | 2025-10-04 | 2025-11-14
Almond | North West | KIRKLISTON ROAD, QUEENSFERRY | At Rosebery Avenue | Scottish Water - mains connection | 3-way temporary traffic lights | 2025-10-14 | 5 days estimated
Almond | North West | GOGAR STATION ROAD | At M8 bridge | Transport Scotland - CCTV camera works | Overnight temporary traffic lights | 2025-11-13 | 2025-11-14
Almond | North West | MAIN STREET, DAVIDSON'S MAINS | At Cramond Road South / Quality Street | Power and water main connections | 3-way temporary traffic lights, East Barnton Gardens closed | 2025-11-17 | 6-8 weeks
Almond | North West | CRAMOND ROAD SOUTH | Between Barnton Avenue and Quality Street, to include Main Street mini-roundabout | City of Edinburgh Council - carriageway resurfacing | Phase 1 - roundabout and all approaches closed; Phase 2 - Cramond Road South closed. | 2026-02-16 | 3 weeks estimated
City Centre | South East | NORTH BRIDGE |  | City of Edinburgh Council / Balfour Beatty - bridge refurbishment | East footway closed, pedestrian access via west footway. One traffic lane open in each direction (as of 21/04/23). | 2020-02-15 | Summer 2026
City Centre | South East | TARVIT STREET |  | Redevelopment of King's Theatre | Tarvit Street closed between Home Street and Drumdryan Street. Drumdryan Street northbound only. NCR 75 closed, cycle diversion signed via Valleyfield Street | 2023-02-14 | Late 2026
City Centre | South East | ROSE STREET | At South St David Street | Redevelopment of former Scottish Widows / Sainsbury's building | Road closed, delivery access via Hanover Street | 2025-06-01 | TBC
City Centre | South East | DEVON PLACE | Between West Coates and no. 4 | For Ogilvie Construction | Road closed to southbound traffic. | 2023-06-06 | March 2026
City Centre | South East | CALTON ROAD | At Leith Street | Crane lift Postponed due to gas main repairs at Abbeymount, new date TBA | Road closed | 2025-06-29 | 2025-06-29
City Centre | South East | GILMORE PLACE |  | City of Edinburgh Council - carriageway resurfacing Dates and details TBC | Road closed in sections | 2025-09-22 | March 2026
City Centre | South East | ROSE STREET SOUTH LANE | Section between South Charlotte Street and Castle Street | Clancy Docwra for Scottish Water | Road closed | 2025-09-29 | 2025-10-08
City Centre | South East | NORTH CHARLOTTE STREET | At Young Street | Scottish Power - cable fault | Traffic management TBC but expect some road and / or footway occupation | 2025-10-01 | 14/10/25 estimated
City Centre | South East | SOUTH WEST CUMBERLAND STREET LANE | Eastern end, at Cumberland Street | Clancy Docwra - emergency repairs for Scottish Water | Road closed | 2025-10-01 | 10/10/25 estimated
City Centre | South East | MORRISON STREET | Between Semple Street and Gardner's Crescent | Tower crane installation Postponed due to forecast high winds | Road closed 12.30am Friday - 6pm Sunday | 2025-10-03 | 2025-10-05
City Centre | South East | LONDON ROAD | At Hillside Crescent | City of Edinburgh Council - pedestrian crossing upgrade | Lane closures, temporary traffic lights as required | 2025-10-06 | 2 weeks estimated
City Centre | South East | QUEEN STREET | At Frederick Street | Cityfibre - cable and ducting installation | Lane closures on all approaches. No left turn from Frederick Street into westbound Queen Street | 2025-10-06 | 2025-10-10
City Centre | South East | THISTLE STREET SOUTH WEST LANE |  | Scottish Water - ironwork repair | Road closed | 2025-10-06 | 8am 08/10/25
City Centre | South East | GAYFIELD SQUARE | At Gayfield Street | SGN - gas main renewal | 2-way temporary traffic lights, Gayfield Street closed | 2025-10-07 | 2025-11-07
City Centre | South East | LOTHIAN ROAD | At Morrison Street / Bread Street | Scottish Power - cable connections to substation at Chuckie Pend | Various lane closures as work progresses | 2025-10-08 | 2025-10-22
City Centre | South East | THE MOUND | At Princes Street | Scottish Water - ironwork repair | Road closed from 12:15am - 4:30am | 2025-10-10 | 2025-10-10
City Centre | South East | QUEEN STREET | At North Castle Street | Scottish Water - ironwork repair | 3-way temporary traffic lights 7pm - 7am | 2025-10-10 | 2025-10-11
City Centre | South East | ST ANDREW SQUARE | West side, between George Street and Rose Street | Crane lift | Road closed 9pm - 5am | 2025-10-12 | 2025-10-13
City Centre | South East | ATHOLL CRESCENT LANE |  | Scottish Water - ironwork repair | Road closed | 2025-10-14 | 2025-10-14
City Centre | South East | CENTRAL EDINBURGH |  | Parade | Rolling road closure The Mound - Bank Street - Lawnmarket - High Street - Canongate - New Street to Sibbald Walk. As required betweeen 1pm and 3pm. | 2025-10-18 | 2025-10-18
City Centre | South East | QUEEN STREET | At North Charlotte Street | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-10-19 | 7am 20/10/25
City Centre | South East | CORNWALL STREET | At Castle Terrace | Crane lift | Road closed | 2025-10-20 | 2025-10-20
City Centre | South East | THISTLE STREET | At Hanover Street (west side) | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-10-20 | 2025-10-24
City Centre | South East | LAURISTON PLACE | Outside George Heriot's | Crane access for roof repairs | 3-way temporary traffic lights 7pm - 7am | 2025-10-23 | 2025-10-24
City Centre | South East | FOUNTAINBRIDGE | At Ponton Street | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-10-24 | 7am 25/10/25
City Centre | South East | THE MOUND | Market Street to Princes Street | Scottish Water - ironwork repair | Road closed to northbound traffic 12.15am - 4.30am | 2025-10-24 | 2025-10-24
City Centre | South East | CENTRAL EDINBURGH | Horse Wynd - Royal Mile - George IV Bridge - Middle Meadow Walk | Parade | Horse Wynd and Queen's Drive at Horse Wynd closed 10am - 11.30am. Royal Mile, New Street, Bank Street, George IV Bridge, Forrest Road, Teviot Place and Laurison Place closed 1030am - 2pm | 2025-10-25 | 2025-10-25
City Centre | South East | THE MOUND | At Princes Street | Scottish Water - ironwork repair | Road closed from 00:15- 04:30am | 2025-10-24 | 2025-10-24
City Centre | South East | WEST PORT | At Lady Lawson Street | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-10-26 | 2025-10-26
City Centre | South East | GRASSMARKET | At Victoria Street / West Bow | Scottish Water - ironwork repair | 2-way temporary traffic lights | 2025-10-27 | 7am 28/10/25
City Centre | South East | LOTHIAN ROAD | Between Morrison Street and Fountainbridge | Scottish Water - ironwork repair | Multiple lane closures and contraflow arrangement, 7pm - 7am | 2025-10-30 | 2025-10-31
City Centre | South East | COATES PLACE |  | Bilfinger for Edinburgh Trams | Road closed to westbound traffic midnight - 4.30am, diversion via Torphichen Place - Morrison Street | 2025-10-31 | 2025-10-31
City Centre | South East | GEORGE IV BRIDGE |  | BRM Utilities - manhole repair for Vodafone | Southbound lane closure and temporary bus stop as signed | 2025-11-03 | 2025-11-07
City Centre | South East | ALBYN PLACE |  | Clancy Docwra for Scottish Water | Eastbound inside lane closed | 2025-11-30 | 2025-12-04
City Centre | South East | VALLEYFIELD STREET |  | Scottish Water - service connection | Road closed except for cycles | 2025-12-01 | 2025-12-10
City Centre | South East | ROSEBERY CRESCENT | At Haymarket Terrace | Clancy Docwra for Scottish Water To be rescheduled for January 2026 | Road closed | 2025-12-15 | 2025-12-19
Colinton / Fairmilehead | South West | FROGSTON ROAD WEST | At Winton Drive | Energetics - cable installation | 3-way temporary traffic lights | 2025-09-22 | 2025-11-06
Colinton / Fairmilehead | South West | OXGANGS AVENUE | Between Oxgangs Green and Oxgangs Crescent (north leg) | Scottish Water - ironwork repair | Temporary traffic lights | 2025-10-16 | 7am 17/10/25
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Murrayfield | Scottish Water - major works to install combined sewer overflow (CSO) | Temporary traffic lights. Ormidale Terrace closed. Westbound bus stop closed, please use the next stop. | 2025-06-08 | November 2025
Corstorphine / Murrayfield | North West | BALGREEN ROAD and SAUGHTON CRESCENT |  | City of Edinburgh Council - carriageway resurfacing and active travel improvements. Extents, traffic management and dates TBC. | Daytime lane closures and temporary traffic lights for preparatory and footway works, nightshift road closures for main resurfacing work. | 2025-10-20 | 9-12 weeks
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Balgreen Road | Scottish Water - ironwork repair | Off-peak 3-way temporary traffic lights | 2025-10-21 | 2025-10-21
Corstorphine / Murrayfield | North West | MURRAYFIELD AREA |  | Autumn Internationals - click cell for fixture list | Road closures before and after each match, details TBC. | 2025-11-01 | 2025-11-23
Corstorphine / Murrayfield | North West | ST JOHN'S ROAD | Opposite Station Road | Clancy Docwra - sewer repairs for Scottish Water Dates and details TBC | 2-way temporary traffic lights, Clermiston Road and Station Road closed | 2025-11-18 | 2025-11-27
Corstorphine / Murrayfield | North West | CORSTORPHINE AREA |  | Corstorphine Connections scheme - replacing some temporary measures with permanent materials. Dates and details TBC | Phased closures of Kirk Loan and Manse Road | 2026-01-05 | 2 weeks estimated
Corstorphine / Murrayfield | North West | ELLERSLY ROAD |  | City of Edinburgh Council - carriageway resurfacing | Road closed (excluding any affected 6 Nations dates) | 2026-01-12 | Up to 6 weeeks
Craigentinny/ Duddingston | North East | ABBEY LANE | At Abbeyhill | Graham Construction - development works | Road closed | 2024-01-09 | End of October 2025
Craigentinny/ Duddingston | North East | DUDDINGSTON LOW ROAD |  | Historic Environment Scotland - risk of rock falls | Road closed to motor vehicles. Road closed to all path users from Tuesday 18/03/25, pedestrian and cyclist diversion via Innocent railway path. Reopened to pedestrians and cyclists 07/08/25, cyclists please dismount through the barrier system at Samson's Ribs. | 2025-03-15 | Until further notice
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Clark Contracts - building development (demolition phase) Not started, new dates TBA. | Section of north footway closed. | 2025-09-01 | December 2027
Craigentinny/ Duddingston | North East | SPRING GARDENS | At Milton Street | Scottish Power - mains disconnection | Temporary traffic lights | 2025-09-30 | 2025-10-13
Craigentinny/ Duddingston | North East | BRITWELL CRESCENT | At Restalrig Avenue | Mackenzie / Scottish Water - CSO works Postponed. New date TBC. | Road closed | 2025-10-06 | 2025-10-07
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Scottish Power - disconnection at development site | Section of north footway closed. Eastbound lane closure to accommodate temporary walkway, cycle lane closed. | 2025-10-13 | 2025-10-17
Craigentinny/ Duddingston | North East | SPRING GARDENS | Between Abbey Lane and Milton Street | Network Rail - vegetation clearance | Road closed for 1 night (times TBC) | 2025-11-03 | 2025-11-04
Drum Brae / Gyle | North West | SOUTH GYLE ROAD | At the rail bridge | Network Rail - renewing rail bridge | Road closed. Access to the station car park via South Gyle Broadway - Gogarloch Road. | 2025-07-28 | April 2026
Drum Brae / Gyle | North West | LADYWELL AVENUE | Between Kirklands and Broomhall Crescent | Network Rail - renewing rail bridge | Road closed | 2025-08-21 | August 2026
Drum Brae / Gyle | North West | GLASGOW ROAD | At the rail bridge between Gogar and Maybury junctions | Network Rail - adjusting parapets as part of electrification project | Lane closures 8pm - 7am each night | 2025-09-13 | 2025-10-24
Drum Brae / Gyle | North West | DRUM BRAE SOUTH | At Drum Brae Avenue | BRM Utilities for Vodafone | 3-way temporary traffic lights | 2025-10-06 | 2025-10-09
Drum Brae / Gyle | North West | LOCHSIDE COURT |  | Carriageway resurfacing | Road closed. Click cell for details of service 32 and 36 diversion. | 2025-10-06 | Up to 1 week
Drum Brae / Gyle | North West | DRUM BRAE SOUTH | At Drum Brae Avenue | Telecoms company - pole and cabinet renewal | Off-peak 3-way temporary traffic lights | 2025-11-03 | 2025-11-07
Drum Brae / Gyle | North West | MEADOW PLACE ROAD | At the rail bridge | Network Rail | Temporary traffic lights, cycle lane closed | 2026-01-16 | 1 week estimated
East Lothian |  | NEWHAILES ROAD | Between Newhailes House and Clayknowes Crescent | Wall repairs | Temporary traffic lights | 2025-09-22 | 2025-10-19
East Lothian |  | A199 EDINBURGH ROAD | At Maitland Park Road, Newhailes | Scottish Power - cable upgrade work | Temporary traffic lights | 2025-10-06 | 2025-10-20
Forth | North West | CRAIGHALL ROAD | Between Craighall Avenue and Grandville | Refurbishment of Trinity Academy | Road closed | 2025-06-30 | May 2028
Forth | North West | GRANTON ROAD | At Boswall Road | BT Morrison - remedial repairs | Temporary traffic lights | 2025-10-12 | 2025-10-14
Forth | North West | BANGHOLM ROAD |  | Clancy Docwra for Scottish Water - sewer cleaning | Road closed to through traffic. | 2025-10-20 | 2025-10-20
Fountainbridge/ Craiglockhart | South West | HARRISON ROAD | At the dog-leg bend where it crosses the cycle path and at the canal bridge | City of Edinburgh Council - bridge repairs | Road closed. Topside footway closures as signed. Road bridge expected to be renewed by end of 2025. Trial holes ongoing at canal bridge. | 2025-02-18 | Ongoing
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Moat Terrace | Scottish Power / Excalon - cable jointing | Temporary traffic lights | 2025-09-17 | 27/10/25 estimated
Fountainbridge/ Craiglockhart | South West | CRAIGLOCKHART TERRACE | At the dog-leg at no.11 | Clancy Docwra for Scottish Water | 4-way temporary traffic lights | 2025-09-29 | 06/10/25 08/10/25
Fountainbridge/ Craiglockhart | South West | HUTCHISON PLACE | At Slateford Road | Scottish Water - ironwork repair Not carried out, new date TBA | Road closed | 2025-09-29 | 2025-09-29
Fountainbridge/ Craiglockhart | South West | SHANDON ROAD | At Shandon Crescent / Shandon Street | Scottish Water - mains survey | 4-way temporary traffic lights | 2025-10-06 | 2025-10-10
Fountainbridge/ Craiglockhart | South West | DUNDEE STREET | At Fountain Park | Scottish Water - ironwork repair | Off-peak temporary traffic lights | 2025-10-13 | 2025-10-13
Fountainbridge/ Craiglockhart | South West | ALLAN PARK ROAD |  | Clancy Docwra for Scottish Water - sewer repairs | Temporary traffic lights | 2025-10-13 | 7-10 days
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Chesser Avenue | Scottish Power - trial holes | 3-way temporary traffic lights 7pm - 7am | 2025-10-13 | 2025-10-14
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Balgreen Road | Scottish Power - trial holes | 4-way temporary traffic lights 7pm - 7am | 2025-10-14 | 2025-10-15
Fountainbridge/ Craiglockhart | South West | WEST APPROACH ROAD | Alongside Fountain Park | Building maintenance via cherry-picker | Sections of south footway closed | 2025-10-18 | 2025-10-18
Fountainbridge/ Craiglockhart | South West | CRAIGLOCKHART AVENUE | Between Craiglockhart Drive North and Craiglockhart Road North | Scottish Water - ironwork repair | 2-way temporary traffic lights | 2025-10-29 | 7am 30/10/25
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Coxfield Lane | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-10-30 | 2025-10-30
Fountainbridge/ Craiglockhart | South West | RITCHIE PLACE | At Watson Crescent | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-11-05 | 2025-11-14
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | Between Ford's Road and Balgreen Road | Scottish Water - major works to install combined sewer overflow (CSO) | Road closed and section of north footway closed. | 2026-01-04 | 16 weeks
Inverleith | North West | STRACHAN ROAD | At Strachan Gardens | Clancy Docwra for Scottish Water - lead renewal | Temporary traffic lights | 2025-09-30 | 03/10/25 08/10/25
Inverleith | North West | EYRE PLACE |  | Openreach - fibre installation | Road closed to through traffic. Temporary traffic lights at Canonmills junction 7pm - 7am each night *no longer required* | 2025-10-06 | 2025-10-10
Inverleith | North West | HAMILTON PLACE | At Stockbridge library | Clancy Docwra - sewer cleaning To be rescheduled for w/c 13/10/25 | Temporary traffic lights | 2025-10-09 | 2025-10-09
Inverleith | North West | HAMILTON PLACE | At Kerr Street / Deanhaugh Street | Mackenzie Construction | 4-way temporary traffic lights | 2025-12-08 | 2025-12-08
Leith | North East | LINDSAY ROAD BRIDGE | Pedestrian / cycle bridge between Nicholfield and Lindsay Road main carriageway | City of Edinburgh Council - public safety measure | Bridge closed, pedestrian and cycle diversion as signed. Hawthornvale Path beneath remains open | 2021-12-15 | Until further notice
Leith | North East | HENDERSON STREET | Between Shore and Parliament Street | City of Edinburgh Council - construction of segregated cycle lane | Lane closures, parking restrictions, temporary traffic lights if required. Currently temporary traffic lights at northern end and Parliament Street closed at Henderson Street. | 2024-12-03 | End of 2025
Leith | North East | GILES STREET | South side of Henderson Gardens | Clancy Docwra for Scottish Water | Road closed | 2025-10-06 | 2025-10-13
Leith | North East | SALAMANDER STREET | Between Assembly Street and Elbe Street | Scottish Water - ironwork repairs (x2) | 2-way temporary traffic lights | 2025-10-14 | 2025-10-15
Leith | North East | BONNINGTON ROAD | At Great Junction Street | Scottish Water - ironwork repair | 4-way temporary traffic lights 7pm - 7am | 2025-10-24 | 2025-10-25
Leith Walk | North East | ALBION ROAD | Between Easter Road and Albion Place | Scottish Water - collapsed manhole | Road closed. No entry from Easter Road | 2025-08-07 | TBC
Leith Walk | North East | EASTER ROAD | Between Sunnyside and Drum Terrace | Clancy Docwra for Scottish Water - lead renewal Work postponed due to Albion Road closure. | 4-way temporary traffic lights | 2025-10-05 | 2025-10-07
Leith Walk | North East | DRYDEN STREET | At Pilrig Street | Scottish Water - mains disconnection Work postponed, new dates TBA | Road closed | 2025-10-06 | 2025-10-08
Leith Walk | North East | LEITH WALK | Between McDonald Road and Annandale Street | Siemens for Edinburgh Trams - track maintenance | Road closed 12.15am - 4.30am, northbound on Wednesday morning and citybound on Thursday morning | 2025-10-08 | 2025-10-09
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Livingston, kick-off 3pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-10-18 | 2025-10-18
Leith Walk | North East | LEITH WALK | Duke Street to Crown Place | Scottish Water - ironwork repair | Citybound bus lane, bus stop and cycle lane closed 12.15am - 4.30am. | 2025-11-08 | 2025-11-08
Leith Walk | North East | BROUGHTON ROAD | At McDonald Road | Scottish Water - manhole repair | 3-way temporary traffic lights | 2025-11-11 | 2025-11-11
Liberton / Gilmerton | South East | LIBERTON BRAE | Between Kirk Brae and Orchardhead Road | SGN - gas main repairs | Lane closures and contraflow, temporary stop for southbound buses | 2025-09-30 | 2 weeks estimated
Liberton / Gilmerton | South East | KAIMES CROSSROADS |  | Scottish Power - high-voltage cable fault | 4-way temporary traffic lights | 2025-10-02 | TBC
Liberton / Gilmerton | South East | LASSWADE ROAD | At Gracemount Avenue | Telecoms company - pole and cabinet installation | 3-way temporary traffic lights | 2025-10-06 | 2025-10-10
Liberton / Gilmerton | South East | GILMERTON ROAD | At Kingston Avenue / Mount Vernon Road | BT Morrison - fibre installation | 3-way temporary traffic lights, Mount Vernon Road closed | 2025-10-11 | 2025-10-12
Liberton / Gilmerton | South East | GILMERTON ROAD | At Morrisons | BT Morrison - fibre installation | 3-way temporary traffic lights | 2025-10-20 | 2025-10-20
Liberton / Gilmerton | South East | LIBERTON BRAE |  | Scottish Water - manhole repair | 2-way temporary traffic lights, Wolrige Road and Hawkhead Crescent closed | 2025-10-22 | 7am 23/10/25
Midlothian |  | A7 at ESKBANK |  | Midlothian Council - carriageway resurfacing and footway construction | Lane closures. Lasswade Road closed between A7 and Captains Gardens. Lasswade Road reopened Monday 18/08/25, lane restrictions thereafter for phase 2. | 2025-07-07 | 2025-10-10
Midlothian |  | MILLERHILL ROAD | Between Shawfair Spine Road and Newton Village | Carriageway upgrade / footway widening / traffic signal installation / utility diversion works / district heating system installation | Temporary traffic lights | 2025-08-11 | April 2026
Morningside | South East | CLUNY GARDENS | At Braid Avenue | Scottish Power - new supply | Temporary traffic lights | 2025-09-22 | 2025-10-09
Morningside | South East | CLUNY GARDENS | At Blackford pond | Scottish Water - valve repairs | Temporary traffic lights | 2025-10-07 | TBC
Morningside | South East | SPOTTISWOODE ROAD | At Marchmont Road | SGN - gas leak repairs | Road closed | 2025-10-07 | TBC
Morningside | South East | BRUNTSFIELD PLACE | Between Holy Corner and Merchiston Place | Clancy Docwra for Scottish Water - lead renewal | Narrow lane citybound with contraflow | 2025-10-15 | 2025-10-17
Morningside | South East | ROSENEATH STREET |  | Clancy Docwra for Scottish Water - sewer survey | Road closed | 2025-11-04 | 2025-11-04
Morningside | South East | BRUNTSFIELD PLACE | At Viewforth | Clancy Docwra for Scottish Water - valve repairs | 2-way temporary traffic lights, Viewforth closed | 2025-12-07 | 2025-12-16
Morningside | South East | MONTPELIER PARK | Between Montpelier and Bruntsfield Place | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2025-12-08 | 2025-12-17
Pentland Hills | South West | MUIR WOOD CRESCENT | Between Thomson Drive and Muir Wood Place | City of Edinburgh Council - carriageway resurfacing | Road closed | 2025-10-06 | 2025-10-10
Pentland Hills | South West | RICCARTON MAINS ROAD | Between Corslet Road and 280m north of the rail bridge | City of Edinburgh Council - carriageway resurfacing | Road closed. Temporary traffic lights at A71 / Curriehill Road junction. Parking suspended on both sides of Curriehill Road between Lanark Road West and Caulderhame Road from 08/10/25. | 2025-10-06 | Up to 8 weeks
Pentland Hills | South West | WESTER HAILES ROAD | Between Clovenstone Road and Harvesters Way | Telecoms company - pole installation | Northbound lane, footway and bus stop closure | 2025-10-06 | 2025-10-17
Pentland Hills | South West | LANARK ROAD WEST | At Blinkbonny Road / Muir Wood Road | BT Morrison | 4-way temporary traffic lights 7pm - 7am | 2025-10-08 | 2025-10-09
Pentland Hills | South West | LANARK ROAD WEST | At Currie Community Centre | BT Morrison Work postponed | Temporary traffic lights | 2025-10-13 | 2025-10-15
Pentland Hills | South West | LANARK ROAD WEST | Between Stewart Road and Dolphin Avenue | BT Morrison | Temporary traffic lights 7pm - 7am for 2 nights | 2025-10-20 | 2025-10-22
Pentland Hills | South West | LANARK ROAD | At City Bypass bridge | Transport Scotland - CCTV camera works | Overnight temporary traffic lights | 2025-11-13 | 2025-11-14
Pentland Hills | South West | CURRIEHILL ROAD | Between Pentland View and Forthview Crescent | Scottish Water - ironwork repair Will be rescheduled if Riccarton Mains Road is still closed | Road closed 9.30am - 9pm | 2025-11-16 | 2025-11-16
Portobello/ Craigmillar | North East | BRUNSTANE ROAD | Between Milton Road East and Argyle Crescent / Dalkeith Street | City of Edinburgh Council - Low Traffic Neighbourhood trial, click cell for more details These measures have now been made permanent and will shortly be removed from this list of temporary restrictions | Road closed to through traffic, except cycles | 2022-02-15 | Ongoing
Portobello/ Craigmillar | North East | GREENDYKES ROAD | Between Greendykes Terrace and the entrance to Greendykes House | Scottish Water - collapsed manhole | Road closed | 2025-10-06 | 2-3 days estimated
Portobello/ Craigmillar | North East | OVERSMAN ROAD | At the roundabout at Whitehill Road / B&Q | Installation of new water services | Temporary traffic lights | 2025-10-06 | 2025-10-19
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Flint Terrace | Marshall Construction | 3-way temporary traffic lights | 2025-10-08 | 2 weeks estimated
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | Between Benhar Road and the rail bridge | Scottish Water - lead renewal and Lightways for Scottish Water - ironwork repair | 3-way temporary traffic lights, bus stops closed on both sides. | 2025-10-14 | 7am 16/10/25
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | Between the A1 and the roundabout at Whitehill Road / McDonalds | BT - manhole repair | Lane closure on westbound Newcraighall Road and A1 (N) off-slip | 2025-10-20 | 2025-10-21
Portobello/ Craigmillar | North East | MUSSELBURGH ROAD | At Coillesdene Terrace | Clancy Docwra for Scottish Water - lead renewal | 3-way temporary traffic lights | 2025-12-01 | 2025-12-10
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Flint Terrace | Scottish Water - manhole repair | 3-way temporary traffic lights | 2025-12-04 | 2025-12-04
Portobello/ Craigmillar | North East | BRIGHTON PLACE | At the rail bridge | Network Rail - bridge repairs | Road closed 10pm - 6am | 2025-12-04 | 2025-12-05
Portobello/ Craigmillar | North East | DUDDINGSTON ROAD | At Mountcastle Drive South | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-12-07 | 7am 08/12/25
Portobello/ Craigmillar | North East | MILTON ROAD | Between Bailie Place and Hope Lane | Scottish Water - ironwork repair | Lane closures and contraflow. Bus lanes and bus stops suspended | 2025-12-07 | 7am 08/12/25
Sighthill/Gorgie | South West | PANSY WALK | Between Baird Drive and Balgreen community garden (just south of the rail / tram bridge) | Scottish Water / CWA - sewer upgrade | Path closed, diversion signed via footbridge and Westfield Avenue | 2025-09-22 | March 2026
Sighthill/Gorgie | South West | BROOMHOUSE CRESCENT | Immediately west of Broomhouse Row | Clancy Docwra for Scottish Water - sewer repairs | Road closed | 2025-10-13 | 2025-10-21
Sighthill/Gorgie | South West | BALGREEN ROAD | At Stevenson Drive | Scottish Water - meter exchange | 3-way temporary traffic lights | 2025-10-15 | 2025-10-23
Sighthill/Gorgie | South West | GORGIE ROAD | At Robertson Avenue | Scottish Power - trial holes Dates TBC | 4-way temporary traffic lights 7pm - 7am | 2025-10-15 | 2025-10-16
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Celtic, kick-off 12pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-10-26 | 2025-10-26
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Dundee, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-11-01 | 2025-11-01
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Dundee Utd, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-11-08 | 2025-11-08
Sighthill/Gorgie | South West | GORGIE ROAD | At Robertson Avenue | Network Rail | 4-way temporary traffic lights 7pm - 7am | 2025-11-08 | 2025-11-09
Sighthill/Gorgie | South West | WESTFIELD ROAD | Between Sainsburys and Roseburn Street | Scottish Water - manhole repair | Overnight temporary traffic lights | 2025-11-21 | 2025-11-21
Sighthill/Gorgie | South West | GORGIE ROAD | At Robertson Avenue | Scottish Water - ironwork repair | 4-way temporary traffic lights 9.30am - 11.30am | 2025-11-30 | 2025-11-30
Southside / Newington | South East | SOUTH CLERK STREET | Bernard Terrace to Lutton Place | Clancy Docwra for Scottish Water - sewer repairs | Southbound lane closure | 2025-08-13 | 26/08/25 02/11/25 estimated
Southside / Newington | South East | KILGRASTON ROAD | At Grange Loan | SGN - gas leak repairs | Crossroads closed | 2025-09-17 | Mid-November estimated
Southside / Newington | South East | NICOLSON STREET | Between West Nicolson Street and Nicolson Square | SGN - new gas service | Citybound lane closure, temporary bus stop for northbound services | 2025-09-22 | 03/10/25 08/10/25
Southside / Newington | South East | LIBERTON ROAD | Between Lady Road and Gilmerton Road | Collapsed manhole | Section of southbound inside lane closed | 2025-09-29 | TBC
Southside / Newington | South East | CAUSEWAYSIDE | At Duncan Street | SGN - new gas service | 3-way temporary traffic lights, section of southbound cycle lane closed, temporary bus stops on both sides. | 2025-10-06 | 2025-10-17
Southside / Newington | South East | DALKEITH ROAD | Between East Mayfield and Spence Street | Clancy Docwra for Scottish Water - lead renewal | Lane closures and contraflow, citybound bus stop closed | 2025-10-06 | 2025-10-10
Southside / Newington | South East | GEORGE SQUARE |  | University of Edinburgh open day | North and east legs and Crichton Street closed 8am - 4.30pm | 2025-10-25 | 2025-10-25
Southside / Newington | South East | BLACKFORD AVENUE | At South Oswald Road | BT - manhole repair Likely to be postponed due to ongoing gas leak repairs at Kilgraston Road | 3-way temporary traffic lights, St Alban's Road closed | 2025-10-26 | 2025-10-26
Southside / Newington | South East | MINTO STREET | At Blacket Place | Clancy Docwra for Scottish Water - valve repairs | 3-way temporary traffic lights, Duncan Street closed | 2025-11-10 | 2025-11-19
Southside / Newington | South East | WEST NICOLSON STREET | At Nicolson Street | Clancy Docwra for Scottish Water | Road closed | 2026-01-05 | 2026-01-18
Southside / Newington | South East | MINTO STREET | At Salisbury Place | Scottish Water - manhole repair | 4-way temporary traffic lights | 2026-01-11 | 7am 12/01/26
Trunk road network |  | M8 | Between J3A and 4 | BEAR Scotland - B792 bridge refurbishment | Contraflow and 40mph speed restriction | 2025-05-18 | 4 months estimated
Trunk road network |  | M9 | Between J1 and J10 | BEAR Scotland - maintenance 29/09/25 - the remainder of this work is on hold to accommodate resurfacing at Cadger's Brae. | Series of overnight lane and carriageway closures - click cell for full details | 2025-09-01 | 2025-10-15
Trunk road network |  | M8 | Between J2 and J3A | BEAR Scotland - carriageway resurfacing | Eastbound on-slip at J3 closed 8.30pm - 6am for 4 nights. Eastbound carriageway closed J4 - J2, 8.30pm - 6am from 29/09/25 for 15 weekday nights. | 2025-09-23 | 2025-10-18
Trunk road network |  | M90 | Between J1A and J3 | BEAR Scotland - routine maintenance programme | Series of overnight lane and carriageway closures - click cell for full details | 2025-10-16 | 2025-11-03
Trunk road network |  | M8 | At J3 | BEAR Scotland - carriageway resurfacing | Westbound on-slip closed 8.30pm - 6am for 3 nights | 2025-10-22 | 2025-10-25
Trunk road network |  | A720 | At Calder junction | BEAR Scotland - carriageway resurfacing | Eastbound on-slip closed 8.30pm - 6am for 3 weekday nights (no weekend works) | 2025-10-23 | 2025-10-28
Trunk road network |  | A720 | Straiton to Lothianburn | BEAR Scotland - carriageway resurfacing | Road closed to westbound traffic 8.30pm - 6am for 15 weekday nights | 2025-10-28 | 2025-11-18
Trunk road network |  | FORTH ROAD BRIDGE |  | BEAR Scotland - removal of traffic management associated with bridge maintenance works | Bridge closed 9.30pm - 5am for 2 nights | 2025-10-29 | 2025-10-31
Trunk road network |  | FORTH ROAD BRIDGE |  | Supernova charity run | Bridge closed 9.30am Friday - 5am Sunday | 2025-10-31 | 2025-11-02
Roadworks & events report
Effective from 8 October 2025