## General Road Works
Links to further information
| Traffic Scotland - realtime information on trunk roads including Edinburgh City Bypass |  |  |  | Details of Ward and Locality boundaries
SE Scotland trunk roads maintenance by BEAR Scotland
Key
| Transport for Edinburgh - Lothian Buses and Edinburgh Trams |  |  |  | New or updated information in this version
Underlined entries contain links to maps or further information
Edinburgh Travelling Safely measures and Low Traffic Neighbourhoods
| Our social media channels: |  | X (formerly Twitter) | Facebook | Threads
Excel - use the drop-down arrows to sort by any column. PDF - use CTRL + F to search for any keyword. |  |  |  | NB this is not intended to be a list of all the roadworks in Edinburgh. Please refer to the Scottish Roadworks Register website for basic information on all registered roadworks
Ward | Locality | Street | Location | Contractor / works description | Measures in place | Start | Finish
Almond | North West | MAYBURY ROAD | At Craigs Road | Construction of signalised junction | Various lane closures and contraflow arrangements. Craigs Road closed on both sides. Programme for resurfacing phase under review. | 2025-05-06 | February 2026
Almond | North West | SILVERKNOWES ROAD | Between Silverknowes Parkway and Marine Drive | City of Edinburgh Council - carriageway reconstruction | Road closed. Click cell for details of service 29 diversion. | 2025-10-01 | 05/10/25 26/10/25 Until further notice
Almond | North West | GLASGOW ROAD | Between Gogar and Ingliston | City of Edinburgh Council - drainage surveys | Various lane closures, off-peak daytime until end of November then nighshift through December and early January. | 2025-10-28 | January 2026
Almond | North West | TURNHOUSE ROAD | At the rail bridge west of Turnhouse Farm Road | Network Rail - parapet adjustments as part of electrification project | Temporary traffic lights | 2025-11-08 | 2026-01-05
Almond | North West | OLD LISTON ROAD | At Bridge Street | Scottish Power - street lighting repairs Actual start date 12/11/25 | Temporary traffic lights | 2025-11-10 | 21/11/25 25/11/25
Almond | North West | MAIN STREET, DAVIDSON'S MAINS | At Cramond Road South / Quality Street | Power and water main connections for new development | 3-way temporary traffic lights, East Barnton Gardens closed | 2025-11-17 | 3 weeks estimated
Almond | North West | TURNHOUSE ROAD | At Turnhouse Farm Road | BT Circet - ducting installation | Temporary traffic lights | 2025-11-19 | 2025-11-23
Almond | North West | B924 | At Dolphington | Clancy Docwra for Scottish Water - repairs to burst pipe | Temporary traffic lights | 2025-11-21 | TBC
Almond | North West | QUEENSFERRY AREA |  | Christmas in Queensferry | High Street / Edinburgh Road closed to through traffic 4pm - 8pm. The Loan closed between Scotmid and High Street 5.45pm - 6pm. | 2025-11-27 | 2025-11-27
Almond | North West | STATION ROAD, KIRKLISTON | At Station Terrace | BT - pole replacement | Off-peak temporary traffic lights | 2025-11-28 | 2025-11-28
Almond | North West | EAST BARNTON GARDENS |  | Christmas lights switch-on | Road closed 8am - 8pm | 2025-11-29 | 2025-11-29
Almond | North West | EASTFIELD AVENUE |  | Siemens for Edinburgh Trams - track maintenance | Road closed 12am - 4am | 2025-12-01 | 2025-12-01
Almond | North West | GLASGOW ROAD | Between Newbridge and Ingliston | City of Edinburgh Council - drainage surveys | Overnight lane closures in both directions | 2025-12-02 | 2025-12-12
Almond | North West | WHITEHOUSE ROAD | At Regis Court | Forestry work | Temporary traffic lights | 2025-12-05 | 2025-12-05
Almond | North West | GOGAR STATION ROAD | Between Glasgow Road and Gogarbank | Advance Construction - new road layout with RBS HQ | Road closed (in sections as work progresses). Temporary traffic lights as required at RBS entrance / Business School entrance. | 2026-01-05 | February 2027
Almond | North West | CRAMOND ROAD SOUTH | Between Barnton Avenue and Quality Street, to include Main Street mini-roundabout | City of Edinburgh Council - carriageway resurfacing | Phase 1 - roundabout and all approaches closed; Phase 2 - Cramond Road South closed. | 2026-02-16 | 3 weeks estimated
City Centre | South East | NORTH BRIDGE |  | City of Edinburgh Council / Balfour Beatty - bridge refurbishment | East footway closed, pedestrian access via west footway. One traffic lane open in each direction (as of 21/04/23). | 2020-02-15 | Summer 2026
City Centre | South East | TARVIT STREET |  | Redevelopment of King's Theatre | Tarvit Street closed between Home Street and Drumdryan Street. Drumdryan Street northbound only. NCR 75 closed, cycle diversion signed via Valleyfield Street | 2023-02-14 | Late 2026
City Centre | South East | DEVON PLACE | Between West Coates and no. 4 | For Ogilvie Construction | Road closed to southbound traffic. | 2023-06-06 | March 2026
City Centre | South East | ROSE STREET | At South St David Street | Redevelopment of former Scottish Widows / Sainsbury's building | Road closed, delivery access via Hanover Street | 2025-06-01 | TBC
City Centre | South East | KING'S STABLES ROAD | Between Lothian Road and the entrance to the NCP car park by Barrace Steps | Edinburgh's Christmas | Road closed to all traffic 27/10 - 24/11 and 08/12 - 18/01. Road closed to westbound traffic except cycles 25/11 - 08/12. | 2025-10-27 | 2026-01-18
City Centre | South East | FOUNTAINBRIDGE | Between Lothian Road and Semple Street | Crane lift for glazing repairs Work postponed | Road closed 6am - 4pm | 2025-11-02 | 2025-11-02
City Centre | South East | GEORGE STREET | Between Charlotte Square and Frederick Street | Edinburgh's Christmas | Road closed except for cycles. Loading permitted on westbound side, 6.30am - 9.30am daily. Castle Street / North Castle Street closed 10am - 11pm each day from 06/11/25. | 2025-11-05 | 2026-01-18
City Centre | South East | BREAD STREET LANE | At East Fountainbridge | Scottish Power - cable jointing | Road closed, access via Bread Street | 2025-11-07 | 2025-11-21
City Centre | South East | COWGATE | Outside the Three Sisters | Scottish Water - ironwork repair Work postponed | Temporary traffic lights, section of north footway closed | 2025-11-13 | 2025-11-13
City Centre | South East | FORREST ROAD |  | Clancy Docwra - sewer repairs for Scottish Water | Road closed 9.30am - 3.30pm each weekday (no access to George IV Bridge, hairpin to Bristo Place remains open). Road closure in place 9.30am - 12.30pm on Saturday 22/11/25 and again on Monday 24/11/25 for reinstatement works. | 2025-11-18 | 2025-11-24
City Centre | South East | MELVILLE CRESCENT | South west leg | Clancy Docwra - urgent repairs for Scottish Water | Road closed (no exit from Walker Street to Melville Street, diversion via William Street - Manor Place) | 2025-11-20 | 27/11/25 estimated
City Centre | South East | LOTHIAN ROAD | Between the Filmhouse and Fountainbridge junction | Scottish Water - repairs to burst pipe | Southbound lane and bus stop closures on Lothian Road, lane 4 of 4 closed on Morrison Street towards Lothian Road. | 2025-11-20 | 2025-11-22
City Centre | South East | MORRISON STREET | Between Semple Street and Gardner's Crescent | Tower crane installation | Road closed 12.30am Friday - 6pm Sunday | 2025-11-21 | 2025-11-23
City Centre | South East | WEST PORT | At King's Stables Road | BT Circet - urgent pole replacement | Temporary traffic lights | 2025-11-21 | 2025-11-21
City Centre | South East | ROYAL MILE AREA |  | March | Rolling road closure Lawnmarket - High Street - Canongate - Horse Wynd, 1pm - 3pm. | 2025-11-22 | 2025-11-22
City Centre | South East | GEORGE IV BRIDGE | At Lawnmarket | For Sir Robert McAlpine development | 3-way temporary traffic lights, Lawnmarket closed between George IV Bridge and St Gile's Street | 2025-11-24 | 2025-11-28
City Centre | South East | YORK LANE | East / West section | Building development | Road closed | 2025-11-24 | April 2027
City Centre | South East | ST MARY'S STREET | At Cowgate / Holyrood Road | Vodafone - network maintenance | 4-way temporary traffic lights 8pm - 7am | 2025-11-26 | 2025-11-27
City Centre | South East | LONDON ROAD | At Blenheim Place | BRM Utilities for Vodafone - proving / clearing ducts | Citybound inside lane closed 8pm - 6am | 2025-11-27 | 2025-11-28
City Centre | South East | MOUND PLACE |  | Edinburgh's Christmas | Road closed 3pm - 5.30pm | 2025-11-30 | 2025-11-30
City Centre | South East | THISTLE STREET | At Hanover Street (west side) | Clancy Docwra for Scottish Power - remedial works | Road closed | 2025-12-01 | 2025-12-05
City Centre | South East | VALLEYFIELD STREET |  | Scottish Water - service connection | Road closed except for cycles | 2025-12-01 | 2025-12-10
City Centre | South East | WAVERLEY BRIDGE |  | Edinburgh's Christmas | Road closed except for cycles. Loading permitted 10pm - 10am daily, via Market Street. | 2025-12-15 | 2025-12-28
City Centre | South East | WAVERLEY BRIDGE |  | Edinburgh's Christmas | Road closed 10am Saturday - 10pm Sunday, except for cycles. Loading permitted 10pm - 10am daily, via Market Street. | 2026-01-03 | 2026-01-04
City Centre | South East | LEVEN STREET AREA |  | City of Edinburgh Council - footway extensions, traffic signals improvements, cycle insfrastructure upgrades, carriageway resurfacing | Lane closures. Temporary traffic lights at Gilmore Pace junction from 19/01/26. Valleyfield Street closed for the majority of the scheme. | 2026-01-12 | Mid April estimated
City Centre | South East | GILMORE PLACE |  | City of Edinburgh Council - carriageway resurfacing | Road closed in sections. Phase 1 (of 3) between Leven Street and Leamington Terrace for 3 weeks, Monday - Friday only. | 2026-01-19 | Early May 2026
City Centre | South East | ROSE STREET SOUTH LANE | Section between South Charlotte Street and Castle Street | Energy Assets - investigation works | Road closed | 2026-01-19 | 2026-02-06
City Centre | South East | QUEEN STREET / ALBYN PLACE |  | Comex2000 for Virgin Media | Lane closure northbound North Charlotte Street / eastbound Albyn Place | 2026-01-26 | 2026-01-31
City Centre | South East | ALBYN PLACE |  | Clancy Docwra for Scottish Water | Eastbound inside lane closed | 2026-02-15 | 2026-02-22
Colinton / Fairmilehead | South West | FROGSTON ROAD WEST | At Winton Drive | Energetics - reinstatement works following cable installation | 3-way temporary traffic lights | 2025-11-18 | 2025-11-28
Colinton / Fairmilehead | South West | BONALY ROAD | Between West Carnethy Avenue and Munro Drive | BT - manhole repair | Road closed | 2026-02-16 | 2026-02-17
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Murrayfield | Scottish Water - major works to install combined sewer overflow (CSO) | Temporary traffic lights. Ormidale Terrace closed. Westbound bus stop closed, please use the next stop. | 2025-06-08 | November 2025
Corstorphine / Murrayfield | North West | BALGREEN ROAD and SAUGHTON CRESCENT |  | City of Edinburgh Council - carriageway resurfacing and active travel improvements. | Daytime lane closures and temporary traffic lights for preparatory and footway works, nightshift road closures for main resurfacing work. Currently temporary traffic lights on Balgreen Road at Glendevon Park. | 2025-10-20 | May 2026 (with a break over Christmas)
Corstorphine / Murrayfield | North West | MURRAYFIELD AREA |  | Autumn Internationals on 1st, 8th, 16th and 23rd November - click cell for fixture list | Road closures before and after each match affecting A8 corridor and West Approach Road, click cell for details. | 2025-11-01 | 2025-11-23
Corstorphine / Murrayfield | North West | ST JOHN'S ROAD | Opposite Station Road | Clancy Docwra - sewer repairs for Scottish Water | 2-way temporary traffic lights, Clermiston Road and Station Road closed | 2025-11-25 | 2025-11-28
Corstorphine / Murrayfield | North West | ROSEBURN STREET | At Roseburn Avenue | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2025-11-25 | 2025-11-26
Corstorphine / Murrayfield | North West | KIRK LOAN |  | Christmas lights switch-on | Road closed 5.30pm - 8pm | 2025-11-28 | 2025-11-28
Corstorphine / Murrayfield | North West | CORSTORPHINE AREA |  | Corstorphine Connections scheme - replacing some temporary measures with permanent materials. Dates and details TBC | Phased closures of Kirk Loan and Manse Road. New information 20/11/25 - Manse Road expected to be closed 01/12/25 for 2 weeks. | 2026-01-05 | 2 weeks estimated
Corstorphine / Murrayfield | North West | ELLERSLY ROAD |  | City of Edinburgh Council - carriageway resurfacing | Road closed (excluding any affected 6 Nations dates) | 2026-01-12 | Up to 6 weeeks
Craigentinny/ Duddingston | North East | DUDDINGSTON LOW ROAD |  | Historic Environment Scotland - risk of rock falls | Road closed to motor vehicles. Road closed to all path users from Tuesday 18/03/25, pedestrian and cyclist diversion via Innocent railway path. Reopened to pedestrians and cyclists 07/08/25, cyclists please dismount through the barrier system at Samson's Ribs. | 2025-03-15 | Until further notice
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Clark Contracts - building development (demolition of existing buildings then construction of new premises) Start date awaiting confirmation. | Section of north footway and inside lane closed for installation of scaffolding (1-2 days). North side cycle lane narrowed to accommodate footway extension. Occasional occupation of eastbound inside lane for deliveries. Section of west footway on Restalrig Road South closed. | 2025-11-06 | December 2027
Craigentinny/ Duddingston | North East | CHRISTIEMILLER AVENUE | At Portobello Road | Scottish Power - cable fault Work extended | Road closed | 2025-11-12 | 21/11/25 estimated 01/12/25
Craigentinny/ Duddingston | North East | MORAY PARK TERRACE |  | Virgin Media | Temporary traffic lights | 2025-11-25 | 2025-11-28
Craigentinny/ Duddingston | North East | RESTALRIG ROAD SOUTH (SMOKEY BRAE) |  | Network Rail - removal of bird netting | Road closed 8pm - 6am | 2025-11-29 | 2025-11-30
Craigentinny/ Duddingston | North East | SLEIGH DRIVE | At Findlay Gardens | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-12-09 | 2025-12-09
Craigentinny/ Duddingston | North East | WILLOWBRAE GARDENS | At Baronscourt Terrace | Clancy Docwra for Scottish Water | Road closed | 2026-02-03 | 2026-02-12
Craigentinny/ Duddingston | North East | ABBEYHILL | At Brae House | Virgin Media - ironwork repairs | Temporary traffic lights | 2026-03-08 | 7am 09/03/26
Drum Brae / Gyle | North West | SOUTH GYLE ROAD | At the rail bridge | Network Rail - renewing rail bridge | Road closed. Access to the station car park via South Gyle Broadway - Gogarloch Road. Station car park closed 24/11 - 05/12/25. | 2025-07-28 | April 2026
Drum Brae / Gyle | North West | LADYWELL AVENUE | Between Kirklands and Broomhall Crescent | Network Rail - renewing rail bridge | Road closed | 2025-08-21 | August 2026
Drum Brae / Gyle | North West | MAYBURY DRIVE | At North Bughtlin Road | BRM Utilities for Vodafone | 3-way temporary traffic lights | 2025-11-24 | 2025-11-26
Drum Brae / Gyle | North West | MEADOW PLACE ROAD | At the rail bridge | City of Edinburgh Council - for upgrade works at Torwood Path | Temporary traffic lights (removed for Christmas period) | 2025-12-03 | 4 months estimated
Drum Brae / Gyle | North West | SOUTH GYLE ACCESS |  | City of Edinburgh Council - installation of segregated cycle lane | Lane closures. Road closures April 2026 for final surfacing. | 2025-12-03 | 5-6 months
Drum Brae / Gyle | North West | MEADOW PLACE ROAD | At the rail bridge | Network Rail | Temporary traffic lights, cycle lane closed | 2026-01-16 | 1 week estimated
East Lothian |  | A199 EDINBURGH ROAD | At Maitland Park Road, Newhailes | Scottish Power - cable upgrade work Work extended | Temporary traffic lights | 2025-10-06 | 20/10/25 21/11/25 12/12/25
Forth | North West | CRAIGHALL ROAD | Between Craighall Avenue and Grandville | Refurbishment of Trinity Academy | Road closed | 2025-06-30 | May 2028
Forth | North West | GRANTON ROAD | At Boswall Green | SGN - gas leak repairs | Temporary traffic lights, Boswall Green closed | 2025-10-21 | 02/12/25 estimated
Forth | North West | WARDIEBURN CRESCENT | At Granton Crescent | Scottish Water - valve repairs | Road closed and Boswall Loan closed | 2025-12-02 | 2025-12-05
Forth | North West | GRANTON CRESCENT | At Wardieburn Place North | Scottish Water - lead renewal | Roads closed | 2025-12-09 | 2025-12-12
Forth | North West | BOSWALL PARKWAY | Between Pilton Avenue and Boswall Terrace | Clancy Docwra for Scottish Water | Temporary traffic lights | 2026-01-17 | 2026-01-21
Fountainbridge/ Craiglockhart | South West | HARRISON ROAD | At the dog-leg bend where it crosses the cycle path and at the canal bridge | City of Edinburgh Council - bridge repairs | Road closed. Topside footway closures as signed. Road bridge expected to be renewed by end of 2025. Trial holes ongoing at canal bridge. | 2025-02-18 | Spring 2026 TBC
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Gorgie Park Road / Westfield Road | Cityfibre - clearing blocked ducts Postponed due to Scottish Power fault, new date TBA | 3-way temporary traffic lights, Westfield Road closed | 2025-11-04 | 2025-11-04
Fountainbridge/ Craiglockhart | South West | GREENBANK DRIVE | At Glenlockhart Road | Scottish Water - lead renewal | 3-way temporary traffic lights, Greenbank Lane closed | 2025-11-27 | 2025-12-01
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Ardmillan Terrace / Harrison Road | Tree trimming at St Michael's Church | 4-way temporary traffic lights 8am - 5pm | 2025-11-30 | 2025-11-30
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Robertson Avenue | Scottish Water - manhole repair | 3-way temporary traffic lights, Hermand Crescent closed. 7pm - 7am | 2025-12-12 | 2025-12-13
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | Between Ford's Road and Balgreen Road | Scottish Water - major works to install combined sewer overflow (CSO) | Road closed and section of north footway closed. | 2026-01-04 | 16 weeks
Fountainbridge/ Craiglockhart | South West | HUTCHISON PLACE | At Slateford Road | Scottish Water - ironwork repair | Road closed | 2026-01-06 | 2026-01-06
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Appin Terrace | Scottish Water - ironwork repair | 2-way temporary traffic lights 7pm - 7am | 2026-01-16 | 2026-01-17
Inverleith | North West | RODNEY STREET |  | SGN - gas leak repairs | Road closed to citybound traffic. | 2025-11-04 | TBC
Inverleith | North West | BELFORD ROAD | At the Water of Leith bridge / Douglas Gardens | City of Edinburgh Council - drainage and gully repairs Work extended | 3-way temporary traffic lights | 2025-11-17 | 21/11/25 estimated 26/11/25
Inverleith | North West | TELFORD ROAD | At Groathill Road North | Clancy Docwra - sewer repair for Scottish Water | 3-way temporary traffic lights | 2025-11-20 | 22/11/25 estimated
Inverleith | North West | HAMILTON PLACE | At Kerr Street / Deanhaugh Street | Mackenzie Construction | 4-way temporary traffic lights | 2025-12-08 | 2025-12-08
Inverleith | North West | EYRE PLACE AREA | Between Eyre Terrace and Canon Street | Morrisons Construction - drainage installation for development site | Phase1 - Canon Street closed for 3 weeks. Phase 2 - temporary traffic lights on Eyre Place. Phase 3 - Eyre Place closed at Eyre Crescent. | 2026-01-05 | 11 weeks estimated
Inverleith | North West | TELFORD ROAD | Groathill Road North to Telford Drive | SGN - gas main renewal | Phase 1 - 3-way temporary traffic lights at Groathill Road North with Groathill Road South closed (approximately 1 week). Phase 2 - lane closures between Groathill Avenue and Telford Drive with Telford Drive closed. | 2026-01-26 | 3 weeks estimated
Leith | North East | LINDSAY ROAD BRIDGE | Pedestrian / cycle bridge between Nicholfield and Lindsay Road main carriageway | City of Edinburgh Council - public safety measure | Bridge closed, pedestrian and cycle diversion as signed. Hawthornvale Path beneath remains open | 2021-12-15 | Until further notice
Leith | North East | HENDERSON STREET AREA |  | City of Edinburgh Council - construction of segregated cycle lane | Lane closures, parking restrictions, temporary traffic lights if required. Currently temporary traffic lights at northern end and Parliament Street closed at Henderson Street. | 2024-12-03 | End of 2025
Leith | North East | LEITH |  | Abnormal load | Bath Road - Salamander Street - A199 - A1 - A720 - A68 - A697 (9pm departure) | 2025-12-13 | 2025-12-14
Leith | North East | COMMERCIAL STREET | At Ocean Drive / Lindsay Road | Scottish Water - manhole repair | 4-way temporary traffic lights | 2026-01-07 | 7am 08/01/26
Leith | North East | BERNARD STREET | At Shore / Commercial Street | Scottish Water - mains surveys | 3-way temporary traffic lights, Bernard Street closed between Shore and Timber Bush, 7pm - 7am | 2026-01-29 | 2026-01-30
Leith | North East | FERRY ROAD | Between Madeira Street and Leith library | Scottish Water - manhole repair | Road closed 7pm - 7am | 2026-02-01 | 2026-02-02
Leith | North East | SHORE | Between Timber Bush and Tower Street | Scottish Water - mains surveys | Road closed | 2026-02-02 | 2026-02-02
Leith | North East | SHORE | At Tower Street | Scottish Water - mains surveys | Roads closed | 2026-02-03 | 2026-02-03
Leith Walk | North East | ALBION ROAD | Between Easter Road and Albion Place | Scottish Water - collapsed manhole | Road closed. No entry from Easter Road | 2025-08-07 | 08/12/25 estimated
Leith Walk | North East | ST MARK'S PATH |  | Development works at former Powderhall bowling green site | Path closed. Diversion signed via Warriston Road - Hughes Close - Powderhall Road - Beaverhall Road - Broughton Road | 2025-11-17 | Until further notice
Leith Walk | North East | BONNINGTON ROAD | Between Tinto Place and Bonnington Road Lane | Scottish Power - cable fault | Road closed to through traffic, diversion signed via Newhaven Road - Ferry Road - Great Junction Street. | 2025-11-19 | TBC
Leith Walk | North East | EASTER ROAD | At Edina Street | SGN - gas leak repairs | Temporary traffic lights | 2025-11-19 | TBC
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Dundee, kick-off 3pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-11-22 | 2025-11-22
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Celtic, kick-off 12pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-11-30 | 2025-11-30
Leith Walk | North East | EASTER ROAD | At Lorne Street / St Clair Avenue | Scottish Water - manhole repair | 3-way temporary traffic lights, Lorne Street closed | 2026-01-06 | 7am 07/01/26
Leith Walk | North East | ARTHUR STREET | At Pilrig Street | Scottish Water - mains disconnection | Road closed to eastbound traffic | 2026-01-12 | 2026-01-16
Leith Walk | North East | DRYDEN STREET | At Pilrig Street | Scottish Water - mains disconnection | Road closed | 2026-01-19 | 2026-01-21
Leith Walk | North East | EASTER ROAD | Between Sunnyside and Drum Terrace | Clancy Docwra for Scottish Water - lead renewal | 4-way temporary traffic lights | 2026-02-08 | 2026-02-10
Leith Walk | North East | PILRIG GARDENS |  | Clancy Docwra for Scottish Water - lead renewal | Road closed to through traffic | 2026-02-11 | 2026-02-15
Liberton / Gilmerton | South East | LASSWADE ROAD | Just south of Lang Loan | City of Edinburgh Council - street lighting installation | Temporary traffic lights | 2025-11-04 | 2025-11-23
Liberton / Gilmerton | South East | LIBERTON DRIVE | At Alnwickhill Road | Scottish Power - cable fault | 4-way temporary traffic lights | 2025-11-10 | TBC
Liberton / Gilmerton | South East | LIBERTON BRAE | At Alnwickhill Road | Scottish Power - cable fault | Temporary traffic lights | 2025-11-20 | TBC
Liberton / Gilmerton | South East | GILMERTON ROAD | Between Moredunvale Road and Ellen's Glen Road | City of Edinburgh Council - bridge inspection | Lane and parking restrictions as signed, cycle lane access disrupted | 2025-11-21 | 2025-11-21
Liberton / Gilmerton | South East | LASSWADE ROAD | At Kirkgate | BT Morrison | 4-way temporay traffic lights | 2025-11-22 | 2025-11-23
Liberton / Gilmerton | South East | OLD DALKEITH ROAD | At Ferniehill Road | BT Morrison - clearing blocked cable ducts | 3-way temporary traffic lights 9.30am - 5pm | 2025-11-23 | 2025-11-23
Liberton / Gilmerton | South East | GILMERTON ROAD | At Moredun Park Road / Morrisons | BT Morrison - cabling | 4-way temporary traffic lights, 8pm - 7am for 2 nights | 2025-11-23 | 2025-11-25
Liberton / Gilmerton | South East | INGLEWOOD PLACE | At Glendinning Crescent | Telecomms company - pole and cabinet installation | Roads closed | 2025-11-24 | 2025-11-28
Liberton / Gilmerton | South East | RAVENSCROFT GARDENS | At Ravenscroft Street | Crane lift | Road closed 9.30am - 12.30pm approximately | 2025-11-24 | 2025-11-24
Liberton / Gilmerton | South East | CAPTAIN'S ROAD | Gracemount Road and Southhouse Broadway | Scottish Water - manhole repair | Temporary traffic lights | 2025-11-25 | 2025-11-25
Liberton / Gilmerton | South East | NEWTOFT STREET | Outside the Miner's Club | BT Morrison - clearing blocked cable ducts | Temporary traffic lights | 2025-11-29 | 2025-11-30
Liberton / Gilmerton | South East | GILMERTON ROAD | At The Spinney | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2026-01-12 | 2026-01-21
Midlothian |  | MILLERHILL ROAD | Between Shawfair Spine Road and Newton Village | Carriageway upgrade / footway widening / traffic signal installation / utility diversion works / district heating system installation | Temporary traffic lights | 2025-08-11 | April 2026
Midlothian |  | NEWTON CHURCH ROAD | At A6106 Millerhill Road | Advance Construction - utility installations | Road closed | 2025-12-01 | 2 weeks estimated
Morningside | South East | COMISTON VIEW | At Comiston Road | SGN - gas leak repairs | Road closed | 2025-11-14 | TBC
Morningside | South East | COLINTON ROAD | At Tipperlinn Road | Scottish Power - cable jointing | 3-way temporary traffic lights | 2025-11-17 | 2025-11-26
Morningside | South East | MARCHMONT ROAD | At Marchmont Crescent | Scottish Power - cable installation | 2-way temporary traffic lights, Marchmont Crescent and Spottiswoode Road closed | 2025-11-17 | 3 months estimated
Morningside | South East | BRUNTSFIELD PLACE | At Whitehouse Loan | Virgin Media - network repairs | Temporary traffic lights | 2025-11-23 | 2025-11-23
Morningside | South East | ETTRICK ROAD |  | BT Morrison - clearing blocked cable ducts | Temporary traffic lights | 2025-11-25 | 2025-11-27
Morningside | South East | BRUNTSFIELD PLACE | At Viewforth | Clancy Docwra for Scottish Water - valve repairs | 2-way temporary traffic lights, Viewforth closed | 2026-01-19 | 2026-01-28
Pentland Hills | South West | RICCARTON MAINS ROAD | Between Corslet Road and 280m north of the rail bridge | City of Edinburgh Council - carriageway resurfacing | Road reopened 10/11/25. Temporary traffic lights for anti-skid surfacing, scheduled for w/c 08/12/25. | 2025-10-06 | 14/11/25 estimated
Pentland Hills | South West | A70 LANARK ROAD | West of the Ravelrig bends | Scottish Power - cable fault | 5-way temporary traffic lights | 2025-11-11 | 30/11/25 estimated
Pentland Hills | South West | MUIR WOOD CRESCENT | Between Thomson Drive and Muir Wood Grove | City of Edinburgh Council - carriageway resurfacing | Road closed and Muir Wood Place closed | 2025-11-17 | 2025-11-21
Pentland Hills | South West | LANARK ROAD WEST | At Blinkbonny Road | Scottish Water - lead renewal Reinstatement prolonged due to cold weather | 3-way temporary traffic lights | 2025-11-18 | 21/11/25 estimated By 24/11/25
Pentland Hills | South West | LANARK ROAD WEST | Between Sainsbury's garage and Bryce Road | City of Edinburgh Council - renewal of barriers | Temporary traffic lights | 2025-11-24 | 2 weeks estimated
Pentland Hills | South West | BABERTON MAINS WAY | At Baberton Mains Rise | BT Morrison - clearing blocked cable ducts | 4-way temporary traffic lights | 2025-11-25 | 2025-11-29
Pentland Hills | South West | NORTH STREET, RATHO | At Main Street | Christmas lights switch-on | Road closed 4.30pm - 7.30pm | 2025-12-12 | 2025-12-12
Pentland Hills | South West | WESTER HAILES ROAD | At the railway bridge between Murrayburn Road and Clovenstone Road | Network Rail - bridge inspection | Road closed 10pm - 6am for 2 nights: Monday night road closed northbound, no access beyond Harvester's Way. Tuesday night road closed southbound, no access to Plaza car park. | 2025-12-15 | 2025-12-17
Pentland Hills | South West | LANARK ROAD WEST | Between Sainsbury's garage and Bryce Road | Scottish Water - valve repairs | Temporary traffic lights | 2025-12-17 | 2025-12-17
Pentland Hills | South West | BELMONT ROAD | Between Baberton Avenue and Juniper Grove | Clancy Docwra for Scottish Water | Road closed | 2026-01-20 | 2026-01-20
Portobello/ Craigmillar | North East | GREENDYKES ROAD / TUDSBURY AVENUE | From Pringle Street into and along Tudsbury Avenue | GTC Pipelines - utility installations | Temporary traffic lights, rolling programme | 2025-11-10 | 2025-11-24
Portobello/ Craigmillar | North East | NIDDRIE MAINS ROAD | At Niddrie Marischal Road | SGN - gas leak repairs | Temporary traffic lights, Niddrie Marischal Road closed | 2025-11-18 | End of November estimated
Portobello/ Craigmillar | North East | NIDDRIE MAINS ROAD | At Niddrie Farm Grove | Maintenance work at phone mast Work postponed | Temporary traffic lights 8pm - 6am | 2025-11-25 | 2025-11-26
Portobello/ Craigmillar | North East | MUSSELBURGH ROAD | At Coillesdene Terrace | Clancy Docwra for Scottish Water - lead renewal | 3-way temporary traffic lights | 2025-12-01 | 2025-12-10
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Flint Terrace | Scottish Water - manhole repair | 3-way temporary traffic lights | 2025-12-04 | 2025-12-04
Portobello/ Craigmillar | North East | BRIGHTON PLACE | At the rail bridge | Network Rail - bridge repairs | Road closed 10pm - 6am | 2025-12-04 | 2025-12-05
Portobello/ Craigmillar | North East | DUDDINGSTON ROAD | At Mountcastle Drive South | Scottish Water - ironwork repair | 4-way temporary traffic lights | 2025-12-07 | 7am 08/12/25
Portobello/ Craigmillar | North East | MILTON ROAD | Between Bailie Place and Hope Lane | Scottish Water - ironwork repair | Lane closures and contraflow. Bus lanes and bus stops suspended | 2025-12-07 | 7am 08/12/25
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Fishwives' Causeway | Scottish Water - pipe repairs | 3-way temporary traffic lights | 2025-12-13 | 2025-12-15
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD |  | Scottish Power - mains installation for housing development opposite Benhar Road | Road closed at the rail bridge for 7 days then lane closures between Whitehill Road and the development site (working eastwards) | 2026-01-05 | 3 months estimated
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | At the bowling club | Clancy Docwra for Scottish Water | Temporary traffic lights | 2026-01-06 | 2026-01-06
Portobello/ Craigmillar | North East | PEFFERMILL ROAD | At the rail bridge at Craigmillar Castle Gardens | Network Rail - installing new railway access staircase | Temporary traffic lights 10pm - 7am for 6 nights | 2026-01-10 | 2026-01-16
Sighthill/Gorgie | South West | PANSY WALK | Between Baird Drive and Balgreen community garden (just south of the rail / tram bridge) | Scottish Water / CWA - sewer upgrade | Path closed, diversion signed via footbridge and Westfield Avenue | 2025-09-22 | March 2026
Sighthill/Gorgie | South West | INGLIS GREEN ROAD | At Redhall Drive / Sainsbury's | BT Circet - repairs to collapsed manhole | 3-way temporary traffic lights, Redhall Drive closed | 2025-11-21 | Up to 5 days
Sighthill/Gorgie | South West | WESTFIELD ROAD | Between Sainsburys and Roseburn Street | Scottish Water - manhole repair | Temporary traffic lights 7pm - 7am | 2025-11-21 | 2025-01-22
Sighthill/Gorgie | South West | SAUGHTON ROAD | At Fairbrae | BT Circet - manhole repair | Temporary traffic lights | 2025-11-22 | 6am 23/11/25
Sighthill/Gorgie | South West | CALDER ROAD | At Parkhead Terrace | Telecoms company - pole replacement | Westbound lane closed and bus stops closed 10pm - 4am on Sunday night. Thereafter, 3-way temporary traffic lights on Calder Road service road | 2025-11-23 | 2025-11-27
Sighthill/Gorgie | South West | BROOMHOUSE PLACE SOUTH | At Broomhouse Walk | Scottish Water - ironwork repair | 3-way temporary traffic lights | 2025-11-24 | 2025-11-24
Sighthill/Gorgie | South West | CALDER ROAD | Between Riccarton Mains Road roundabout and Hermiston House Road | City of Edinburgh Council - verge works | Outside lane closed in both directions, off-peak hours only | 2025-11-25 | 2025-11-25
Sighthill/Gorgie | South West | GORGIE ROAD | At Robertson Avenue | Scottish Water - ironwork repair | 4-way temporary traffic lights 9.30am - 11.30am | 2025-11-30 | 2025-11-30
Sighthill/Gorgie | South West | BALGREEN ROAD | Between Stevenson Road and Stevenson Drive | Telecoms company - pole and cabinet renewal | Temporary traffic lights 8pm - 7am for 5 nights | 2025-12-01 | 2025-12-06
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Kilmarnock, kick-off 7.45pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-12-03 | 2025-12-03
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v St Mirren, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-12-13 | 2025-12-13
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Rangers, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-12-20 | 2025-12-20
Sighthill/Gorgie | South West | STENHOUSE ROAD | At HMP Saughton | Scottish Water - manhole repair | 3-way temporary traffic lights | 2026-01-08 | 7am 09/01/26
Sighthill/Gorgie | South West | ARDMILLAN TERRACE | At Slateford Road | Clancy Docwra for Scottish Water - lead renewal | 4-way temporary traffic lights | 2026-02-23 | 5 days estimated
Southside / Newington | South East | SOUTH CLERK STREET | Bernard Terrace to Lutton Place | Clancy Docwra for Scottish Water - sewer repairs | Southbound lane closure | 2025-08-13 | 26/08/25 Ongoing
Southside / Newington | South East | LIBERTON ROAD | Between Lady Road and Gilmerton Road | Collapsed manhole | Section of southbound inside lane closed | 2025-09-29 | TBC
Southside / Newington | South East | SCIENNES AREA |  | SGN - gas main renewal | Lane and parking restrictions as signed on Chalmers Crescent, Mansionhouse Road, Lauder Road, Tantallon Place and Hatton Place | 2025-10-27 | End of 2025
Southside / Newington | South East | POTTERROW | At Marshall Street | Cherry-picker access for roof inspection Not carried out, new date TBA | 4-way temporary traffic lights. 8am start, finish time TBC | 2025-11-02 | 2025-11-02
Southside / Newington | South East | KILGRASTON ROAD | At Oswald Road | City of Edinburgh Council - footway works | 3-way temporary traffic lights | 2025-11-17 | 3-4 weeks
Southside / Newington | South East | MELVILLE TERRACE | Between Moncrieff Terrace and Gladstone Terrace | Scottish Power - new service connection | Road closed | 2025-11-19 | 2025-11-23
Southside / Newington | South East | CLERK STREET | At St Patrick Square | Scottish Water - manhole repair | Lane closures / contraflow | 2025-11-21 | TBC
Southside / Newington | South East | MARSHALL STREET | Between Potterrow and Nicolson Square | City of Edinburgh Council - carriageway repairs | Road closed | 2025-11-23 | 2025-11-23
Southside / Newington | South East | NICOLSON STREET | At Nicolson Square north leg | Scottish Water - manhole repair | 3-way temporary traffic lights | 2025-11-25 | 7am 26/11/25
Southside / Newington | South East | SCIENNES | Between Summerhall and Sciennes Place | Scottish Power - crane lift | Road closed | 2025-11-25 | 2025-11-27
Southside / Newington | South East | WEST CROSSCAUSEWAY |  | Community event | Road closed between Chapel Street and Quarry Close, 9.30am - 12.30pm | 2025-11-29 | 2025-11-29
Southside / Newington | South East | OSWALD ROAD | Between Kilgraston Road and Blackford Avenue | City of Edinburgh Council - carriageway resurfacing Start date TBC, depending on progress at Kilgraston Road | Road closed | 2025-12-08 | 1 week estimated
Southside / Newington | South East | WEST NICOLSON STREET | At Nicolson Street | Clancy Docwra for Scottish Water | Road closed | 2026-01-05 | 2026-01-18
Southside / Newington | South East | MINTO STREET | At Salisbury Place | Scottish Water - manhole repair | 4-way temporary traffic lights | 2026-01-11 | 7am 12/01/26
Southside / Newington | South East | SUMMERHALL AREA |  | City of Edinburgh Council - footway extensions, traffic signals upgrade, improved cycle infrastructure, carriageway resurfacing | Daytime lane closures, temporary traffic lights and side-road closures (Melville Terrace and Sciennes) for around 10 weeks. Overnight road closures for main resurfacing work at Melville Drive junction. | 2026-01-19 | 10 weeks estimated
Trunk road network |  | M8 | Between J3A and 4 | BEAR Scotland - B792 bridge refurbishment | Contraflow and 40mph speed restriction | 2025-05-18 | 6 months estimated
Trunk road network |  | M8 | J4A | BEAR Scotland - drainage works | Westbound on-slip closed 8.30pm - 6am for 5 nights | 2025-11-17 | 2025-11-22
Trunk road network |  | M8 | J2 - J3 | BEAR Scotland - carriageway resurfacing | Road closed to westbound traffic 8.30pm - 6am for 6 weekday nights | 2025-11-19 | 2025-11-27
Trunk road network |  | M9 | J5 - J1A | BEAR Scotland - road markings | Road closed to southbound traffic 7.30pm - 6am for 3 nights | 2025-12-01 | 2025-12-04
Trunk road network |  | A720 | Millerhill to Sheriffhall | BEAR Scotland - carriageway resurfacing (at westbound on-slip) | Road closed to westbound traffic 8.30pm - 6am for 2 nights | 2025-12-03 | 2025-12-05
Trunk road network |  | M8 | At J2 | BEAR Scotland - street lighting upgrade | Westbound slip to M9 (N) closed 8pm - 4.30am each night. Diversion via M8 (W) to J3 and return. | 2025-12-08 | 2025-12-20
West Lothian |  | A71 | At Linburn Road | Scottish Power - cable installation | Temporary traffic lights | 2025-11-24 | 18/01/26 (with a break over Christmas)
Roadworks & events report
Effective from 21 November 2025