## General Road Works
Links to further information
| Traffic Scotland - realtime information on trunk roads including Edinburgh City Bypass |  |  |  | Details of Ward and Locality boundaries
SE Scotland trunk roads maintenance by BEAR Scotland
Key
| Transport for Edinburgh - Lothian Buses and Edinburgh Trams |  |  |  | New or updated information in this version
Underlined entries contain links to maps or further information
Edinburgh Travelling Safely measures and Low Traffic Neighbourhoods
| Our social media channels: |  | X (formerly Twitter) | Facebook | Threads
Excel - use the drop-down arrows to sort by any column. PDF - use CTRL + F to search for any keyword. |  |  |  | NB this is not intended to be a list of all the roadworks in Edinburgh. Please refer to the Scottish Roadworks Register website for basic information on all registered roadworks
Ward | Locality | Street | Location | Contractor / works description | Measures in place | Start | Finish
Almond | North West | MAYBURY ROAD | At Craigs Road | Construction of signalised junction | Various lane closures and contraflow arrangements. Craigs Road closed on both sides. Programme for resurfacing phase under review. | 2025-05-06 | February 2026
Almond | North West | SILVERKNOWES ROAD | Between Silverknowes Parkway and Marine Drive | City of Edinburgh Council - carriageway reconstruction | Road closed. Click cell for details of service 29 diversion. | 2025-10-01 | 05/10/25 26/10/25 Until further notice
Almond | North West | GLASGOW ROAD | Between Gogar and Newbridge | City of Edinburgh Council - drainage surveys | Various lane closures, off-peak daytime until end of November then nighshift through December and early January. | 2025-10-28 | January 2026
Almond | North West | TURNHOUSE ROAD | At the rail bridge west of Turnhouse Farm Road | Network Rail - parapet adjustments as part of electrification project | Temporary traffic lights | 2025-11-08 | 2026-01-05
Almond | North West | MAIN STREET, DAVIDSON'S MAINS | At Cramond Road South / Quality Street | Power and water main connections for new development. Cable jointing completed 11/12/25. Reinstatement to be carried out 12/12/25 then 48hrs curing time and site clear-up on 15/12/25. | 3-way temporary traffic lights, East Barnton Gardens closed | 2025-11-17 | 12/12/25 15/12/25
Almond | North West | STANDINGSTANE ROAD | Between Milton Farm Road and the rail bridge | Network Rail - construction of temporary site access | Temporary traffic lights | 2025-12-08 | 2025-12-14
Almond | North West | GLASGOW ROAD | Opposite Norton House entrance | Scottish Power - new service connection | Off-peak citybound lane closure, Monday - Thursday only | 2025-12-11 | 2025-12-24
Almond | North West | OLD LISTON ROAD | At Cliftonhall Road / Huly Hill Road | Telecoms company - clearing blocked cable ducts | 4-way temporary traffic lights (morning only) | 2025-12-13 | 2025-12-13
Almond | North West | STIRLING ROAD | At the M90 bridge (just west of the leisure centre) | Telecoms company - cherry-picker access to phone mast | Temporary traffic lights | 2025-12-15 | 2025-12-15
Almond | North West | GOGAR STATION ROAD | Between Glasgow Road and Gogarbank | Places for People - new road layout | Road closed (in sections as work progresses). Temporary traffic lights as required at RBS entrance / Business School entrance. | 2026-01-19 | February 2027
Almond | North West | WHITEHOUSE ROAD | At Braepark Road | Scottish Water - manhole repair | 3-way temporary traffic lights | 2026-01-20 | 20/01/26
Almond | North West | CRAMOND ROAD SOUTH | Between Barnton Avenue and Quality Street, to include Main Street mini-roundabout | City of Edinburgh Council - carriageway resurfacing | Phase 1 - roundabout and all approaches closed; Phase 2 - Cramond Road South closed. | 2026-02-16 | 3 weeks estimated
City Centre | South East | NORTH BRIDGE |  | City of Edinburgh Council / Balfour Beatty - bridge refurbishment | East footway closed, pedestrian access via west footway. One traffic lane open in each direction (as of 21/04/23). | 2020-02-15 | Summer 2026
City Centre | South East | TARVIT STREET |  | Redevelopment of King's Theatre | Tarvit Street closed between Home Street and Drumdryan Street. Drumdryan Street northbound only. NCR 75 closed, cycle diversion signed via Valleyfield Street | 2023-02-14 | Late 2026
City Centre | South East | DEVON PLACE | Between West Coates and no. 4 | For Ogilvie Construction | Road closed to southbound traffic. | 2023-06-06 | March 2026
City Centre | South East | ROSE STREET | At South St David Street | Redevelopment of former Scottish Widows / Sainsbury's building | Road closed, delivery access via Hanover Street | 2025-06-01 | TBC
City Centre | South East | KING'S STABLES ROAD | Between Lothian Road and the entrance to the NCP car park by Barrace Steps | Edinburgh's Christmas | Road closed to all traffic 27/10 - 24/11 and 08/12 - 18/01. Road closed to westbound traffic except cycles 25/11 - 08/12. | 2025-10-27 | 2026-01-18
City Centre | South East | GEORGE STREET | Between Charlotte Square and Frederick Street | Edinburgh's Christmas | Road closed except for cycles. Loading permitted on westbound side, 6.30am - 9.30am daily. Castle Street / North Castle Street closed 10am - 11pm each day from 06/11/25. | 2025-11-05 | 2026-01-18
City Centre | South East | WAVERLEY BRIDGE |  | Edinburgh's Christmas | Road closed except for cycles. Loading permitted 10pm - 10am daily, via Market Street. | 2025-11-15 | 2025-12-28
City Centre | South East | YORK LANE | East / West section | Building development | Road closed | 2025-11-24 | April 2027
City Centre | South East | ALBANY STREET LANE | At Broughton Street | Clancy Docwra - sewer repair for Scottish Water | Road closed | 2025-12-04 | 15/12/25 estimated
City Centre | South East | CENTRAL EDINBURGH |  | Edinburgh's Hogmanay - Street Party | Road closures, pedestrian closures and parking restrictions, phased in from 27/12/25. Click cell for details. | 2025-12-27 | 2026-01-02
City Centre | South East | CENTRAL EDINBURGH |  | Edinburgh's Hogmanay - Torchlight Procession | City centre road and pedestrian closures from 3pm, click cell for more details | 2025-12-29 | 2025-12-29
City Centre and Southside / Newington | South East | HOLYROOD PARK AREA |  | New Year's Day triathlon | Holyrood Park Road, Queen's Drive, Holyrood Gait and Horse Wynd closed 8am - 5pm. | 2026-01-01 | 2026-01-01
City Centre | South East | WAVERLEY BRIDGE |  | Edinburgh's Christmas | Road closed 10am Saturday - 10pm Sunday, except for cycles. Loading permitted 10pm - 10am daily, via Market Street. | 2026-01-03 | 2026-01-04
City Centre | South East | LEVEN STREET | At Gilmore Place | For relocation of site cabins at King's Theatre | 3-way temporary traffic lights | 2026-01-09 | 2026-01-09
City Centre | South East | LEVEN STREET AREA |  | City of Edinburgh Council - footway extensions, traffic signals improvements, cycle insfrastructure upgrades, carriageway resurfacing | Lane closures. Temporary traffic lights at Gilmore Pace junction from 19/01/26. Valleyfield Street closed for the majority of the scheme. | 2026-01-12 | Mid April estimated
City Centre | South East | GILMORE PLACE |  | City of Edinburgh Council - carriageway resurfacing | Road closed in sections. Phase 1 (of 3) between Leven Street and Leamington Terrace for 3 weeks, Monday - Friday only. | 2026-01-19 | Early May 2026
City Centre | South East | ROSE STREET SOUTH LANE | Section between South Charlotte Street and Castle Street | Energy Assets - investigation works | Road closed | 2026-01-19 | 2026-02-06
City Centre | South East | QUEEN STREET / ALBYN PLACE |  | Comex2000 for Virgin Media | Lane closure northbound North Charlotte Street / eastbound Albyn Place | 2026-01-26 | 2026-01-31
City Centre | South East | ALBYN PLACE |  | Clancy Docwra for Scottish Water | Eastbound inside lane closed | 2026-02-15 | 2026-02-22
Colinton / Fairmilehead | South West | COLINTON ROAD | At Patie's Road | Openreach - ducting installation | 3-way temporary traffic lights, Elliot Road closed | 2025-12-16 | 2025-12-19
Colinton / Fairmilehead | South West | PATIE'S ROAD | At no. 8 | BT - manhole repair | Temporary traffic lights | 2026-01-12 | 2026-01-14
Colinton / Fairmilehead | South West | BONALY ROAD | Between West Carnethy Avenue and Munro Drive | BT - manhole repair | Road closed | 2026-02-16 | 2026-02-17
Corstorphine / Murrayfield | North West | CORSTORPHINE ROAD | At Murrayfield | Scottish Water - major works to install combined sewer overflow (CSO) | Temporary traffic lights. Ormidale Terrace closed. Westbound bus stop closed, please use the next stop. | 2025-06-08 | 2025-12-19
Corstorphine / Murrayfield | North West | BALGREEN ROAD and SAUGHTON CRESCENT |  | City of Edinburgh Council - carriageway resurfacing and active travel improvements. | Daytime lane closures and temporary traffic lights for preparatory and footway works, nightshift road closures for main resurfacing work. Currently Balgreen Road closed between Saughtonhall Drive and Glendevon Avenue plus Saughtonhall Avenue West closed | 2025-10-20 | May 2026 (with a break over Christmas)
Corstorphine / Murrayfield | North West | CORSTORPHINE AREA |  | Corstorphine Connections scheme - replacing some temporary measures with permanent materials. | 3-way temporary traffic lights on Corstorphine High Street and Manse Road closed from 01/12/25 for 2 weeks. Kirk Loan closed from 05/01/25 for 4 - 6 weeks. | 2025-12-01 | February 2026
Corstorphine / Murrayfield | North West | CRAIGLEITH VIEW |  | City of Edinburgh Council - carriageway resurfacing | Road closed | 2025-12-08 | 12/12/25 19/12/25
Corstorphine / Murrayfield | North West | MURRAYFIELD AREA |  | 1872 Cup at Scottish Gas Murrayfield, kick-off 3pm | Multiple road closures and parking restrictions affecting residential streets around Murrayfield, A8 corridor and West Approach Road. Click cell for full details. | 2025-12-27 | 2025-12-27
Corstorphine / Murrayfield | North West | BELGRAVE ROAD | At the tennis club | Clancy Docwra for Scottish Water | Road closed to through traffic | 2026-01-10 | 13/01/26
Corstorphine / Murrayfield | North West | ELLERSLY ROAD |  | City of Edinburgh Council - carriageway resurfacing | Road closed (excluding any affected 6 Nations dates) | 2026-01-12 | Up to 6 weeeks
Craigentinny/ Duddingston | North East | DUDDINGSTON LOW ROAD |  | Historic Environment Scotland - risk of rock falls | Road closed to motor vehicles. Road closed to all path users from Tuesday 18/03/25, pedestrian and cyclist diversion via Innocent railway path. Reopened to pedestrians and cyclists 07/08/25, cyclists please dismount through the barrier system at Samson's Ribs. | 2025-03-15 | Until further notice
Craigentinny/ Duddingston | North East | LONDON ROAD (WOLSELEY TERRACE) | At Jock's Lodge | Clark Contracts - building development (demolition of existing buildings then construction of new premises) | North side footway and cycleway restriction for installation of footway extension, hoarding and scaffolding. Occasional occupation of eastbound inside lane for deliveries. Section of west footway on Restalrig Road South closed. | 2025-11-24 | December 2027
Craigentinny/ Duddingston | North East | LONDON ROAD (CADZOW PLACE) | Between Abbey Lane and Montrose Terrace | Scottish Water - meter exchange | Citybound inside lane closed, temporary stop for citybound buses | 2026-01-08 | 2026-01-15
Craigentinny/ Duddingston | North East | WILLOWBRAE ROAD | At Willowbrae Avenue / Piershill Terrace | SGN - ironwork repairs | Contraflow on Willowbrae Road. No right turns into or out of Willowbrae Avenue and Piershill Terrace. | 2026-01-13 | 2026-01-15
Craigentinny/ Duddingston | North East | MORAY PARK TERRACE |  | Virgin Media | Temporary traffic lights | 2026-01-13 | 2026-01-20
Craigentinny/ Duddingston | North East | WILLOWBRAE GARDENS | At Baronscourt Terrace | Clancy Docwra for Scottish Water | Road closed | 2026-02-03 | 2026-02-12
Craigentinny/ Duddingston | North East | NORTHFIELD FARM AVENUE | At Mountcastle Drive North | Clancy Docwra for Scottish Water | Road closed | 2026-03-02 | 2026-03-06
Craigentinny/ Duddingston | North East | ABBEYHILL | At Brae House | Virgin Media - ironwork repairs | Temporary traffic lights | 2026-03-08 | 7am 09/03/26
Craigentinny/ Duddingston | North East | PORTOBELLO ROAD | Between Piershill Terrace and Piersfield Grove | Scottish Water - ironwork repair | Temporary traffic lights | 2026-03-29 | 7am 30/03/26
Drum Brae / Gyle | North West | SOUTH GYLE ROAD | At the rail bridge | Network Rail - renewing rail bridge | Road closed. Access to the station car park via South Gyle Broadway - Gogarloch Road. Station car park closed 24/11 - 05/12/25. | 2025-07-28 | April 2026
Drum Brae / Gyle | North West | LADYWELL AVENUE | Between Kirklands and Broomhall Crescent | Network Rail - renewing rail bridge | Road closed | 2025-08-21 | August 2026
Drum Brae / Gyle | North West | MEADOW PLACE ROAD | At the rail bridge | City of Edinburgh Council - for upgrade works at Torwood Path | Temporary traffic lights (removed for Christmas period) | 2025-12-03 | March 2026
Drum Brae / Gyle | North West | SOUTH GYLE ACCESS |  | City of Edinburgh Council - installation of segregated cycle lane | Lane closures. Road closures April 2026 for final surfacing. | 2025-12-03 | 5-6 months
Drum Brae / Gyle | North West | MEADOW PLACE ROAD | At the rail bridge | Network Rail | Temporary traffic lights, cycle lane closed | 2026-01-16 | 1 week estimated
East Lothian |  | NORTH HIGH STREET, MUSSELBURGH | At the Ship Inn | SGN - gas leak repairs | Temporary traffic lights, Harbour Road closed | 2025-11-28 | TBC
Forth | North West | CRAIGHALL ROAD | Between Craighall Avenue and Grandville | Refurbishment of Trinity Academy | Road closed | 2025-06-30 | May 2028
Forth | North West | GRANTON CRESCENT | At Wardieburn Place North | Scottish Water - lead renewal Work extended | Roads closed | 2025-12-09 | 12/12/25 19/12/25 estimated
Forth | North West | WATERFRONT BROADWAY | Between West Granton Road and Morrisons entrance | Clancy Docwra - mains repairs for Scottish Water | One lane closed in each direction | 2025-12-09 | 18/12/25 estimated
Forth | North West | BOSWALL PARKWAY | Between Pilton Avenue and Boswall Terrace | Clancy Docwra for Scottish Water | Temporary traffic lights | 2026-01-17 | 2026-01-21
Fountainbridge/ Craiglockhart | South West | HARRISON ROAD | At the dog-leg bend where it crosses the cycle path and at the canal bridge | City of Edinburgh Council - bridge repairs | Road closed. Topside footway closures as signed. Road bridge expected to be renewed by end of 2025. Trial holes ongoing at canal bridge. | 2025-02-18 | Spring 2026 TBC
Fountainbridge/ Craiglockhart | South West | DUNDEE STREET | At West Approach Road / Angle Park Terrace | Scottish Power - cable fault | Temporary traffic lights (from around 4pm on Monday) | 2025-12-08 | TBC
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Robertson Avenue | Scottish Water - manhole repairs (x3) | 3-way temporary traffic lights, Hermand Crescent closed. 7pm - 7am | 2025-12-12 | 2025-12-13
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | At Chesser Avenue | Scottish Water - manhole repair | 3-way temporary traffic lights | 2026-01-08 | 7am 09/01/26
Fountainbridge/ Craiglockhart | South West | HUTCHISON PLACE | At Slateford Road | Scottish Water - ironwork repair | Road closed | 2026-01-06 | 2026-01-06
Fountainbridge/ Craiglockhart | South West | SLATEFORD ROAD | At Appin Terrace | Scottish Water - ironwork repair | 2-way temporary traffic lights 7pm - 7am | 2026-01-16 | 2026-01-17
Fountainbridge/ Craiglockhart | South West | GORGIE ROAD | Between Ford's Road and Balgreen Road | Scottish Water - major works to install combined sewer overflow (CSO) | Road closed and section of north footway closed. | 2026-01-25 | July 2026
Inverleith | North West | INVERLEITH TERRACE | At Arboretum Avenue | Clancy Docwra - sewer repair for Scottish Water Work finished | 3-way temporary traffic lights | 2025-12-10 | TBC
Inverleith | North West | CRAIGLEITH HILL AVENUE | At Craigleith Hill Green | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2025-12-11 | 2025-12-20
Inverleith | North West | EYRE PLACE AREA | Between Eyre Terrace and Canon Street | Morrisons Construction - drainage installation for development site | Phase1 - Canon Street closed for 3 weeks. Phase 2 - temporary traffic lights on Eyre Place. Phase 3 - Eyre Place closed at Eyre Crescent. | 2026-01-05 | 11 weeks estimated
Inverleith | North West | HAMILTON PLACE | At Kerr Street / Deanhaugh Street | Mackenzie Construction for Scottish Water - installation of sewer monitoring equipment | 4-way temporary traffic lights | 2026-01-08 | 2026-01-08
Inverleith | North West | LEARMONTH TERRACE | Between Queensferry Road and Comely Bank Avenue | Clancy Docwra for Scottish Water - lead renewal | Road closed | 2026-01-12 | 2026-01-16
Inverleith | North West | TELFORD ROAD | Groathill Road North to Telford Drive | SGN - gas main renewal | Phase 1 - 3-way temporary traffic lights at Groathill Road North with Groathill Road South closed (approximately 1 week). Phase 2 - lane closures between Groathill Avenue and Telford Drive with Telford Drive closed. | 2026-01-26 | 3 weeks estimated
Inverleith | North West | COMELY BANK ROAD | At Fettes Avenue | Scottish Water - lead renewal | 3-way temporary traffic lights, Learmonth Avenue closed | 2026-02-17 | 5 days estimated
Leith | North East | LINDSAY ROAD BRIDGE | Pedestrian / cycle bridge between Nicholfield and Lindsay Road main carriageway | City of Edinburgh Council - public safety measure | Bridge closed, pedestrian and cycle diversion as signed. Hawthornvale Path beneath remains open | 2021-12-15 | Until further notice
Leith | North East | HENDERSON STREET AREA |  | City of Edinburgh Council - construction of segregated cycle lane | Lane closures, parking restrictions, temporary traffic lights if required. Currently temporary traffic lights at northern end and Parliament Street closed at Henderson Street. | 2024-12-03 | End of 2025
Leith | North East | DUKE STREET |  | BT Circet - manhole repair | Temporary traffic lights | 2025-12-09 | 3 days estimated
Leith | North East | COMMERCIAL STREET | At North Junction Street / Lindsay Road / Ocean Drive | Scottish Water - repairs to burst pipe | 4-way temporary traffic lights | 2025-12-12 | TBC
Leith | North East | LEITH |  | Abnormal load Postponed | Bath Road - Salamander Street - A199 - A1 - A720 - A68 - A697 (9pm departure) | 2025-12-13 | 2025-12-14
Leith | North East | COMMERCIAL STREET | At Ocean Drive / Lindsay Road | Scottish Water - manhole repair | 4-way temporary traffic lights | 2026-01-07 | 7am 08/01/26
Leith | North East | BERNARD STREET | At Shore / Commercial Street | Scottish Water - mains surveys | 3-way temporary traffic lights, Bernard Street closed between Shore and Timber Bush, 7pm - 7am | 2026-01-29 | 2026-01-30
Leith | North East | FERRY ROAD | Between Madeira Street and Leith library | Scottish Water - manhole repair | Road closed 7pm - 7am | 2026-02-01 | 2026-02-02
Leith | North East | SHORE | Between Timber Bush and Tower Street | Scottish Water - mains surveys | Road closed | 2026-02-02 | 2026-02-02
Leith | North East | SHORE | At Tower Street | Scottish Water - mains surveys | Roads closed | 2026-02-03 | 2026-02-03
Leith Walk | North East | ST MARK'S PATH |  | Development works at former Powderhall bowling green site | Path closed. Diversion signed via Warriston Road - Hughes Close - Powderhall Road - Beaverhall Road - Broughton Road | 2025-11-17 | Until further notice
Leith Walk | North East | HAWKHILL AVENUE | At St Clair Street | Telecoms company - ducting installation for Vodafone | 3-way temporary traffic lights | 2025-12-08 | 2025-12-12
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Hearts, kick-off 12.30pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-12-27 | 2025-12-27
Leith Walk | North East | EASTER ROAD AREA |  | Hibs v Aberdeen, kick-off 7.45pm | Roads closed before and after the match: Hawkhill Avenue / Close, St Clair Street, Albion Place / Road / Terrace / Gardens, Harrismith Place. Local parking restrictions as signed | 2025-12-30 | 2025-12-30
Leith Walk | North East | EASTER ROAD | At Lorne Street / St Clair Avenue | Scottish Water - manhole repair | 3-way temporary traffic lights, Lorne Street closed | 2026-01-06 | 7am 07/01/26
Leith Walk | North East | ARTHUR STREET | At Pilrig Street | Scottish Water - mains disconnection | Road closed to eastbound traffic | 2026-01-12 | 2026-01-16
Leith Walk | North East | DRYDEN STREET | At Pilrig Street | Scottish Water - mains disconnection | Road closed | 2026-01-19 | 2026-01-21
Leith Walk | North East | EASTER ROAD | Between Sunnyside and Drum Terrace | Clancy Docwra for Scottish Water - lead renewal | 4-way temporary traffic lights | 2026-02-08 | 2026-02-10
Leith Walk | North East | PILRIG GARDENS |  | Clancy Docwra for Scottish Water - lead renewal | Road closed to through traffic | 2026-02-11 | 2026-02-15
Liberton / Gilmerton | South East | GILMERTON ROAD | Just south of Kingston Avenue | Clancy Docwra - sewer repair for Scottish Water | 3-way temporary traffic lights | 2025-12-10 | TBC
Liberton / Gilmerton | South East | NEWTOFT STREET | Between Hyvot Park and Hyvot Bank Avenue | Scottish Power - cable fault | Lane closures, possible temporary traffic lights | 2025-12-10 | TBC
Liberton / Gilmerton | South East | KAIMES CROSSROADS |  | City of Edinburgh Council - repairs to collapsed manhole | 4-way temporary traffic lights 7pm Friday - 7pm Sunday | 2025-12-12 | 2025-12-14
Liberton / Gilmerton | South East | MOREDUNVALE ROAD | At Moredun Park Gardens | BT Morrison - pole replacement | Temporary traffic lights | 2025-12-12 | 2025-12-12
Liberton / Gilmerton | South East | MOREDUN PARK ROAD | At Moredun Park Gardens | BT Morrison - clearing blocked cable ducts | 2-way temporary traffic lights, Moredun Park Gardens closed on both sides | 2025-12-13 | 2025-12-14
Liberton / Gilmerton | South East | CRAIGOUR DRIVE | Between Craigour Crescent and Craigour Gardens | Crane lift and building works | Road closed to through traffic (between 66a and 72a) | 2025-12-15 | 2025-12-19
Liberton / Gilmerton | South East | KEDSLIE ROAD | At Liberton Drive | BT Morrison - clearing blocked cable ducts | Road closed | 2025-12-15 | 2025-12-19
Liberton / Gilmerton | South East | MOREDUN PARK ROAD | At Gilmerton Road | BT Circet - pole replacement | Road closed | 2025-12-15 | 2025-12-15
Liberton / Gilmerton | South East | GILMERTON ROAD | At The Spinney | Clancy Docwra for Scottish Water | 3-way temporary traffic lights | 2026-01-13 | 2026-01-22
Liberton / Gilmerton | South East | LASSWADE ROAD | At Captain's Road / Gilmerton Dykes Street | Scottish Water - manhole repair | 4-way temporary traffic lights | 2026-03-15 | 7am 16/03/26
Midlothian |  | MILLERHILL ROAD | Between Shawfair Spine Road and Newton Village | Carriageway upgrade / footway widening / traffic signal installation / utility diversion works / district heating system installation | Temporary traffic lights | 2025-08-11 | April 2026
Midlothian |  | NEWTON CHURCH ROAD | At A6106 Millerhill Road | Advance Construction - utility installations | Road closed | 2025-12-01 | 2 weeks estimated
Midlothian |  | OLD PENTLAND ROAD | At Hillside Cottage | Scottish Water - pipe repairs | Temporary traffic lights | 2025-12-11 | 5 days estimated
Morningside | South East | MARCHMONT ROAD | At Marchmont Crescent | Scottish Power - cable installation | 2-way temporary traffic lights, Marchmont Crescent and Spottiswoode Road closed | 2025-11-17 | 3 months estimated
Morningside | South East | COMISTON ROAD | At Greenbank Crescent | Scottish Power - cable fault | 3-way temporary traffic lights, Greenbank Drive closed | 2025-12-09 | TBC
Morningside | South East | GREENBANK CRESCENT | At Greenbank Row | Scottish Water - lead renewal | 2-way temporary traffic lights, Greenbank Row closed and bus stops closed in both directions | 2025-12-09 | 2025-12-13
Morningside | South East | GREENBANK CRESCENT | At Braid Burn | Scottish Water - manhole repair | Temporary traffic lights | 2025-12-19 | 2025-12-19
Morningside | South East | BRUNTSFIELD PLACE | At Viewforth | Clancy Docwra for Scottish Water - valve repairs | 2-way temporary traffic lights, Viewforth closed | 2026-01-19 | 2026-01-28
Pentland Hills | South West | COCKBURN CRESCENT | At the south west corner between Highlea Circle and Whitelea Road | Clancy Docwra - repairs to burst pipe for Scottish Water | Temporary traffic lights | 2025-12-09 | TBC
Pentland Hills | South West | RICCARTON MAINS ROAD | At the rail bridge | City of Edinburgh Council - high-friction surfacing | Temporary traffic lights 8.30am - 4pm each weekday | 2025-12-10 | 7 days, weather permitting
Pentland Hills | South West | NORTH STREET, RATHO | At Main Street | Christmas lights switch-on | Road closed 4.30pm - 7.30pm | 2025-12-12 | 2025-12-12
Pentland Hills | South West | WESTER HAILES ROAD | At the railway bridge between Murrayburn Road and Clovenstone Road | Network Rail - bridge inspection | Road closed 10pm - 6am for 2 nights: Monday night road closed northbound, no access beyond Harvester's Way. Tuesday night road closed southbound, no access to Plaza car park. | 2025-12-15 | 2025-12-17
Pentland Hills | South West | LANARK ROAD WEST | Between Sainsbury's garage and Provost Haugh | Scottish Water - valve repairs | 3-way temporary traffic lights | 2025-12-17 | 2025-12-18
Pentland Hills | South West | BELMONT ROAD | Between Baberton Avenue and Juniper Grove | Clancy Docwra for Scottish Water | Road closed | 2026-01-20 | 2026-01-20
Pentland Hills | South West | MURRAYBURN DRIVE | At Wester Hailes Road bridge | City of Edinburgh Council - bridge renewal | Road closed and contraflow on Wester Hailes Road | 2026-02-16 | 9 months estimated
Portobello/ Craigmillar | North East | NIDDRIE MAINS ROAD | At Niddrie Farm Grove | Maintenance work at phone mast Work postponed | Temporary traffic lights 8pm - 6am | 2025-11-25 | 2025-11-26
Portobello/ Craigmillar | North East | MUSSELBURGH ROAD | At Coillesdene Terrace | Clancy Docwra for Scottish Water - lead renewal Work postponed | 3-way temporary traffic lights | 2025-12-01 | 2025-12-10
Portobello/ Craigmillar | North East | PORTOBELLO HIGH STREET | At Fishwives' Causeway | Scottish Water - pipe repairs | 3-way temporary traffic lights | 2025-12-13 | 2025-12-15
Portobello/ Craigmillar | North East | MILTON ROAD | Between Bailie Place and Hope Lane | Scottish Water - ironwork repair | Lane closures and contraflow. Bus lanes and bus stops suspended | 2025-12-14 | 7am 15/12/25
Portobello/ Craigmillar | North East | FILLYSIDE ROAD | At Seafield Road | Cityfibre - clearing blocked ducts | No entry from Seafield Road East, no right turn out of Fillyside Road. | 2025-12-15 | 2025-12-15
Portobello/ Craigmillar | North East | SIR HARRY LAUDER ROAD | Between Baileyfield Road and Fishwives' Causeway | City of Edinburgh Council - footbridge inspection | Off-peak lane clsoures | 2025-12-16 | 2025-12-16
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD |  | Scottish Power - mains installation for housing development opposite Benhar Road | Road closed at the rail bridge for 7 days then lane closures between Whitehill Road and the development site (working eastwards) | 2026-01-05 | 3 months estimated
Portobello/ Craigmillar | North East | NEWCRAIGHALL ROAD | At the bowling club | Clancy Docwra for Scottish Water | Temporary traffic lights | 2026-01-06 | 2026-01-06
Portobello/ Craigmillar | North East | PEFFERMILL ROAD | At the rail bridge at Craigmillar Castle Gardens | Network Rail - installing new railway access staircase | Temporary traffic lights 10pm - 7am for 6 nights | 2026-01-10 | 2026-01-16
Portobello/ Craigmillar | North East | GREENDYKES ROAD | At the junction with Tudsbury Avenue and Niddrie Marischal Place | Scottish Water - manhole repair | All approaches closed | 2026-01-22 | 7am 23/01/26
Portobello/ Craigmillar | North East | SEAVIEW TERRACE | At Milton Road East | Clancy Docwra for Scottish Water - lead renewal | Temporary traffic lights | 2026-01-22 | 2026-01-31
Sighthill/Gorgie | South West | PANSY WALK | Between Baird Drive and Balgreen community garden (just south of the rail / tram bridge) | Scottish Water / CWA - sewer upgrade | Path closed, diversion signed via footbridge and Westfield Avenue | 2025-09-22 | March 2026
Sighthill/Gorgie | South West | GORGIE ROAD | At Robertson Avenue | Scottish Water - ironwork repair Work postponed | 4-way temporary traffic lights 9.30am - 11.30am | 2025-11-30 | 2025-11-30
Sighthill/Gorgie | South West | BANKHEAD TERRACE | At Bankhead Drive (east side) | SGN - gas leak repairs | Road closed | 2025-12-01 | TBC
Sighthill/Gorgie | South West | CALDER ROAD | At Longstone roundabout | City of Edinburgh Council - barriers renewal No work carried out as at 12/12/25, new dates TBA | Lane closures | 2025-12-01 | Up to 10 days
Sighthill/Gorgie | South West | CALEDONIAN ROAD AREA |  | City of Edinburgh Council - carriageway resurfacing, footway improvements and traffic calming works | Phased road closures affecting Caledonian Road / Crescent / Place and Orwell Terrace / Place | 2025-12-09 | April 2026
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Rangers, kick-off 1.30pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2025-12-21 | 2025-12-21
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v Livingston, kick-off 3pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2026-01-03 | 2026-01-03
Sighthill/Gorgie | South West | STENHOUSE ROAD | At HMP Saughton | Scottish Water - manhole repair | 3-way temporary traffic lights | 2026-01-08 | 7am 09/01/26
Sighthill/Gorgie | South West | LONGSTONE ROAD | Between the junctions with Longstone Crescent | Clancy Docwra for Scottish Water - sewer survey / clean | Temporary traffic lights | 2026-01-10 | 2026-01-10
Sighthill/Gorgie | South West | GORGIE AREA |  | Hearts v St Mirren, kick-off 7.45pm | McLeod Street, Wheatfield Street and Wheatfield Place closed before and after the match, Gorgie area parking restrictions as signed | 2026-01-14 | 2026-01-14
Sighthill/Gorgie | South West | INGLIS GREEN ROAD | At the rail bridge | Network Rail - bridge maintenance | Temporary traffic lights 8pm - 6am each night | 2026-01-19 | 4 weeks estimated
Sighthill/Gorgie | South West | ARDMILLAN TERRACE | At Slateford Road | Clancy Docwra for Scottish Water - lead renewal | 4-way temporary traffic lights | 2026-02-23 | 5 days estimated
Southside / Newington | South East | SCIENNES AREA |  | SGN - gas main renewal | Lane and parking restrictions as signed on Chalmers Crescent, Mansionhouse Road, Lauder Road, Tantallon Place and Hatton Place | 2025-10-27 | End of 2025
Southside / Newington | South East | POTTERROW | At Marshall Street | Cherry-picker access for roof inspection Not carried out, new date TBA | 4-way temporary traffic lights. 8am start, finish time TBC | 2025-11-02 | 2025-11-02
Southside / Newington | South East | OSWALD ROAD | Between Kilgraston Road and Blackford Avenue | City of Edinburgh Council - carriageway resurfacing Road reopened 09/12/25, an additional closure will be required to complete line marking, date TBC | Road closed | 2025-12-01 | 1 week estimated
Southside / Newington | South East | NICOLSON STREET | At West Crosscauseway | Clancy Docwra - sewer repair for Scottish Water | Temporary traffic lights | 2025-12-05 | 12/12/25 estimated
Southside / Newington | South East | BLACKFORD AVENUE | At Eva Place | Scottish Water - repairs to burst pipe | Lane closures / contraflow, Eva Place closed | 2025-12-08 | 17/12/25 estimated
Southside / Newington | South East | KIRKHILL ROAD | At Priestfield Road | BT Circet - pole replacement | Road closed | 2025-12-12 | 2025-12-12
Southside / Newington | South East | SCIENNES | Between Summerhall and Sciennes Place | Scottish Power - crane lift | Road closed | 2025-12-15 | 2025-12-17
Southside / Newington and City Centre | South East | HOLYROOD PARK AREA |  | New Year's Day triathlon | Holyrood Park Road, Queen's Drive, Holyrood Gait and Horse Wynd closed 8am - 5pm. | 2026-01-01 | 2026-01-01
Southside / Newington | South East | WEST NICOLSON STREET | At Nicolson Street | Clancy Docwra for Scottish Water | Road closed | 2026-01-05 | 2026-01-18
Southside / Newington | South East | MINTO STREET | At Salisbury Place | Scottish Water - manhole repair | 4-way temporary traffic lights | 2026-01-11 | 7am 12/01/26
Southside / Newington | South East | SUMMERHALL AREA |  | City of Edinburgh Council - footway extensions, traffic signals upgrade, improved cycle infrastructure, carriageway resurfacing | Daytime lane closures, temporary traffic lights and side-road closures (Melville Terrace and Sciennes) for around 10 weeks. Overnight road closures for main resurfacing work at Melville Drive junction. | 2026-01-19 | 10 weeks estimated
Southside / Newington | South East | PEFFERMILL ROAD | Between the primary school and Prestonfield Avenue | Scottish Water - valve repairs | 3-way temporary traffic lights | 2026-01-27 | 30/01/26 estimated
Trunk road network |  | M8 | Between J3A and 4 | BEAR Scotland - B792 bridge refurbishment. Work pauses 19/12/25, resumes 19/01/26 for 2 months | Contraflow and 40mph speed restriction (to be removed on 19/12/25). Road closed both ways 8.30pm - 6am on nights of 17 and 18/01/26 to reinstall traffic management. | 2025-05-18 | 6 months estimated
Trunk road network |  | M8 | Between J1 and J2 | BEAR Scotland - central reserve barrier replacement | Lane closures in both directions, 8.30pm - 6am each night | 2025-11-30 | 2025-12-19
Trunk road network |  | M90 | M9 J1A to M90 J1 | BEAR - bridge repairs | Road closed to northbound traffic 8pm - 6am for 5 nights | 2025-12-08 | 2025-12-13
Trunk road network |  | M8 | At J2 | BEAR Scotland - street lighting upgrade | Westbound slip to M9 (N) closed 8pm - 4.30am each night. Diversion via M8 (W) to J3 and return. | 2025-12-08 | 2025-12-20
Trunk road network |  | A720 | Between Calder and Baberton | Network Rail - bridge inspection | Road closed 10pm - 6am for 2 nights (westbound on Wednesday night and eastbound on Thursday night) | 2025-12-17 | 2025-12-19
West Lothian |  | A71 | At Linburn Road | Scottish Power - cable installation | Temporary traffic lights | 2025-11-24 | 18/01/26 (with a break over Christmas)
Roadworks & events report
Effective from 12 December 2025